## Sheet1
Failed Start List
Project: Factories Low-process Unit (HAFR Al Batin)
2026-09-21
# | P6 Activity ID | P6 Activity Description | Planned Start | Forecast Start | Variance | Remarks
1 | HFR1-05-4590 | Site Works & External Networks Completed |  |  | 0 | Not required
2 | HFR1-05-4620 | Main Buildings Architectural Completed |  |  | 0 | Not required
3 | HFR1-05-3390 | Main Buildings Structure Completed |  |  | 0 | Not required
4 | HFR1-05-4400 | Mosque Works Completed |  |  | 0 | Not required
5 | HFR1-05-2730 | External Paint Touch-up & Inspection | 2026-05-30 | 06-Aug-26 A | -73 | Not required
6 | HFR1-05-2630 | External Paint Primer + Final Coat | 2026-05-03 | 06-Aug-26 A | -71 | Not required
7 | HFR1-05-2600 | Paint Primer + Putty + Final Coat INSIDE | 2026-04-25 | 24-Aug-26 A | -71 | Not required
8 | HFR1-05-2820 | Specialites Fittings | 2026-07-13 | 01-Sep-26 A | -71 | Not required
9 | HFR1-05-2900 | Testing plumping system & Final Inspection | 2026-09-06 | 04-May-26 A | -71 | Not required
10 | HFR1-05-2910 | Fire Fighting Testing (Hydrostatic Test) & Final Inspection | 2026-09-16 | 02-May-26 A | -25 | Not required
11 | HFR1-05-2070 | Power System and lighting and lightcurrent Testing (Continuity + Insulation) & Final Inspection | 2026-08-12 | 01-Apr-26 A | -72 | Not required
12 | HFR1-05-2080 | Comission of Panel boards ( cables and testing) | 2026-08-19 | 14-Jun-26 A | -72 | Not required
13 | HFR1-05-2100 | Comission of Lighting Fixtures Installations /LED lighting | 2026-08-30 | 29-Jun-26 A | -72 | Not required
14 | HFR1-05-1530 | External Paint Touch-up & Inspection | 2026-06-08 | 06-Aug-26 A | -69 | Not required
15 | HFR1-05-1480 | External Paint Primer + Final Coat | 2026-05-12 | 08-Aug-26 A | -69 | Not required
16 | HFR1-05-1450 | Paint Primer + Putty + Final Coat INSIDE | 2026-05-04 | 23-Aug-26 A | -69 | Not required
17 | HFR1-05-1570 | Specialites Fittings | 2026-07-06 | 01-Sep-26 A | -69 | Not required
18 | HFR1-05-1790 | Testing plumping system & Final Inspection | 04-May-26 A | 04-Aug-26 A | -69 | Not required
19 | HFR1-05-1800 | Fire Fighting Testing (Hydrostatic Test) & Final Inspection | 04-May-26 A | 05-Sep-26 A | -69 | Not required
20 | HFR1-05-2210 | Power System and lighting and lightcurrent Testing (Continuity + Insulation) & Final Inspection | 2026-06-11 | 07-Apr-26 A | -69 | Not required
21 | HFR1-05-2220 | Comission of Panel boards ( cables and testing) | 2026-06-18 | 14-Jun-26 A | -69 | Not required
22 | HFR1-05-2240 | Comission of Lighting Fixtures Installations /LED lighting | 2026-07-02 | 02-Jul-26 A | -69 | Not required
23 | HFR1-05-4230 | External Paint Touch-up & Inspection | 2026-07-07 | 11-Jul-26 A | -86 | Not required
24 | HFR1-05-4120 | External Paint Primer + Final Coat | 2026-07-01 | 09-Jul-26 A | -90 | Not required
25 | HFR1-05-4000 | Paint Primer + Putty + Final Coat INSIDE | 2026-06-25 | 08-Jul-26 A | -90 | Not required
26 | HFR1-05-3900 | External Paint Surface Preparation | 2026-06-20 | 09-Jul-26 A | -90 | Not required
27 | HFR1-05-4020 | Supply and install carpet rolls | 2026-06-25 | 19-Sep-26 A | -90 | Not required
28 | HFR1-05-4300 | Mosque Arch Carpet | 2026-07-13 | 19-Sep-26 A | -90 | Not required
29 | HFR1-05-3930 | Plumping fixtures | 2026-06-24 | 09-May-26 A | -90 | Not required
30 | HFR1-05-3240 | steel fence gate | 2026-06-02 | 17-Sep-26 A | -56 | Not required
31 | HFR1-05-3270 | install galvanized steel fence | 2026-06-13 | 14-Apr-26 A | -56 | Not required
32 | HFR1-05-4150 | Street Lighting Testing (Megger + Lighting Test) & Final Inspection | 2026-05-19 | 27-Apr-26 A | -56 | Not required
33 | HFR1-05-4390 | ROADTack Coat (RC2) | 2026-08-25 | 17-Sep-26 A | -65 | Not required
34 | HFR1-05-4510 | ROAD Interlock install concrete parking bumpers | 2026-09-06 | 25-Aug-26 A | -65 | Not required
35 | HFR1-05-4540 | ROAD Road Marking thermoplastic traffic lines | 2026-09-05 | 17-Sep-26 A | -65 | Not required
38 | HFR1-05-4530 | ROAD single I.P.E. post Road signs-Asphalt install traffic signs | 2026-09-05 | 10-Sep-26 A | -65 | Not required
39 | HFR1-05-4520 | ROAD Asphalt Reflective Road Markings | 2026-09-06 | 17-Sep-26 A | -65 | Not required
40 | HFR1-05-4420 | Test For Roads | 2026-09-13 | 23-Jun-26 A | -65 | Not required
43 | HFR1-05-4630 | Test For Electrical Works | 2026-09-03 | 22-Jun-26 A | -32 | Not required
44 | HFR1-05-4600 | Test For Water Utilities | 2026-04-01 | 26-Apr-26 A | -32 | Not required
45 | HFR1-05-4430 | Test For Pump Room | 2026-07-21 | 14-Jun-26 A | -25 | Not required
46 | HFR1-05-4680 | As-Built Documentation Final Submission | 2026-09-17 | 15-Sep-26 A | -25 | Not required
47 | HFR1-05-4690 | O&M Manuals and Warranties Final Submission | 2026-09-17 | 16-Sep-26 A | -25 | Not required
48 | HFR1-05-4700 | Final Handover MODON Inspection & Approval | 2026-09-17 | 19-Sep-26 A | -25 | Not required

## Sheet2
Activity ID | Activity Name | BL Project Start | Start | Schedule % Complete | Performance % Complete
HFR1-05-4590 | Site Works & External Networks Completed |  |  | 100% | 0%
HFR1-05-4620 | Main Buildings Architectural Completed |  |  | 100% | 0%
HFR1-05-3390 | Main Buildings Structure Completed |  |  | 100% | 0%
HFR1-05-4400 | Mosque Works Completed |  |  | 100% | 0%
HFR1-05-2730 | External Paint Touch-up & Inspection | 2026-05-30 | 06-Aug-26 A | 100% | 90%
HFR1-05-2630 | External Paint Primer + Final Coat | 2026-05-03 | 06-Aug-26 A | 100% | 90%
HFR1-05-2600 | Paint Primer + Putty + Final Coat INSIDE | 2026-04-25 | 24-Aug-26 A | 100% | 90%
HFR1-05-2820 | Specialites Fittings | 2026-07-13 | 01-Sep-26 A | 100% | 90%
HFR1-05-2900 | Testing plumping system & Final Inspection | 2026-09-06 | 04-May-26 A | 100% | 95%
HFR1-05-2910 | Fire Fighting Testing (Hydrostatic Test) & Final Inspection | 2026-09-16 | 02-May-26 A | 75% | 95%
HFR1-05-2070 | Power System and lighting and lightcurrent Testing (Continuity + Insulation) & Final Inspection | 2026-08-12 | 01-Apr-26 A | 100% | 95%
HFR1-05-2080 | Comission of Panel boards ( cables and testing) | 2026-08-19 | 14-Jun-26 A | 100% | 95%
HFR1-05-2100 | Comission of Lighting Fixtures Installations /LED lighting | 2026-08-30 | 29-Jun-26 A | 100% | 95%
HFR1-05-1530 | External Paint Touch-up & Inspection | 2026-06-08 | 06-Aug-26 A | 100% | 90%
HFR1-05-1480 | External Paint Primer + Final Coat | 2026-05-12 | 08-Aug-26 A | 100% | 90%
HFR1-05-1450 | Paint Primer + Putty + Final Coat INSIDE | 2026-05-04 | 23-Aug-26 A | 100% | 90%
HFR1-05-1570 | Specialites Fittings | 2026-07-06 | 01-Sep-26 A | 100% | 90%
HFR1-05-1790 | Testing plumping system & Final Inspection | 2026-08-18 | 04-May-26 A | 100% | 95%
HFR1-05-1800 | Fire Fighting Testing (Hydrostatic Test) & Final Inspection | 2026-09-06 | 04-May-26 A | 88.24% | 95%
HFR1-05-2210 | Power System and lighting and lightcurrent Testing (Continuity + Insulation) & Final Inspection | 2026-06-11 | 07-Apr-26 A | 100% | 95%
HFR1-05-2220 | Comission of Panel boards ( cables and testing) | 2026-06-18 | 14-Jun-26 A | 100% | 95%
HFR1-05-2240 | Comission of Lighting Fixtures Installations /LED lighting | 2026-07-02 | 02-Jul-26 A | 100% | 95%
HFR1-05-4230 | External Paint Touch-up & Inspection | 2026-07-07 | 11-Jul-26 A | 100% | 95%
HFR1-05-4120 | External Paint Primer + Final Coat | 2026-07-01 | 09-Jul-26 A | 100% | 95%
HFR1-05-4000 | Paint Primer + Putty + Final Coat INSIDE | 2026-06-25 | 08-Jul-26 A | 100% | 90%
HFR1-05-3900 | External Paint Surface Preparation | 2026-06-20 | 09-Jul-26 A | 100% | 90%
HFR1-05-4020 | Supply and install carpet rolls | 2026-06-25 | 19-Sep-26 A | 100% | 30%
HFR1-05-4300 | Mosque Arch Carpet | 2026-07-13 | 19-Sep-26 A | 100% | 30%
HFR1-05-3930 | Plumping fixtures | 2026-06-24 | 09-May-26 A | 100% | 80%
HFR1-05-3240 | steel fence gate | 2026-06-02 | 17-Sep-26 A | 100% | 40%
HFR1-05-3270 | install galvanized steel fence | 2026-06-13 | 14-Apr-26 A | 100% | 40%
HFR1-05-4150 | Street Lighting Testing (Megger + Lighting Test) & Final Inspection | 2026-05-19 | 27-Apr-26 A | 100% | 85%
HFR1-05-4390 | ROADTack Coat (RC2) | 2026-08-25 | 17-Sep-26 A | 100% | 95%
HFR1-05-4510 | ROAD Interlock install concrete parking bumpers | 2026-09-06 | 25-Aug-26 A | 100% | 80%
HFR1-05-4540 | ROAD Road Marking thermoplastic traffic lines | 2026-09-05 | 17-Sep-26 A | 100% | 50%
HFR1-05-4530 | ROAD single I.P.E. post Road signs-Asphalt install traffic signs | 2026-09-05 | 10-Sep-26 A | 100% | 50%
HFR1-05-4520 | ROAD Asphalt Reflective Road Markings | 2026-09-06 | 17-Sep-26 A | 100% | 60%
HFR1-05-4420 | Test For Roads | 2026-09-13 | 23-Jun-26 A | 81.82% | 90%
HFR1-05-4630 | Test For Electrical Works | 2026-09-03 | 22-Jun-26 A | 100% | 85%
HFR1-05-4600 | Test For Water Utilities | 2026-04-01 | 26-Apr-26 A | 100% | 85%
HFR1-05-4430 | Test For Pump Room | 2026-07-21 | 14-Jun-26 A | 100% | 85%
HFR1-05-4680 | As-Built Documentation Final Submission | 2026-09-17 | 15-Sep-26 A | 83.33% | 0%
HFR1-05-4690 | O&M Manuals and Warranties Final Submission | 2026-09-17 | 16-Sep-26 A | 100% | 0%
HFR1-05-4700 | Final Handover MODON Inspection & Approval | 2026-09-17 | 19-Sep-26 A | 71.43% | 0%