## DB (hidden)
MODON - Weekly Progress Report - Construction Projects
| Contract General Information | [7 empty] | Key Dates | [10 empty] | Cost Summary (SR) | [8 empty] | Performance Summary | [11 empty] | Shop Drawings |  |  |  | Material Approval |  |  | Procurement Summary | [6 empty] | Quality Reports | [15 empty] | Key Submittals Approval Status | [9 empty] | Invoices Summary | [13 empty] | Resources at Site | [6 empty] | Safety Statistics | [63 empty] | Primavera P6 Schedule Status | [7 empty] | Weekly Prgoress Photos
Data Date | Project Name | Project ID | Contractor | Consultant | Stage | Status | Modon PM | Project Scope | Contract Award | Contract Sign | Site Handover | Original Completion | Contract Award (Hijri) | Contract Sign (Hijri) | Site Handover (Hijri) | Original Completion (Hijri) | Revised Completion | Committed Completion | Forecast Completion | Original Contract Value | Revised Contract Value | Estimate At Completion Value | Potential Changes | O&M Value (if any) | Submitted Invoices (Gross Value) | Penalities | FIR Value (Todate) | Original Plan Value | Plan Value | Earn Value | Phys. Plan Value | Phys. Earn Value | Quality Score | Safety Score | Weekly PV (SAR) | Weekly EV (SAR) | Weekly PV % | Weekly PV % | Weekly Phys PV% | Weekly Phys PV% | Total SD Planned | SD Remaining | SD Pending | Total SD Submittals | Planned Materials Approv | Material Pending Approval | Materila Total Submittals | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) | NCR Issued | NCR Closed | NCR Pending | NCR Avg. Closing (Days) | SIR Issued | SIR Closed | SIR Pending | SIR Avg. Closing (Days) | MIR Issued | MIR Closed | MIR Pending | MIR Avg. Closing (Days) | FIR Issued | FIR Closed | FIR Pending | FIR Avg. Closing (Days) | 1 Quality Plan Approval | 2 Quality Plan Last Up | 3 Safety Plan Approval | 4 Safety Plan Last Up | 5 Construction Plan Approval | 6 Baseline Approval | 7 No of Approved Version of Schedule | 8 Last Approved Schedule | 9 BOQ Approval Date | 10 No of Approved Version of BOQ | Total Submitted Invoices | PM Approved Invoices | No of Paid Invoices | No of Pending Invoices | Advance Payment % | Retention % | Deduction / Penalties % | Submitted Invoices (SAR) | PM Approved Invoices (SAR) | Paid Invoices (SAR) | Last Submitted Period | Advance Payment (SAR) | Retention (SAR) | Deduction / Penalties (SAR) | Planned Head Count | Actual Head Count | Saudi Staff | Labor Planned | Labor Actual | Equipment Planned | Equipment Actual | This Week Total Hours Worked | This Week Safe Hours Worked | This Week LTI | This Week MTC (Healed w/o Disability) | This Week MTC (Healed w/ Disability) | This Week Near Miss | This Week First Aid Cases | This Week Fatality | This Week Fire Incident Cases | This Week Vehicle Incident | This Week Property Damages | This Week Induction Training | This Week No.of Internal Training | This Week No.of Internal Audit | This Week No. of Toolbox Talks | This Week Safety Awards/Incentives | This Month Total Hours Worked | This Month Safe Hours Worked | This Month LTI | This Month MTC (Healed w/o Disability) | This Month MTC (Healed w/ Disability) | This Month Near Miss | This Month First Aid Cases | This Month Fatality | This Month Fire Incident Cases | This Month Vehicle Incident | This Month Property Damages | This Month Induction Training | This Month No.of Internal Training | This Month No.of Internal Audit | This Month No. of Toolbox Talks | This Month Safety Awards/Incentives | YTD Total Hours Worked | YTD Safe Hours Worked | YTD LTI | YTD MTC (Healed w/o Disability) | YTD MTC (Healed w/ Disability) | YTD Near Miss | YTD First Aid Cases | YTD Fatality | YTD Fire Incident Cases | YTD Vehicle Incident | YTD Property Damages | YTD Induction Training | YTD No.of Internal Training | YTD No.of Internal Audit | YTD No. of Toolbox Talks | YTD Safety Awards/Incentives | Cum Total Hours Worked | Cum Safe Hours Worked | Cum LTI | Cum MTC (Healed w/o Disability) | Cum MTC (Healed w/ Disability) | Cum Near Miss | Cum First Aid Cases | Cum Fatality | Cum Fire Incident Cases | Cum Vehicle Incident | Cum Property Damages | Cum Induction Training | Cum No.of Internal Training | Cum No.of Internal Audit | Cum No. of Toolbox Talks | Cum Safety Awards/Incentives | Total Act. | Not Started | In Progress | Completed | Critical Path Act.Last Week | Critical Path Act.This Week | Failed start Last Week | Failed start This Week | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-21 | Factories Low-process Unit (HAFR Al Batin) | HFR1-05-03 | SOROH AL KHAIR CONTRACTING CO. | EGIS | Construction | Active | Eng. Mohammed Al Essa | The Project scope of work to construct a Factories of low process unit (Hafr Al Batin) industrial city that refer to specific tasks and activities involved in a project. This typically includes activities such as site preparation, Excavation, Foundation work, Structural construction work, Installation of utilities, Finishing works, Electrical Work, Mechanical Works and Landscaping. The scope outlines what will be done and by whom and within the planned timeframe. | 2025-10-15 | 2025-11-16 | 2025-11-27 | 2026-09-26 | 2025-10-15 | 2025-11-16 | 2025-11-27 | 2026-09-26 | 2026-09-26 | 2026-10-29 | 2026-11-07 | 16496855.87 | 16496855.87 | 16496855.87 | 0 | 0 | 10687825.21 | -141000 | 11743680.0968 | 99.55% | 99.55% | 98.17% | 99.72% | 98.02% | 0.79138 | 0.78846 | 311438.92 | 195657.68 | 1.888% | 1.186% | 0.951% | 1.942% | 266 | 0 | 0 | 266 | 86 | 2 | 86 | 93 | 93 | 93 | 0 | 93 | 0 | 2026-09-19 | 7 | 7 | 0 | 0 | 15 | 15 | 0 | 0 | 81 | 65 | 16 | 0 | 727 | 716 | 11 | 0 | 2026-03-25 | 2026-03-25 | 2026-09-22 | 0 | 0 | 2026-03-07 | 2 | 2026-03-07 | 2026-05-16 | 0 | 5 | 0 | 0 | 0 | 0.1 | 0 | 0.0085471 | 10687825.21 | 0 | 281548.46 | 2026-08-20 | 1649685.587 | 0 | -141000 | 12 | 10 | 0 | 34 | 58 | 0 | 13 | 3480 | 3480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11400 | 11400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 4 | 1 | 18 | 0 | 143630 | 143630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 5 | 5 | 23 | 0 | 143630 | 143630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 5 | 5 | 23 | 0 | 902 | 9 | 40 | 854 | 12 | 2 | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0

## Weekly Progress Report
MODON - Weekly Progress Report - Construction Projects | [30 empty] | Data Date | 2026-09-21
Contract General Information | [5 empty] | Key Dates | [5 empty] | Cost Summary (SR) | [7 empty] | Performance Summary | [5 empty] | Project Scope
Project Name | Factories Low-process Unit (HAFR Al Batin) |  |  |  |  | Contract Award | 2025-10-15 | Contract Award (Hijri) | 2025-10-15 | Revised Completion | 2026-09-26 | Original Contract Value |  | 16496855.87 |  | O&M Value (if any) |  | 0 | EAC | Plan Value | 99.55% | Phys. Plan Value | 99.72% | Quality Score | 79.14% | The Project scope of work to construct a Factories of low process unit (Hafr Al Batin) industrial city that refer to specific tasks and activities involved in a project. This typically includes activities such as site preparation, Excavation, Foundation work, Structural construction work, Installation of utilities, Finishing works, Electrical Work, Mechanical Works and Landscaping. The scope outlines what will be done and by whom and within the planned timeframe.
Project ID | HFR1-05-03 |  | Stage | Construction |  | Contract Sign | 2025-11-16 | Contract Sign (Hijri) | 2025-11-16 | Committed Completion | 2026-10-29 | Revised Contract Value |  | 16496855.87 | EAC | Submitted Invoices (Gross Value) |  | 10687825.21 |  | Earn Value | 98.17% | Phys. Earn Value | 98.02% |  | ¢¢¢¢¢ ¢¢£££
Contractor | SOROH AL KHAIR CONTRACTING CO. |  | Status | Active |  | Site Handover | 2025-11-27 | Site Handover (Hijri) | 2025-11-27 | Forecast Completion | 2026-11-07 | Estimate At Completion Value |  | 16496855.87 | #REF! | Penalities |  | -141000 |  | Variance | -1.372% | Variance | -1.701% | Safety Score | 78.85%
Consultant | EGIS |  | Modon PM | Eng. Mohammed Al Essa |  | Original Completion | 2026-09-26 | Original Completion (Hijri) | 2026-09-26 | Variance | -42 | Potential Changes |  | 0 |  | FIR Value (Todate) |  | 11743680.0968 |  | FIR % | 71.19% | Invoiced % | 64.79% |  | ¢¢¢¢¢ ¢¢£££
Progress Overview
Earned Value Progress (SAR) | [13 empty] | Physical Progress (Effort) | [11 empty] | Earned Value Progress (%)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) | [7 empty] | Budgeted | % Wt. | Weekly Physical Progress |  |  |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Revised Planned | Earned | Original Plan % | Revised Planned % | Earned % | Variance | SPI | (Manhours) |  | Planned | Earned | Plan % | Earned % | Planned | Earned | Plan % | Earned % | Variance | SPI
Mobilization |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 4400 | 3.002% | 0 | 0 | 0% | 0% | 4400 | 4400 | 100% | 100% | 0% | 1
Engineering Phase |  | 494865 | 3% | 0 | 0 | 494865 | 494865 | 494865 | 100% | 100% | 100% | 0% | 1 | 7321 | 4.995% | 0 | 0 | 0% | 0% | 7321 | 7321 | 100% | 100% | 0% | 1
Procurment |  | 3299371 | 20% | 0 | 10324.7 | 3299371 | 3299371 | 3299371 | 100% | 100% | 100% | 0% | 1 | 17626 | 12.02% | 0 | 74 | 0% | 0.4198% | 17626 | 17626 | 100% | 100% | 0% | 1
Construction phase |  | 11052935.87 | 67% | 52113.6 | 144090.88 | 11052935.87 | 11052935.87 | 10978371.61 | 100% | 100% | 99.33% | -0.6746% | 0.99325 | 109913 | 74.98% | 244 | 2590 | 0.222% | 2.356% | 109832 | 108012 | 99.93% | 98.27% | -1.656% | 0.98343
site general works |  | 1298122.04 | 7.869% | 0 | 0 | 1298122.04 | 1298122.04 | 1298122.04 | 100% | 100% | 100% | 0% | 1 | 5423 | 3.7% | 0 | 0 | 0% | 0% | 5423 | 5423 | 100% | 100% | 0% | 1
Hunger -1 |  | 3846587.17 | 23.32% | 52113.6 | 33514.57 | 3846587.17 | 3846587.17 | 3832084.23 | 100% | 100% | 99.62% | -0.377% | 0.99623 | 23347 | 15.93% | 157 | 320 | 0.6725% | 1.371% | 23295 | 23137 | 99.78% | 99.1% | -0.6767% | 0.99322
Hunger-2 |  | 3851109.03 | 23.34% | 0 | 33277.93 | 3851109.03 | 3851109.03 | 3836609.69 | 100% | 100% | 99.62% | -0.3765% | 0.99624 | 24765 | 16.9% | 88 | 350 | 0.3553% | 1.413% | 24736 | 24529 | 99.88% | 99.05% | -0.8359% | 0.99163
Sephtic Tank |  | 149552.06 | 0.9065% | 0 | 0 | 149552.06 | 149552.06 | 149552.06 | 100% | 100% | 100% | 0% | 1 | 7817 | 5.333% | 0 | 0 | 0% | 0% | 7817 | 7817 | 100% | 100% | 0% | 1
Mosque -elec room-Toilets Works |  | 396377.89 | 2.403% | 0 | 20068.17 | 396377.89 | 396377.89 | 386130.49 | 100% | 100% | 97.41% | -2.585% | 0.97415 | 15308 | 10.44% | 0 | 671 | 0% | 4.383% | 15308 | 14842 | 100% | 96.96% | -3.044% | 0.96956
GRB Tank |  | 163749.6 | 0.9926% | 0 | 0 | 163749.6 | 163749.6 | 163749.6 | 100% | 100% | 100% | 0% | 1 | 9922 | 6.769% | 0 | 0 | 0% | 0% | 9922 | 9922 | 100% | 100% | 0% | 1
Pump room |  | 389712.84 | 2.362% | 0 | 2664.93 | 389712.84 | 389712.84 | 387774.89 | 100% | 100% | 99.5% | -0.4973% | 0.99503 | 7698 | 5.252% | 0 | 192 | 0% | 2.494% | 7698 | 7313 | 100% | 95% | -5.001% | 0.94999
External WORKS-MEP |  | 581705.66 | 3.526% | 0 | 3195.27 | 581705.66 | 581705.66 | 570319.85 | 100% | 100% | 98.04% | -1.957% | 0.98043 | 6008 | 4.099% | 0 | 7 | 0% | 0.1165% | 6008 | 5985 | 100% | 99.62% | -0.3828% | 0.99617
External Works landscape |  | 376019.58 | 2.279% | 0 | 51370.56 | 376019.58 | 376019.58 | 354028.77 | 100% | 100% | 94.15% | -5.848% | 0.94152 | 9626 | 6.567% | 0 | 1050 | 0% | 10.91% | 9626 | 9045 | 100% | 93.96% | -6.036% | 0.93964
Testing and comissiong |  | 1649684 | 10% | 259325.32 | 41242.1 | 1574698.36 | 1574698.36 | 1422852.45 | 95.45% | 95.45% | 86.25% | -9.205% | 0.90357 | 7320 | 4.994% | 1150 | 183 | 15.71% | 2.5% | 6987 | 6314 | 95.45% | 86.26% | -9.194% | 0.90368
Close Out |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
| Total | 16496855.87 | 100% | 311438.92 | 195657.68 | 16421870.23 | 16421870.23 | 16195460.06 | 99.55% | 99.55% | 98.17% | -1.372% | 0.98621 | 146580 | 100% | 1394 | 2847 | 0.951% | 1.942% | 146166 | 143673 | 99.72% | 98.02% | -1.701% | 0.98294
Construction Milestones
[26 empty] | Item No. | Milestones |  | Original (Baseline) | Latest Plan | Forecast | Status | Days Change
[26 empty] | 1 | Award Date |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | A | 0
[26 empty] | 2 | Contract Sign Date |  | 2025-11-16 | 2025-11-16 | 2025-11-16 | A | 0
[26 empty] | 3 | Site Handover Date |  | 2025-11-27 | 2025-11-27 | 2025-11-27 | A | 0
[26 empty] | 4 | Complete Mobilization |  | 2025-12-28 | 2025-12-28 | 2025-12-28 | A | 0
[26 empty] | 7 | Complete Earthworks |  | 2026-03-22 | 2026-04-04 | 2026-04-04 | F | 0
[26 empty] | 8 | Complete Civil & Arch Works |  | 2025-07-16 | 2026-11-14 | 2026-10-11 | F | 34
[26 empty] | 9 | Complete Electrical Works |  | 2025-09-02 | 2026-11-07 | 2026-10-17 | F | 21
[26 empty] | 10 | Complete Mechanical Works |  | 2025-09-26 | 2026-12-02 | 2026-10-29 | F | 34
[26 empty] | 11 | Complete Finishing Works |  | 2026-09-26 | 2026-11-29 | 2026-10-29 | F | 31
[26 empty] | 12 | Project Handover |  | 2026-09-26 | 2026-12-28 | 2026-11-07 | F | 51
Performance overview
Submittals Status | [10 empty] | Quality | [10 empty] | Safety
Shop Drawings | [10 empty] | Quality Reports | [10 empty] | Safety Statistics | [7 empty] | Proactive Vs Reactive Actions Taken
Item Per WBS |  | Total | Total Submitted Drawings |  |  |  |  | Remaining | Pending | Total Submittals | Quality Reports |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending |  |  |  |  | Category | Item |  | This Week |  | This Month | Year to Date | Cumulative
|  |  | A | B | C | D | Processed | [9 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Civil /Roads |  | 19 | 2 | 17 |  |  | 19 | 0 |  | 19 | [11 empty] | General | Total Hours Worked |  | 3480 |  | 11400 | 143630 | 143630 |  |  | Proactive | 44
Structural |  | 129 | 8 | 121 |  |  | 129 |  |  | 129 | Non Conformance (NCR) |  | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Safe Hours Worked |  | 3480 |  | 11400 | 143630 | 143630 |  |  | Reactive | 0
Architectural |  | 37 | 3 | 34 |  |  | 37 | 0 | 0 | 37 | Site Instruction (SIR) |  | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Reactive | LTI |  | 0 |  | 0 | 0 | 0
Mechanical |  | 41 |  | 41 |  |  | 41 | 0 | 0 | 41 | Material Inspection (MIR) |  | 81 | 65 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  | MTC (Healed w/o Disability) |  | 0 |  | 0 | 0 | 0
Electrical |  | 40 | 0 | 40 |  | 0 | 40 | 0 | 0 | 40 | Field Inspection (FIR) |  | 727 | 716 | 11 | 0 | 0 | 0 | 0 | 0 | 0 |  | MTC (Healed w/ Disability) |  | 0 |  | 0 | 0 | 0
TOTAL |  | 266 | 13 | 253 | 0 | 0 | 266 | 0 | 0 | 266 | Key Submittals Approval Status | [11 empty] | Near Miss |  | 0 |  | 0 | 0 | 0
Material Approval | [10 empty] | 1 Quality Plan Approval |  |  | 2026-03-25 |  | 6 Baseline Approval |  |  |  | 2026-03-07 |  |  | First Aid Cases |  | 0 |  | 0 | 0 | 0 | Total Hours Worked Vs Safe Hours Worked
Item Per WBS |  | Total | Total Submitted Material |  |  |  |  | Remaining to approve | Pending | Total Submittals | 2 Quality Plan Last Up |  |  | 2026-03-25 |  | 7 No of Approved Version of Schedule |  |  |  | 2 |  |  | Fatality |  | 0 |  | 0 | 0 | 0
|  |  | A | B | C | D | Processed | with Designer |  |  | 3 Safety Plan Approval |  |  | 2026-09-22 |  | 8 Last Approved Schedule |  |  |  | 2026-03-07 |  |  | Fire Incident Cases |  | 0 |  | 0 | 0 | 0
Civil / Roads |  | 9 |  | 9 |  | 0 | 9 |  | 0 | 9 | 4 Safety Plan Last Up |  |  | 0 |  | 9 BOQ Approval Date |  |  |  | 2026-05-16 |  |  | Vehicle Incident |  | 0 |  | 0 | 0 | 0
Structural |  | 9 | 0 | 9 | 0 | 0 | 9 |  |  | 9 | 5 Construction Plan Approval |  |  | 0 |  | 10 No of Approved Version of BOQ |  |  |  | 0 |  |  | Property Damages |  | 0 |  | 0 | 0 | 0
Architectural |  | 30 | 1 | 26 | 0 | 1 | 26 | 0 | 2 | 30 | Invoices Summary | [10 empty] | Proactive | Induction Training |  | 0 |  | 7 | 11 | 11
Mechanical |  | 20 | 0 | 20 |  | 0 | 20 | 0 |  | 20 | Total Submitted Invoices |  | 5 | Submitted Invoices (SAR) |  |  | 10687825.21 |  | Contract Value (SR) | 16496855.87 |  |  | No.of Internal Training |  | 0 |  | 4 | 5 | 5
Electrical |  | 18 | 0 | 18 | 0 | 0 | 18 |  |  | 18 | PM Approved Invoices |  | 0 | PM Approved Invoices (SAR) |  |  | 0 |  | Planned Value (SR) | 16421870.23 |  |  | No.of Internal Audit |  | 0 |  | 1 | 5 | 5
TOTAL |  | 86 | 1 | 82 | 0 | 1 | 82 | 0 | 2 | 86 | No of Paid Invoices |  | 0 | Paid Invoices (SAR) |  |  | 281548.46 |  | Earned Value (SR) | 16195460.06 |  |  | No. of Toolbox Talks |  | 0 |  | 18 | 23 | 23
Procurement Summary | [10 empty] | No of Pending Invoices |  | 0 | Last Submitted Period |  |  | 2026-08-20 |  | Submitted (SAR) | 10687825.21 |  |  | Safety Awards/Incentives |  | 0 |  | 0 | 0 | 0
Item Per WBS |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) |  |  | Advance Payment % |  | 10% | Advance Payment (SAR) |  |  | 1649685.587 |  | PM Approved (SAR) | 0 |  | Latest Contract Change Order Log
|  |  | A | B | C | D | Processed |  |  |  | Retention % |  | 0% | Retention (SAR) |  |  | 0 |  | Total Paid (SAR) | 281548.46
Civil |  | 9 | 9 | 9 |  | 9 | 0 | 2026-09-19 |  |  | Deduction / Penalties % |  | 0.8547% | Deduction / Penalties (SAR) |  |  | -141000 |  |  |  |  | CCO No. | Date Added | Description of Change |  |  |  |  | Status | Cost | Sch Impact (Months) | Date Approved | Duration
Structural |  | 9 | 9 | 9 |  | 9 | 0 | 2026-05-05 |  |  | Resources at Site
Architectural |  | 22 | 22 | 22 |  | 22 | 0 | 2026-09-19 |  |  | Head Count - Non Manual |  |  |  | Head Count - Manual |  |  |  | Total Head Count |  |  | 1
Mechanical |  | 28 | 28 | 28 | 0 | 28 | 0 | 2026-08-29 |  |  | Planned | Actual | Next Month Forecast | Saudi Staff | Planned | Actual | Next Month Forecast | Saudi Staff | Total Plan | Total Actual | Variance
Electrical |  | 25 | 25 | 25 |  | 25 |  | 2026-08-29 |  |  | 12 | 10 | #N/A | 0 | 34 | 58 | #N/A | 0 | 46 | 68 | 22
TOTAL |  | 93 | 93 | 93 | 0 | 93 | 0 | 2026-09-19 |  |  | Manpower Breakdown by Trade | [6 empty] | Major Equipment
Primavera P6 Schedule Status | [10 empty] | Key Trade | Planned | Actual |  |  |  |  | Type | Planned | Actual | Idle
Project Activities Overview | [10 empty] | General Labor | 10 | 12 |  |  |  |  | Excavator | 0 | 1 | 0
Schedule Statistics |  |  |  |  | Active Schedule Activities | [5 empty] | Carpenter | 4 | 4 |  |  |  |  | Loader | 0 | 2 | 0 | Major Quantity Trackers
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag | 0 | Plumber | 3 | 4 |  |  |  |  | Dozer | 0 | 0 | 0 | BOQ N0. | Item Description |  |  |  |  | Total Qty | Measu Unit | Plan to Date | Act to Date | Remaining | Variance
902 | 9 | 40 | 854 | 94.68% | 40 | 29 | 14 | 15 | 28 |  | Operator | 0 | 13 |  |  |  |  | Dumper | 0 | 2 | 0 | 2.1.1 | Excavation |  |  |  |  | 1503 | M3 | 1503 | 629.42 | 873.58 | 873.58
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities |  |  |  | Steel Fixer | 4 | 4 |  |  |  |  | Crane | 0 | 1 | 0 | 2.1.3 | Backfilling |  |  |  |  | 20258.76 | M3 | 20258.76 | 14724.77 | 5533.99 | 5533.99
|  |  | Greater Than 14 Days |  | Less Than 14 Days | [5 empty] | Mason | 2 | 2 |  |  |  |  | Grader | 0 | 1 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag | 0 | Others | 11 | 19 |  |  |  |  | Other | 0 | 6 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
12 | 2 | 10 | 41 | 41 | -80 | -36 | 11 | 10 | 1 |  | Total | 34 | 58 |  |  |  |  | Total | 0 | 13 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Weekly Prgoress Photos | [15 empty] | Top Issues and Risks
Installation of Exaust Fan for Building 2 |  |  |  |  | Installation of Epoxy Paint - Building 2 | [5 empty] | Commsission of Panel Board for Building 2 |  |  |  |  | Top 5 Issues
[16 empty] | Issue No | Date Identified | Issue Description |  |  |  | Responsible | Action Taken |  |  | Mitigation |  |  |  |  | Current Status | Expected/Actual Closure | Duration Elapsed
[16 empty] | 1 | 14/06/2026 | Workers at height during lifting operations without proper coordination. |  |  |  | Contractor | Work sequence revised, lifting and work-at-height activities separated, supervision increased. | [7 empty] | Closed | 14/06/2026 | 0 days
[16 empty] | 2 | 14/06/2026 | Workers were exposed to suspended load during lifting operations due to inadequate barricading and unsafe work positioning. |  |  |  | Contractor | Lifting activity stopped, exclusion zone established, barricades installed, workers relocated from the danger area, toolbox talk conducted, and tag lines provided. | [7 empty] | Closed | 14/06/2026 | 0 days
[16 empty] | 3 | 14/06/2026 | Lack of proper isolation of lifting area. |  |  |  | Contractor | Barricades and warning signs installed, access restricted to authorized personnel only. | [7 empty] | Closed | 14/06/2026 | 0 days
[16 empty] | 4 | 29-06-2026 | Poor House keeping obsered in work zone area |  |  |  | Contractor | Site house keeping team has been instruted to clean area immediately and maintain daily monitoring | [7 empty] | Open | 2026-09-22
5
Formulas:
Earned = MAX(I82:[Earned, row above])
2,137,565

## General Information
Weekly Progress Report - Construction Projects |  |  | Data Date | 2026-09-21
Contract General Information
Project Name | Factories Low-process Unit (HAFR Al Batin)
Project ID | HFR1-05-03
Contractor | SOROH AL KHAIR CONTRACTING CO.
Consultant | EGIS
Stage | Construction
Status | Active
Modon PM | Eng. Mohammed Al Essa
Key Dates
Contract Award Date | 2025-10-15
Contract Sign Date | 2025-11-16
Site Handover Date | 2025-11-27
Original Completion | 2026-09-26
Contract Award Date (Hijri) | 2025-10-15
Contract Sign Date (Hijri) | 2025-11-16
Site Handover Date (Hijri) | 2025-11-27
Original Completion (Hijri) | 2026-09-26
Revised Completion Date | 2026-09-26
Committed Completion Date | 2026-10-29
Forecast Completion | 2026-11-07
Variance | -42
Key Project Submittals | Submission Date | Days taken to approve orginal plan from site handover date
Quality Plan submission | 2026-01-10 | 118
Quality Plan approval | 2026-03-25
Quality Plan Last Update | 2026-03-25
Safety Plan submission | 2025-12-30 | 299
Safety Plan approval | 2026-09-22
Safety Plan Last Update
Risk Management Plan submission | 2025-12-30 | 299
Risk Management Plan approval | 2026-09-22
Risk Management Plan Last Update
Baseline Schedule submission | 2025-12-29 | 32
Baseline Schedule approval | 2026-03-07
No of Schedule Versions | 2
Last Recovery Schedule Approval Date | 2026-03-07
BOQ submission | 2026-01-01 | 35
BOQ approval | 2026-05-16
No of Approved Version of BOQ | 0
Construction Plan submission | 2026-09-22 | 299
Construction Plan Approval
Note on D25: AlNuaim, Abdulaziz: As per contract requirments submission of Plans should be 30 days after site handover

## Progress
Project Scope Statement | The Project scope of work to construct a Factories of low process unit (Hafr Al Batin) industrial city that refer to specific tasks and activities involved in a project. This typically includes activities such as site preparation, Excavation, Foundation work, Structural construction work, Installation of utilities, Finishing works, Electrical Work, Mechanical Works and Landscaping. The scope outlines what will be done and by whom and within the planned timeframe. | [13 empty] | Data Date | 2026-09-21
Earned Value Progress (SAR) | [8 empty] | Physical Progress (Effort)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  |  | To Date (SAR) |  | Budgeted | % Wt. | Weekly Physical Progress |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Planned | Earned | (Manhours) |  | Planned | Earned | Planned | Earned
Project Milestones |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0
Mobilization |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 4400 | 3.002% | 0 |  | 4400 | 4400
Engineering Phase | premilinary submittals | 494865 | 3% |  |  | 494865 | 494865 | 494865 | 7321 | 4.995% | 0 |  | 7321 | 7321
Procurment | premilinary Approve | 3299371 | 20% |  | 10324.7 | 3299371 | 3299371 | 3299371 | 17626 | 12.02% |  | 74 | 17626 | 17626
Construction phase |  | 11052935.87 | 67% | 52113.6 | 144090.88 | 11052935.87 | 11052935.87 | 10978371.61 | 109913 | 74.98% | 244 | 2590 | 109832 | 108012
site general works |  | 1298122.04 | 7.869% |  |  |  | 1298122.04 | 1298122.04 | 5423 | 3.7% |  |  | 5423 | 5423
Hunger -1 |  | 3846587.17 | 23.32% | 52113.6 | 33514.57 |  | 3846587.17 | 3832084.23 | 23347 | 15.93% | 157 | 320 | 23295 | 23137
Hunger-2 |  | 3851109.03 | 23.34% |  | 33277.93 |  | 3851109.03 | 3836609.69 | 24765 | 16.9% | 88 | 350 | 24736 | 24529
Sephtic Tank |  | 149552.06 | 0.9065% |  |  |  | 149552.06 | 149552.06 | 7817 | 5.333% |  |  | 7817 | 7817
Mosque -elec room-Toilets Works |  | 396377.89 | 2.403% |  | 20068.17 |  | 396377.89 | 386130.49 | 15308 | 10.44% |  | 671 | 15308 | 14842
GRB Tank |  | 163749.6 | 0.9926% |  |  |  | 163749.6 | 163749.6 | 9922 | 6.769% |  |  | 9922 | 9922
Pump room |  | 389712.84 | 2.362% |  | 2664.93 |  | 389712.84 | 387774.89 | 7698 | 5.252% |  | 192 | 7698 | 7313
External WORKS-MEP |  | 581705.66 | 3.526% |  | 3195.27 |  | 581705.66 | 570319.85 | 6008 | 4.099% |  | 7 | 6008 | 5985
External Works landscape |  | 376019.58 | 2.279% |  | 51370.56 | 0 | 376019.58 | 354028.77 | 9626 | 6.567% |  | 1050 | 9626 | 9045
Testing and comissiong |  | 1649684 | 10% | 259325.32 | 41242.1 | 1574698.36 | 1574698.36 | 1422852.45 | 7320 | 4.994% | 1150 | 183 | 6987 | 6314
Close Out |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0
| Total | 16496855.87 | 100% | 311438.92 | 195657.68 | 16421870.23 | 16421870.23 | 16195460.06 | 146580 | 100% | 1394 | 2847 | 146166 | 143673
|  |  |  | 1.888% | 1.186% | 99.55% | 99.55% | 98.17% |  |  | 0.951% | 1.942% | 99.72% | 98.02%
`

## Weekly Photos
Date | 2026-09-21
Commsission of Panel Board for Building 2 |  | Installation of Water draiange from roof top
Installation of Exaust Fan for Building 2 |  | Installation of Epoxy Paint - Building 2
Installation of Traffic Signs |  | Installation of Road Markings Work
Installation of Cladding for Building 2 |  | Asphlat work 2nd layer for Road Work

## FIR Summary
Project Name |  |  | Factories Low-process Unit (HAFR Al Batin)
Project ID |  |  | HFR1-05-03 | Project Budget |  | 16496855.87
Total FIR Approved Value (Cumulative) |  |  | 11743680.0968 | Remaining FIRs Value (Cumulative) |  | 4753175.7732
Date Period |  |  | 2026-09-14 | To |  | 2026-09-21
BOQ Item # | BOQ Description | FIR / DATE | FIR # | FIR Description | Status | Unit Rate | Current Period Quantity | Progress (%) | Total (SAR) | Remarks
2.2.4 | Supply and execute subgrade material up to the full width of the road as per specifications and drawings | 2026-08-19 | HFR1-05-003-SAK-TS9-1FIR-SUV-0144-00 | Supply and execute subgrade material Layer-2 (15cm Sub Base), as per highlighted drawing. | Approved | 66 | 1047.6555 | 100% | 69145.263
5.1 | Supply and install steel ladder with safety cage including all necessary fixings, fixtures, painting all as per drawings and specifications. (Height = 5.5m) |  | HFR1-05-003-SAK-TS9-1-FIR- ARC-0074-00 | Supply and install steel ladder with safety cage including all necessary fixings, fixtures. | Approved | 5940 | 2 | 100% | 11880
8.1.1 | Supply and install (D6) 3000*3500mm galvanized steel heavy duty industrial isolated type roll up shutter door finished with polyurethane coating, with automatic and manual control system, as per manufacturer specification and approved by the Client, complete with all accessories and fittings, and as per door schedule and specifications |  | HFR1-05-003-SAK-TS9-1-FIR-ARC-0122-00 |  | Approved | 15510 | 24 | 35% | 130284
8.1.2 | Supply and install fire rated 45 min. (D5) 1000*2200mm single leaf steel door with door construction type C with hardware set type HW2 paint finish as per manufacturer detail and approved by the Client with complete accessories as per door schedule, drawings and specification |  | HFR1-05-003-SAK-TS9-1-FIR-ARC-0123-00 |  | Approved | 2750 | 24 | 35% | 23100
8.1.3 | Supply and install (D2) 1000*2200 mm single leaf galvanized steel door with door construction type B with hardware set type HW1 paint finish as per manufacturer detail and approved by the Client with complete accessories as per door/window schedule and as per drawings and specification. | 2026-08-20 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0120-00 | Supply and install (D2) 1000*2200 mm single leaf galvanized steel door with door construction type B with hardware set type HW1 paint finish at Building-1 (axis A-N/1x3), as per highlighted drawing. | Approved | 3355 | 2 | 100% | 6710
8.1.4 | Supply and install (D3) 800*2200 mm single leaf semi solid wood door with door construction type B with hardware set type HW1 paint finish as per manufacturer detail and approved by the Client with complete accessories as per door/window schedule and as per drawings and specification. | 2026-08-20 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0121-00 | Supply and install (D3) 800*2200 mm single leaf semi solid wood door with door construction type B with hardware set type HW1 paint finish at Building-1 (axis A-N/1x3), as per highlighted drawing. | Approved | 2896 | 2 | 100% | 5792
8.1.4 | Supply and install (D3) 800*2200 mm single leaf semi solid wood door with door construction type B with hardware set type HW1 paint finish as per manufacturer detail and approved by the Client with complete accessories as per door/window schedule and as per drawings and specification. | 2026-08-20 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0119-00 | Supply and install (D3) 800*2200 mm single leaf semi solid wood door with door construction type B with hardware set type HW1 paint finish at Building-2 (axis A-N/1x3), as per highlighted drawing. | Approved | 2896 | 2 | 100% | 5792
9.2.8 | Supply and install phenolic partitions with doors for toilets including accessories, fixations, fittings, and all the required works as shown in the drawings and specification with approved quality by the Client |  | HFR1-05-003-SAK-TS9-1-FIR- ARC-0116-00 |  | Approved | 660 | 65 | 100% | 42900
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | Total Excuted Amount | [6 empty] | 295603.263

## Quality
QC OBSERVATIONS CHECKLIST
2026-02-16
Project No. |  |  | HFR1-05-03 |  |  | OBS No. |  |  |  | 14 |  |  | Inspection Day: |  | 2026-09-21
Project |  |  | Factories Low-process Unit (HAFR Al Batin) | [6 empty] | Contractor: Consultant: |  |  | SOROH AL KHAIR CONTRACTING CO. EGIS
4 |  | Excellent |  | Quality Management System is being practiced and applies to MODON System | [11 empty] | 90 - 100 |  | QC Overall Score | 79.14% |  |  |  |  | 0% | 100 | 0.22883
3 |  | Good |  | Evidence of compliance with plans and procedures. | [11 empty] | 80 - 89 | [7 empty] | 0 | 89 | 0.20366
2 |  | Average |  | Indication level of compliance with standards but there is room for improvement | [11 empty] | 70 - 79 | [8 empty] | 79 | 0.18078
1 |  | Improve |  | Quality and Control is NOT being managed effectively. Needs Improvement | [11 empty] | ≤ 69 | [8 empty] | 69 | 0.15789
0 |  | N/A |  | Item was not applicable or this item was not reviewed during the inspection. | [11 empty] | Zero | [8 empty] | 100 | 0.22883
No. | Topic |  |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) | No. | Topic |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) |  |  |  |  | 437
[6 empty] | 100% | 89% | 79% | 69% | 100% | [5 empty] | 100% | 89% | 79% | 69% | 100% | 79.14%
1 | Control of Access to Site/Office | [5 empty] | 0 | 1 | 0 |  | 30 | QC of Excavation |  |  |  | 0 | 0 | 0 | 1 | 0 | 0.79 | 0.69 | [6 empty] | Item Count | Score | Distributtion
2 | Document Control Administration |  |  |  |  | 0 | 0 | 0 | 1 |  | 31 | QC of Roads/Round about |  |  |  | 0 | 0 |  | 1 | 0 | 0.69 | 0.69 | [8 empty] | Overall | Relevant
3 | Project Documents and Progress |  |  |  |  | 0 | 0 | 0 | 1 |  | 32 | QC of Interlock & Curbstone |  |  |  | 0 |  |  | 1 | 0 | 0.69 | 0.69 | 4 | 58 | counts |  | 4 | Excellent | 0 | 0 | 0% | 0%
4 | Contractor's Quality Plan/CM (Updated and Reviewed) |  |  |  |  | 0 | 0 | 1 |  |  | 33 | Layers/Backfilling Sampling |  |  |  | 0 | 0 | 0 | 1 | 0 | 0.79 | 0.69 | 3 | 58 | counts |  | 3 | Good | 0 | 0 | 0% | 0%
5 | MS Log and Paperwork |  |  |  |  | 0 | 0 | 0 | 1 |  | 34 | Pump Stations Units |  |  |  | 0 | 0 | 0 | 1 | 0 | 0.69 | 0.69 | 2 | 58 | counts |  | 2 | Average | 3 | 6 | 5.172% | 7.5% |  | NB: Insert 1, or 0 in the required cell only.
6 | RFI, FIR, & MIR Procedure |  |  |  |  | 0 | 0 | 0 | 1 |  | 35 | Quality of Form Work |  |  |  | 0 | 0 | 0 | 1 | 0 | 0.69 | 0.69 | 1 | 58 | counts |  | 1 | Improve | 37 | 37 | 63.79% | 92.5%
7 | RFI, FIR, & MIR Inventory system |  |  |  |  | 0 | 0 | 0 | 1 |  | 36 | Design Change List | [6 empty] | 0 | 1 | 0.69 | 1 | 0 | 58 | counts |  | 0 | N/A | 18 | 0 | 31.03% | -
8 | NCRs Control & Procedure |  |  |  |  | 0 | 0 | 0 | 1 |  | 37 | Quality of Concrete Placing |  |  |  | 0 |  | 0 | 1 | 0 | 0.69 | 0.69 | [5 empty] | Total | 58 | 43 | 100% | 100%
9 | NCR Log |  |  |  |  | 0 |  | 0 | 1 |  | 38 | Concrete Surface Finishing |  |  |  | 0 | 0 | 0 | 1 | 0 | 0.69 | 0.69
10 | MODON Standard* |  |  |  |  | 0 | 0 |  | 1 |  | 39 | Pedestals/Columns/Beams Alignment |  |  |  | 0 | 0 | 0 | 1 | 0 | 0.69 | 0.69 | [6 empty] | Maz Score Available: | 160 | <- Excludes N/A items
11 | Project Risk Plan/Management* |  |  |  |  | 0 | 0 |  | 1 |  | 40 | Siporex Lifting & Unloading | [5 empty] | 0 |  | 1 | 0.69 | 1
12 | Monthly Quality Reports* |  |  |  |  | 0 | 0 | 0 | 1 |  | 41 | Siporex Quality Pre-installation | [5 empty] | 0 |  | 1 | 0.69 | 1
13 | ITP |  |  |  |  | 0 | 0 | 1 |  |  | 42 | Siporex Finishing Quality |  |  |  | 0 |  |  |  | 1 | 0.79 | 1 | [5 empty] | Total Score |  | Percentage (%)
14 | MODON Weekly Report |  |  |  |  | 0 | 0 | 0 | 1 |  | 43 | Roads / Parking Markings |  |  |  | 0 | 0 |  |  | 1 | 0.69 | 1 |  | 58 |  |  |  | 43 |  | 26.875 |  | %
15 | Design Change Official Paperwork* |  |  |  |  | 0 |  |  |  | 1 | 44 | QC of Finishing Outdoors |  |  |  | 0 | 0 |  |  | 1 | 1 | 1 | [5 empty] | Max Score Available | [6 empty] | 31
16 | Design Change was Applied* |  |  |  |  | 0 |  |  |  | 1 | 45 | Quality of Finishing Indoors |  |  |  | 0 |  |  | 1 | 0 | 1 | 0.69 | [5 empty] | 160 | [6 empty] | 32
17 | Material List |  |  |  |  | 0 |  | 0 | 1 |  | 46 | Stairs Quality |  |  |  | 0 |  |  |  | 1 | 0.69 | 1 | [12 empty] | 33
18 | Pending Material Status |  |  |  |  | 0 |  | 0 | 1 | 0 | 47 | Tanks Method Statement Work |  |  |  | 0 |  |  |  | 1 | 0.69 | 1 | [12 empty] | 34
19 | Lifting Plan* | [8 empty] | 1 | 48 | Electric Rooms |  |  |  | 0 |  |  |  | 1 | 1 | 1 | [12 empty] | 35
20 | DWG Log | [5 empty] | 0 | 0 | 1 | 0 | 49 | QC of MCC/ATS Plant Units |  |  |  | 0 |  |  |  | 1 | 0.69 | 1 | [12 empty] | 36
21 | Invoice Status |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 50 | Qualified Subcontractor |  |  |  | 0 | 0 |  |  | 1 | 0.69 | 1 | [12 empty] | 37
22 | Site Handover Letter |  |  |  |  | 0 | 0 |  |  | 1 | 51 | Scaffold/Ladders/Slope/Bridge Compliance |  |  |  | 0 |  |  | 1 | 0 | 1 | 0.69 | [12 empty] | 38
23 | Material Testing Results & Certification |  |  |  |  | 0 |  | 0 | 1 |  | 52 | Protection Applied to Completed Work | [6 empty] | 0 | 1 | 0.69 | 1
24 | As Build Drawings Status* |  |  |  |  | 0 | 0 |  |  | 1 | 53 | Storage Management in/out Control |  |  |  |  | 0 |  | 1 | 0 | 1 | 0.69
25 | Calibrated Lab Tools & Equipment |  |  |  |  | 0 | 0 |  | 0 | 1 | 54 | Material Control |  |  |  |  | 0 | 0 | 1 | 0 | 1 | 0.69
26 | Storage Inventory System | [5 empty] | 0 | 0 | 1 |  | 55 | Manholes Storing and Quality |  |  |  |  | 0 |  | 1 | 0 | 0.69 | 0.69
27 | Logistics Plan | [6 empty] | 0 | 1 |  | 56 | Reinforced Steel Quality |  |  |  |  | 0 |  | 1 | 0 | 0.69 | 0.69
28 | Project Progress Planview |  |  |  |  | 0 |  | 0 | 1 | 0 | 57 | Safety Overview |  |  |  | 0 |  | 0 | 1 | 0 | 0.69 | 0.69
29 | Sufficient Number of QC Inspectors |  |  |  |  | 0 |  | 0 | 1 | 0 | 58 | Waste Management Control |  |  |  | 0 |  | 0 | 1 | 0 | 0.69 | 0.69
0
Score
[8 empty] | *QC % |  |  | 79.14%
Prepared by: |  |  |  | Abdul Majeed | [6 empty] | Issued to PM: |  |  | Eng.Mohammed Al Essa
*QC Observations refer only to the practices and documentation observed at time of inspection. The responsibility of the CM and Contractor is to ensure that aspects of Quality are suitably managed. *Scores are a reflection of the general site conditions based upon the findings at the time of the walk through *If Applicable

## Quality-Stat
Quality Reports
Item |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending
[6 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Non Conforomance Report (NCR) |  | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Site Instruction (SI) |  | 15 | 15 |  | 0 | 0 | 0 | 0 | 0 | 0
Material Inspection Report (MIR) |  | 81 | 65 | 16 | 0 | 0 | 0 | 0 | 0 | 0
Field Inspection Report (FIR) |  | 727 | 716 | 11 | 0 | 0 | 0 | 0 | 0 | 0
Shop Drawings
Item Per WBS |  |  | Total Planned | Total Drawings Submitted |  |  |  |  | Remaining Drawings | Pending | Total Submittals
|  |  |  | A | B | C | D | Approved | with Designer | Submittals With Consultant
Civil /Roads |  |  | 19 | 2 | 17 |  |  | 19 | 0 |  | 19
Structural |  | Structural | 129 | 8 | 121 |  |  | 129 |  |  | 129
Architectural |  | Architectural | 37 | 3 | 34 |  |  | 37 | 0 | 0 | 37
Mechanical |  | Mechanical | 41 |  | 41 |  |  | 41 | 0 | 0 | 41
Electrical |  | Electrical | 40 | 0 | 40 |  | 0 | 40 | 0 | 0 | 40
TOTAL |  |  | 266 | 13 | 253 | 0 | 0 | 266 | 0 | 0 | 266
Material Approval
Item Per WBS |  |  | Total Planned | Total Materials Submitted |  |  |  |  | Remaining to approve | Pending | Total Submittals
|  |  |  | A | B | C | D | Approved | with Designer | Submittals With Consultant
Civil / Roads |  |  | 9 |  | 9 |  | 0 | 9 |  | 0 | 9
Structural |  | Structural | 9 | 0 | 9 | 0 | 0 | 9 |  |  | 9
Architectural |  | Architectural | 30 | 1 | 26 | 0 | 1 | 26 | 0 | 2 | 30
Mechanical |  | Mechanical | 20 | 0 | 20 |  | 0 | 20 | 0 |  | 20
Electrical |  | Electrical | 18 | 0 | 18 | 0 | 0 | 18 |  |  | 18
TOTAL |  |  | 86 | 1 | 82 | 0 | 1 | 82 | 0 | 2 | 86
Procurement Summary
Item Per WBS |  |  | Total Materials Planned | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Actual Material on Site | Remaining Materials | Material Delivery Completion (Date)
|  |  |  | A | B | C | D | Processed
Civil |  |  | 9 | 9 | 9 |  | 9 | 0 | 2026-09-19
Structural |  | Structural | 9 | 9 | 9 |  | 9 | 0 | 2026-05-05
Architectural |  | Architectural | 22 | 22 | 22 |  | 22 | 0 | 2026-09-19
Mechanical |  | Mechanical | 28 | 28 | 28 | 0 | 28 | 0 | 2026-08-29
Electrical |  | Electrical | 25 | 25 | 25 |  | 25 |  | 2026-08-29
TOTAL |  |  | 93 | 93 | 93 | 0 | 93 | 0 | 2026-09-19
Consultant Quality Inspections / Observations (Weekly Basis) | [7 empty] | Overall Average | 78.88% |  | Average Closing | 1.4
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Quality Score | Date Closed | Closure Duration |  | This Week Score | 79.14% |  | Average Number of Comments Per Audit | 1.3
Week-1 | 2026-03-02 | 2026-02-11 | 2 | 80.2% | 2026-02-21 | 10
Week-2 | 2026-03-09 | 2026-02-24 | 1 | 80.2% | 2026-02-28 | 4
Week-3 | 2026-03-16 | 2026-03-02 | 2 | 80.2% | 2026-03-03 | 1
Week-4 | 2026-03-23 | 2026-03-14 | 2 | 80.2% | 2026-03-17 | 3
Week-5 | 2026-03-30 | 2026-03-25 | 1 | 80.2% | 2026-03-31 | 6
Week-6 | 2026-04-06 | 2026-04-06 | 2 | 80.2% | 2026-04-07 | 1
Week-7 | 2026-04-13 | 2026-04-09 | 3 | 80.2% | 2026-04-09 | 0
Week-8 | 2026-04-19 | 2026-04-19 | 2 | 78.3% | 2026-04-19 | 0
Week-9 | 2026-04-27 | 2026-04-26 | 3 | 78.3% | 2026-04-26 | 0
Week-10 | 2026-05-04 | 2026-05-04 | 1 | 78.3% | 2026-05-04 | 0
Week-11 | 2026-05-11 | 2026-05-10 | 1 | 78.3% | 2026-05-11 | 1
Week-12 | 2026-05-18 | 2026-05-16 | 1 | 78.3% | 2026-05-18 | 2
Week-13 | 2026-05-24 | 2026-05-23 | 1 | 78.3% | 2026-05-24 | 1
Week-14 | 2026-06-01 | 2026-05-31 | 1 | 78.3% | 2026-06-01 | 1
Week-15 | 2026-06-08 | 2026-06-07 | 1 | 78.3% | 2026-06-08 | 1
Week-16 | 2026-06-15 | 2026-06-14 | 1 | 78.3% | 2026-06-15 | 1
Week-17 | 2026-06-22 | 2026-06-21 | 1 | 78.3% | 2026-06-21 | 0
Week-18 | 2026-06-29 | 2026-06-28 | 1 | 78.3% | 2026-06-28 | 0
Week-19 | 2026-07-06 | 2026-07-05 | 1 | 78.3% | 2026-07-06 | 1
Week-20 | 2026-07-13 | 2026-07-12 | 1 | 78.3% | 2026-07-12 | 0
Week-21 | 2026-07-20 | 2026-07-19 | 1 | 78.3% | 2026-07-20 | 1
Week-22 | 2026-07-27 | 2026-07-26 | 1 | 78.3% | 2026-07-27 | 1
Week-23 | 2026-08-03 | 2026-08-02 | 1 | 78.3% | 2026-08-03 | 1
Week-24 | 2026-08-10 | 2026-08-09 | 1 | 78.3% | 2026-08-10 | 1
Week-25 | 2026-08-17 | 2026-08-16 | 1 | 78.3% | 2026-08-17 | 1
Week-26 | 2026-08-24 | 2026-08-23 | 1 | 79.1% | 2026-08-24 | 1
Week-27 | 2026-08-31 | 2026-08-30 | 1 | 79.1% | 2026-08-31 | 1
Week-28 | 2026-09-07 | 2026-09-07 | 1 | 79.1% | 2026-09-07 | 0
Week-29 | 2026-09-14 | 2026-09-13 | 1 | 79.1% | 2026-09-14 | 1
Week-30 | 2026-09-21 | 2026-09-20 | 1 | 79.1% | 2026-09-21 | 1
Week-31
Week-32
Week-33
Week-34
Week-35
Week-36
Week-37
Week-38
Week-39
Week-40
Week-41
Week-42
Week-43
Week-44
Week-45
Week-46
Week-47
Week-48
Week-49
Week-50
Week-51
Week-52
Week-53
Week-54
Week-55
Week-56
Week-57
Week-58
Week-59
Week-60
Week-61
Week-62
Week-63
Week-64
Week-65
Week-66
Week-67
Week-68
Week-69
Week-70
Week-71
Week-72
Week-73
Week-74
Week-75
Formulas:
Remaining Drawings = MAX(J34:[Remaining Drawings, row above])
Note on J24: dell: Not yet Submitted
Note on A41: Malik, Muhammad: This refers to quality observation sheet

## HSE
MODON HSE Site Inspection Report
Date |  |  | 2026-09-21 |  |  |  |  | Inspected By: |  |  |  |  | Engr Abdul Salam
Project ID. |  |  | HFR1-05-03 |  |  |  |  | Report No. | 5 |  |  |  |  | MODON PM Name |  | Eng. Mohammed Al Essa
Project Name: |  |  | Factories Low-process Unit (HAFR Al Batin) |  |  |  |  | Contractor: |  | SAK |  |  |  |  | Safety Performance |  | 3 |  |  | 78.85%
Inspections are a snapshot in time and refer only to the practices and documentation observed at the time of the Inspection. It remains the responsibility of the Consultant and Contractor to ensure that all aspects of Health & Safety are suitably managed.
1 |  | Good Practice |  |  | 2 | Need Improvement | [5 empty] | 3 | Fail (Life Threatening Activity) / Comliance with Plan & Procedures |  | N/A | Atcitty Not Applicable for this Site Inspection Report
No. | Topic | [5 empty] | Wt. | HSE Compliance |  |  | No. | Topic | [5 empty] | Wt. | HSE Compliance
1 | Access and Egress - (General access to site, segregated from vehicles, / Overhead protection, while entering into the building /Adequate lighting provided when dark or overnight work) | [5 empty] | 5% | 1 |  |  | 14 | Work at Height - (PPE/Fall Protection(Same level, above and blow) / Training / Fall restraint / competency /Safe access & egress to and from work at height / Ladders / Openings (floor/shafts/Provision of emergency rescue) | [5 empty] | 5% | 2 |  |  |  | 1 | 100 | 1
2 | Traffic Management - (Loading/unloading/sheeting/temp. routes/speed/parking/competence) | [5 empty] | 3% | 2 |  |  | 15 | Scaffolding - (Temp. Scaffolding Work-platform (All types) - qualified scaffolder / Inspection / Tagged / Safe Access/egress / PTW/Falsework & Formwork) | [5 empty] | 4% | 2 |  |  |  | 2 | 75 | 2
3 | Site Signage - (Project Notice Board & General Signage) | [5 empty] | 2% | 1 |  |  | 16 | Mobile Elevated Work platform (MEWP) - (PTW/competence requirements/conditions/inspections/tagged/training/Full-body harness) | [5 empty] | 4% | 2 |  |  |  | 3 | 0 | 3
4 | PPE Compliance - (Use, storage, stock, handling & checks - Head, Foot, Eye, Hearing) | [5 empty] | 5% | 2 |  |  | 17 | Excavation & Trenches - (PTW/Edge protection/buffer zone/Slope/Benching/Shoring/Geo-tech report/Atmospheric hazards/Acess&egress/Emergency management / MS&RA/H.E) | [5 empty] | 3% | 2 | [5 empty] | N/A
5 | Housekeeping - (Material correctly stored/Rubbish cleaned & removed daily/slips & trips hazards) | [5 empty] | 3% | 1 |  |  | 18 | Confined Space - (PTW/Training/competence/Emergency Management/MS & RA/Safe access/egress) | [5 empty] | 5% | 2
6 | Storage of Materials - (Transporting, storage, training and use - Combustible / Flammable / Hazardous substances (COSHH) | [6 empty] | 2 |  |  | 19 | Fire Protection - (Flammable/Oxy. LPG /Combustible separated/FE's/Flashback arrestor/Sparks & slags/Smoking area/PTW/Generators/MS & RA/Emergency Management) | [6 empty] | 2 |  | Red | Serious injury or death (immediately)
7 | Site Waste Management - (Hazardous waste /Combustible waste / Human waste / Construction waste - asphalt, cable, timber, paving roof sheeting tiles, plastic & bricks) | [6 empty] | 2 |  |  | 20 | Health & Welfare - (Adequate drinking water/shaded - eating & rest area/washing & sanitary facilities/Certified FA/FA Box & Stock/adequate toilets/Ambulance) | [6 empty] | 2 |  | Yellow | Minor or near miss (3 days to comply)
8 | Health Surveillance - (Expose to excessive noise/vibration/dust/silica/CO/cement/radiation/extreme weather condition) | [5 empty] | 3% | 2 |  |  | 21 | Environmental Incident Measures - (Spill/ Leakage / Concrete wash / vehicle & eqpts. wash / waste disposal/Sewers and drains/emissions/Emergency Management/Training/site run-off water) | [5 empty] | 5% | 2 |  | Green | No issues
9 | Electrical Safety - (Electrical qualified /RCD/GFCI/Industrial Cocket/LOTO/Cable-overhung or buried/Cords in good condition/current inspection tag) | [5 empty] | 5% | 2 |  |  | 22 | HSE Communications & Meetings - (Schedule HSE Meetings/Safety Committee meetings/Alerts / Lesson learned/Safety Bulletin contains latest HSE KPI) | [5 empty] | 5% | 2
10 | Tools & Equipment - (Includes, powered, hydraulic & pneumatic/Guards in place/Properly stored/RCD Protection/Earthed/Good condition & tagged) | [5 empty] | 3% | 2 |  |  | 23 | HSE Plan & Associated Procedures - (Approved updated HSE Plan/ CEMP/HAZComm/Procedures/Standards/Project Safety Risk Register) | [5 empty] | 3% | 2 |  | 26 points > 4 minors then is it’s a serious issue
11 | Manual Handling - (Lifting/loading/pulling/pushing/twisting/awkward posture/repetitive task/frequent and prolong physical effort/Reasonable practicable use of mechanical aid) | [5 empty] | 3% | 2 |  |  | 24 | Health, Safety & Environment Incident reporting - (Review of HSE Statistics, Reporting of Unsafe Act & Conditions/ Reporting of Near Miss incident/Reporting of FA cases/Record MT cases) | [5 empty] | 3% | 2
12 | Vehicle and mobile equipment / Plant - (dumpers; excavators, cranes, piling rigs, grader, roller, loaders/condition/KSA License/certification) | [5 empty] | 5% | 1 |  |  | 25 | HSE Awareness, Training & Competence - (Policy /Objective & targets/Information, training/Climatic condition awareness/Reponses in emergency situation/ Safety Behavior Observation) | [5 empty] | 4% | 2
13 | Lifting Operations & Rigging - (Lifting Plan/Lifting devices & gears/PTW/Condition/3rd party certification/bank-man/rigger/slingers/man-basket/inspection record/tagged) | [6 empty] | 2 |  |  | 26 | Project Leadership Site Tours - (Provide evidence of proactive safety performance/Deficient discovered discussed/Positive feedback/Workers resolving safety issues) | [6 empty] | 2
Prepared by: |  |  |  | Taher Alabdullatif | [6 empty] | Sent to MODON PM: |  |  |  | Eng. Mohammed Al Essa
Safety Results
1 |  | 4 |  |  |  | 2 |  | 22 |  |  |  |  | 3 | 0
Note on C13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Safe access / egress for people to their work area 2 - Safe access / egress for construction vehicles 3 - Access properly restricted-site fencing provided and maintained 4 - Access proper and not blocked 5 - Safe access is available for rescue operation 6 - Storage access / exit are clearly marked and unobstructed 8 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 9 - Ensure unauthorized public access is prevented 11 - Site assembled ladders or make-shift tables for access are forbidden on site. 13 - Use proper bridges, walkways or gangways to access or cross trenches or an excavation area 14 - Surrounding areas are cleared and barricaded and access restricted to all unauthorized trades while crane in operation 15 - To ensure early access to accredited medical / rehabilitation services 16 - Parking vehicles on site access roads causing obstruction 17 - All personnel will be instructed that access to firefighting equipment must remain clear at all times 18 - Access control gates to be locked out of hours 19 - Site access gates to be designed and located to, where possible, avoid clashes with external hazards / activities
Note on T13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Personal Fall Arrest System; 1 - Is the suitable harness harnesses is provided 2 - Are shock absorbing lanyard with 2 locking snap hooks. 3 - Is anchorage point strong enough and can support 5,000 Ibs. 4 - Do inspection checklist is being implemented before use. 5 - Is the emergency plan for rescue in place Personal Fall Restraint System; 1 - The fall restraint equipment should be set and adjusted so there is no free fall over the edge. 2 - A harness or body belt may be used 3 - The anchorage point must support 4 times the intended load. Positioning System; 1 - Is a suitable harness or body belt provided 2 - Is there a not more than 2' free fall maintained 3 - Is the anchorage point capable of supporting 2 times the intended load or 3.000 Ibs, whichever is greater 4 - Is 100% tie-off (protection from falls at all times, even when moving from point to point) provided while using personal fall protection with two lanyards Fall Protection System; 1 - Suitable edge protection and work platforms are to be provided to prevent a fall occurring 2 - Where the provision of edge protection or adequate platforms cannot be provided safety nets or other soft-landing systems such as inflatable bags are to be used to minimize the consequences of a fall. 3 - If nets are used, they must be installed by a competent rigger and fitted as close under the work surface as possible. 4 - Areas below roof works are to be cordoned off and properly signed to prevent personnel being injured from falling materials 5 - If access onto the roof cannot be avoided, edge protection is to be installed 6 - Floor and wall openings are to be protected using covers of adequate strength to withstand the expected load that will be imposed and securely fixed. 7 - Penetrations in walls such as those provided for lift shafts, door openings, etc. are to be closed with suitable strength material or have fixed protective barriers around the penetration with a sign warning personnel of the danger of falling.
Note on C14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are arrival and departure of vehicles and delivery accompany by security department? 2 - Are proper loading, unloading and securing loads, being properly controlled? 3 - Is the proper sheeting & coupling in place when transporting and disposing material to and from site? 4 - Is the parking to the designated parking lot and in reverse order? 5 - Is the designated speed limit adhered on workplace? 6 - Provision of ramps, traffic signs, cones, barriers, demarcation posts and tape, flashing lights and any other traffic control devices. 7 - Do visiting drivers are being inducted at the workplace, prior to enter on the workplace? 8 - Are visiting drivers restricted to dangerous areas, e.g. moving to and from they vehicles to washrooms, lavatory & offices etc.? 9 - Do drivers observe site rules and procedures, for delivery, loading and unloading? 10 - Are the areas wide enough for the safe movement of large vehicles (including visiting vehicles)? 11 - Does drivers are competent, hold valid local driving license and competent training? 12 - Ensure the vehicle and trailers have their brakes applied and all stabilizers properly positioned before beginning loading or unloading?
Note on T14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Base soundness, load adequately spread (base plate jacks, base plate on firm ground). 2 - Line of standard (vertical) and ledger (horizontal) secure and plumb. 3 - Spacing of transoms on platforms, support for Scaff boards, boards are not over protruded and boards are secured. 4 - Staggering of joints vertical and horizontal. 5 - Guardrail / fall protection. (Top rail – Min.1mtr, Mid rail – 470mm from floor and Toe boards – Minimum150mm) 6 - Longitude and bracing on standards and ledgers. 7 - If close to structure, ties must be on lift below to top working platform and every 3m, load bearing couplers used or tie with certified anchor bolts (eye bolts). 8 - Clamps and tubes used are of correct fittings, size and free from defects. 9 - Tubes & fittings free from defects / deformation. 10 - Safe and proper access available to the working platform. 11 - Scaff tags signed, displayed and up to date. 12 - If close to slab edge/opening scaffold tied and secured to structure correctly.
Note on C15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a Project Notice Board - (showing HSE Statistics / Safety alerts / lesson learned)? 2 - Is there prominent safety boards that are depicting the mandatory PPE on the workplace? 3 - Are other safety required signs are prominently installed on the workplace in relevant to their work-task, as following: > Hazardous Substances - e.g. respiratory protection Sign > Working at Height - e.g. Full body Harness Sign > Working UG - e.g. Full body Harness, SCBA, Ventilation, PTW Signage etc. > Working with Electrical - e.g. Leather Gloves, Goggles, Face shield, Electric shock proof helmet & shoes > Working with Chemicals - Signage = e.g. Impermeable gloves/clothing's, long sleeves, Goggles 4 - General Site Safety Signs: > Prohibition Sign = (e.g., ‘no access for unauthorized persons’). > Warning Signs = (e.g., ‘danger: electricity’) > Mandatory Signs = e.g., ‘eye protection must be worn’) > Emergency Escape or First Aid Sign = e.g., ‘emergency exit/escape route’) > Safety Color Signs = (e.g., yellow means ‘be careful’ or ‘take precautions’) > Illuminated Signs = (e.g., many emergency exit signs) > Acoustic Signals =( e.g., fire alarm) > Fire safety sign > Supplementary Signs = "This way"
Note on T15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Man-Lift operators are to be competent and trained to operate the specific Man-Lift by examination and hold a current approved certificate / license from an approved and internationally recognized source (TUV, SGS etc. 1 - All Man-Lifts shall be inspected by a 3rd party on an annual basis. 2 - All Man-Lifts shall display a sticker corresponding to the 3rd party inspection certificate. 3 - The manufacturer's instruction manual must be on site for each and every type of Man-Lift in use. 4- A pre-start daily operator inspection of the equipment will be performed and documented on a daily basis as per the manufacturer's instructions. The user is responsible for ensuring this has occurred. 5 - The use of a Man-Lift as, or in lieu of, a Crane is strictly prohibited. Man-Lifts are to be used only for lifting personnel and small tools within the designed Safe Working Load. 6 - The platform is not to be loaded in excess of the designed working load; the safe working load of the platform is to be clearly displayed on both the platform, and body of the equipment. 7 - All persons inside work platforms shall wear a full-body harness attached to the designated anchor point. Personnel must stand on the floor of the working platform; standing on the handrails is strictly prohibited. Harnesses must not be attached to other structures outside of the working platform. 8 - Personnel must stay inside the working platform at all times; the platform must not be used as an access to structures. The use of staging or ladders to extend height is strictly forbidden. 9 - Securing the boom or work platform to any structure is strictly prohibited. The boom or working platform must not be rested upon on any structure, nor is the Man-Lift to be used as a jack/ prop or tie to support other structures. 10 - All Man-Lifts must be equipped with a 5kg (10lb) fire extinguisher. 11 - No man-lifts are to be operated that have had safety devices removed or disabled. Daily operator inspections are to include the testing of these devices (limit switches, alarms and hazard flashing beacons). 12 - Specific Man-Lifts are fitted with outriggers and/or stabilizers which must be used as per manufacturer's instructions. 13 - The work area surrounding the man-lift is to be cordoned off using barricades and signage if the area is used by other workers or vehicles. A full traffic management plan is required for all works involving man-lifts when working on highways. Under no circumstances is any part of a man-lift to extend or swing into a line of traffic.
Note on C16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Does required mandatory PPE (refer specification BS, EN & ANSI) is provided, as following? > Safety helmet (see below for color scheme) > Safety glasses (shaded for outdoor work and clear inside structures and during non-daylight hours) > Safety boots (safety shoes are prohibited) > Orange hi-visibility vest 2 - Additional PPE shall be provided to a specific task 3 - Do specific PPE is provided according to their job requirement? > To work at height - Full Body harness / Fall arrest Devices / Fall Restraint Devices / V & H Lifeline etc. > To work in the confined space - Full Bodyarness, Tripod with retractable lifeline, SCBA, Masks etc. > 4 - Are the PPE stored appropriately to prevent deformation or distortion? 5 - Has self assessment being carried out for in according to the work requirements? 6 - EYEWEAR (Glasses/Goggles/Face Shields) > Eyewear cleaning supplies available. > Safety glasses in good condition and lenses free of scratches. > Goggles adjustment strap not cracked or frayed, not deformed, or lenses not > Face shields in good condition, including adjustment band, and free of scratches or 7 - HEAD PROTECTION > Hard hat bill and suspension attached as allowed by manufacturer. > is pliable, free of dents, cracks, nicks, or any damage due to impact. > Suspension maintained at 1.25 inches from inside of shell. > Suspension free of cuts or fraying, torn headband, adjustment strap workable. > Electrical hard hat matched to hazard classification. > Dated to determine whether within manufacturer’s allowable 5-year use time period. 8 - HAND PROTECTION > Available in sizes matched to employee. > Gloves free of rips tears, abrasions, or holes. > Matched to manufacturer’s specification for chemicals used onsite. > Electrical gloves matched to hazard and periodically inspected for insulating rating. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. 9 - BODY PROTECTION > Available in sizes matched to employee. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. > Vapor-tight fully encapsulated suits tested at required periodic intervals. > Flame-resistant clothing matched to electrical hazard and arc flash rating. > Welding gear matched to degree of hazard and free of cuts, tears or burn holes. > Flotation gear available for work near or on water and in good condition. 10 - HOT AND COLD BODY PROTECTION > Cooling gear available based on degree of heat stress hazard. > Cooling gear in operable, clean, and sanitary condition. > Cold-weather gear provided based on needs assessment. > Cold-weather gear available in sizes to match employees. > Cold-weather gear is in free of tears, rips, or holes and in maintained in a clean condition. 11 - TRAINING > Initial PPE training completed by employees. > Training conducted when new types or styles of PPE are issued. > PPE selection, use, and maintenance reviewed at daily safety briefings. 12 - Provision of impermeable clothing appropriate for the work being performed? 13 - Wearing of shorts, sleeveless shirts, loose clothing are prohibited across the MODON Projects. 14 - Clothing contaminated with grease, oils, fuels and other hazardous substances is not to be worn.
Note on T16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a valid Excavation PTW in place? 2 - Are spoils, materials, and equipment set back at least 1.5 meters from the edge of the excavation? 3 - Are walkways and bridges over excavations structurally sound, minimum 0.5 meter in width and equipped with standard guard rails and toe boards? 4 - Are warning systems established and used when mobile equipment is operating near the edge of an excavation? 5 - Are employees prohibited from working on the faces of sloped or benched excavations above other employees? 6 - Are the exact locations of Utilities (piping, electrical, etc.) clearly marked? 7 - Are underground installations protected, supported, or removed when an excavation is open? 8 - Are ladders or other means of access and egress in place as per the PTW requirements? 9 - Are all workers within 7.6 meters of a means of access and egress to a trench? 10 - Are ALL ramps constructed of materials of uniform thickness, cleated together, equipped with no-slip surfaces? 11 - Are employees protected from cave-ins when entering or exiting excavation? 12 - Are precautions taken to protect employees from water accumulation and dewatering is being carried out? 13 - Is surface water or runoff diverted after every rainstorm or other hazard-increasing occurrence? 14 - Is the excavation classified as a confined space? If so, is their a valid confined space PTW and is the atmosphere being tested when there is a reasonable possibility of an oxygen-deficient, oxygen-enriched, combustible, toxic, or other harmful contaminant? 15 - Have materials and/or equipment chosen for shoring been based upon soils analysis, trench depth and expected loads (as per Excavation PTW)? 16 - Are shoring materials and equipment that are used for protective systems inspected and in good condition? 17 - Are damaged shoring materials and equipment immediately removed from service? 18 - Are damaged shoring materials and equipment inspected by a Registered Professional Engineer after repairs are made and before being placed back in service? 19 - Are protective systems installed without exposing employees to hazards of cave-ins, collapses, or threat of being struck by materials or equipment? 20 - Are ALL members of support systems securely fastened together to prevent failure? 21 - Are support systems provided to insure stability of adjacent structures, buildings, roadways, sidewalks, etc.? 22 - Are excavations below the level of the base or footing supported, and approved by a Registered Professional Engineer? 23 - Does back-filling progress with the removal of the support system? 24 - Is a shield system installed to prevent lateral movement? 25 - Are employees prohibited from remaining in a shield system during vertical movement?
Note on C17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Sites are to be kept clean and tidy and free from slip, trip and fall hazards. 2 - Do all personnel trained in the importance of good housekeeping, managers, supervisors undertake regular monitoring and inspection of the workplace? 3 - Workplace are to be left clean and tidy at the end of each shift and where there is an accumulation of materials throughout the shift, at regular intervals as required to maintain a clean and safe site. 4 - Buildings under construction and nearing completion must ensure that all combustible and flammable materials are removed at the end of each shift. 5 - Nails are to be removed from timber as soon as possible, where this is not practical they are to be flattened and placed in a safe area (barrier and signs) until nails can be removed at a later time. 6 - Materials are to be stored so as they do not pose a risk to personnel stacking, removing or walking by (further guidance is given in the materials storage and handling section). 7 - All spills are to be cleaned up immediately using absorbent material. 8 - Cables/hoses/other trailing leads are to be protected, buried or secured above head height to avoid a slip trip, fall hazard. 9 - Waste is to be placed in designated containers and covered to protect against high winds, pests or risk of fire. Waste containers are to be emptied on a regular basis to prevent a build-up of material. 10 - Loose or light materials that are stored on roofs or open spaces are to be secured to prevent them from inclement weather. Location: 1 - Receptacles located inside buildings shall be kept at least 18 inches away from combustible walls and partitions. 2 - Receptacles for combustible trash that are located outside of buildings shall be placed at least 15 feet from the building or combustible material. Use: 1 - Cigarettes, cigar butts, matches, and similar potential ignition sources should never be placed in a trash receptacle. Proper receptacles for such items should be provided in areas designated for smoking. 2 - Broken glass, empty jars, scrap metal, and similar construction material should never be placed in office trash containers. A roll-off bin or other appropriate container should be used to hold construction debris. Environmental: 1 - Container storage areas shall be kept clean and free of trash. Improper disposal of food waste can attract pests and vermin. Prevention methods that do not involve the use of toxic chemicals is the preferred method of pest control. 2 - Outdoor containers should be kept covered when not in use so as to avoid attracting pests and to prevent the entry of water. Dripping or leaking trash containers may violate local storm water quality discharge regulations. 3 - Promote recycling by contracting with a waste removal company that provides reuse as part of the waste processing or by providing segregated bins for the collection of office paper, aluminum cans, plastic bottles, and toner cartridges. Rinse empty cans and bottles of sugar-based soda so as not to attract ants and other pests. 4 - Proper lighting (indoor) or during Night Shift are provided. Accurately installed. No impairement or poor visibilty is generated. No shadow due to installation of lights are presents.
Note on T17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Permit is taken for confined space entry and all recommended precautions are in place. 2 - Operatives are trained and fit for the specified job. 3 - Confined space is well ventilated by means of mechanical ventilation. (Exhaust fan, blowers, low velocity air hose etc.). 4 - Rescue system (Tripod with hoisting device, Rescue Harness etc.) in place and sufficient trained persons are available for the rescue operation. 5 - Safe access is available for rescue operation. (Manhole size - Min. 450 mm X 407 mm or 457 mm Dia.) 6 - Atmospheric monitoring conducted and confined space is safe to enter. Percentage of gas concentration will be monitored and recorded every 4 hrs. A. Oxygen percentage. (Permissible limit – 19.5% to 23.5%) B. Flammable gas or vapors.(Permissible limit - <10% of LFL) C. Carbon Monoxide. (Permissible limit - <50ppm) D. Hydrogen sulfide.(Permissible limit - <10ppm) E. Any other toxic gas or vapors. _______________________________ 7 - Minimum two persons shall be assigned to work in the confined space. One person will remain in the entrance at all times to monitor the work 8 - All persons shall wear safety harness, which should be connected to safety line from outside at all times. 9 - All electrical equipment & leads are free from damage and guards in place. 10 - All electrical tools & equipment are connected through ELCB. 11 - Compressed gas cylinders are kept outside the confined space. 12 - supervisor / Foreman will be available at all time to monitor the work and for the rescue operation. 13 - Tool box talk conducted for the entire team and they are well aware of the risks. 14 - Proper communication system is available in between persons inside and standby person. 15 - Trained First aider with first aid kit will be available when working in the confined space. 16 - Confined space entry register is available and shift records will be maintained. -
Note on C18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Combustible: 1 - Ensure oily rags, combustible material and other flammable substances which may ignite are not accumulated and that they are removed without delay to the designated disposal / storage area. 2 - Combustible materials shall not be stored within 20 feet (6.1 meters) of compressed gas cylinders. 3 - Safety cans used for dispensing combustible liquids shall be kept at a point of use 4 - Storage rooms for combustible liquids must have explosion-proof light fixtures 5 - No flames - hot work or smoking is be permitted in combustible liquid storage areas. Flammable: 1 - Adequate training in the use and storage of flammable liquids is in place. 2 - Storage of Flammable liquids in accordance with NFPA approved flammable storage lockers or in low value structures at least 50 feet from any other structure. 3 - Do not store other combustible materials near flammable storage areas 4 - Bulk drums of flammable liquids must be grounded and bonded to containers during dispensing 5 - Portable containers of gasoline or diesel are not to exceed 5 gallons 6 - Safety cans used for dispensing flammable liquids shall be kept at a point of use 7 - Appropriate fire extinguishers are to be mounted within 75 feet of outside areas containing flammable liquids, and within 10 feet of any inside storage area for such materials. 8 - Storage rooms for flammable liquids must have explosion-proof light fixtures 9 - No flames - hot work or smoking is be permitted in flammable or combustible liquid storage areas. 10 - Flammable liquid transfer areas are to be separated from other operations by distance or by construction having proper fire resistance. 11 - When not in use flammable liquids shall be kept in covered containers. 12 - Flammable materials are considered hazardous and as such, material safety data sheets and appropriate hazard communication training for affected employees is required 13 - Maintain high levels of housekeeping, particularly with relations to flammable materials. 14 - Where flammable materials are handled in the course of work, safe work procedures must be prepared and documented with reference made to the Material Safety Data Sheets (MSDS‘s) for the materials concerned. 15 - All people handling, working with or in control of flammable substances must be properly trained and supervised (documentation to be maintained). 16 - Lead, dust, fumes and vapor constitute a major health hazard to workers. Hazardous Substances COSHH 1 - Under COSHH the risk presented by any hazardous substance assessed using hierarchy of control, stored, transported, created or disposed and usage at the workplace; > Very toxic or toxic: Substances that, in low quantities, cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Harmful: Substances that may cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Corrosive: Substances that may, on contact with living tissues, destroy them > inhalation into the lungs, when the substance is in the form of a gas, vapor, fume, mist, aerosol or dust > absorption through the skin or eyes by contact with a substance that can penetrate unbroken skin, or is absorbed through unprotected cuts or grazes > injection by contact with contaminated sharp objects or high-pressure equipment, e.g. water jetting > ingestion by swallowing particles of a hazardous substance resulting from hand-to- mouth transfer
Note on T18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are regular and frequent fire safety inspections carried out? 2 - Have a sufficient number of fire marshals/evacuation officers been appointed? 3 - Are water supplies adequate? 4 - Does the building or site have a written fire procedure? 5 - Is there an effective permit to work system in operation for all hot work and other fire related work? 6 - Do all doors from areas from which a large number of people may have to escape open in the direction of travel? 7 - Do all emergency exit doors (i.e. doors not in normal use) have clear instructions displayed on how to open? 8 - Are all escape routes clear and unobstructed? 9 - Are all fire exit doors correctly signed? 10 - Is all fire fighting equipment immediately visible or correctly signed? 11 - Are all flammable and explosive substances adequately signed to indicate their presence and danger? 12 - Where necessary, is there a sufficient number of emergency lights to adequately illuminate all internal escape routes, exit doors and signs? 13 - Where automatic fire detection is deemed to be necessary is there an adequate number of detectors in the critical areas? 14 - Where the means of raising the alarm is by hand-operated devices, can the operation of one device be heard throughout the entire building or site? 15 - Is there an adequate number of fire extinguishers in the building? 16 - Is there firefighting equipment other than extinguishers in the building? 17 - Are all electrical circuits and fixed electrical installations examined and tested at an acceptable frequency? 18 - Is housekeeping to an acceptable standard? 19 - Have all staff been trained in fire procedures in the last twelve months? 20 - Are all fire drills adequately recorded?
Note on C19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - General construction waste streams generated including; > Asphalt, cable, timber, paving, roof sheeting, tiles, plastic sheeting and brickwork. > Excess concrete, spoil material from excavations. > General waste, such as putrescible food scraps and packaging from workers. > General (food) waste, construction/concrete waste, hazardous waste, paper/cardboard and waste water/sewage. 2 - Are hazardous waste identified with hazardous Waste label. 3 - Containers are properly labeled in according to their contents. 4 - Container inspections are documented in writing using the Container Inspection Checklist. 5 - Weekly inspections logged into book using the Accumulation Area Inspection Log Sheet. “NO SMOKING OR OPEN FLAME” sign posted. 6 Disposal facilities identified, evaluated using the procedures. 7 - Disposal facility accepted waste and issue approval letter. 8 - Waste transfer/dispose tracked using Waste Tracking Form. 9 - Waste streams, such as asphalt and concrete, to be recycled should be segregated and separately stored. 10 - Spill Release Contingency: 1 - Prior to beginning operations, ensure that on-site spill response capabilities (containment and personal protective equipment) are consistent with task requirements described in job hazard analysis.
Note on T19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: HHE is required at all locations where chemical hazards exist, such as; storing, transferring and handling facilities, under routine conditions. The HHE scope shall include the physical, chemical, radiological, and biological health hazards. Physical health hazards include elevated noise and vibration exposures, repetitive motion work operations, ionizing and non-ionizing radiation exposures heat and cold stress and biological hazards include infectious disease agents. HHE shall be performed before the site mobilization; 1 - Is the adequate eating or mess area is provided and sufficient for number of workers? 2 - Are sufficient tables and Chair are provide and Kept Clean? 3 - Are FEs, signs, pest control being implemented? 4 - Is washing Area sufficient and Kept Clean? 5- Cooking Area Kept Clean? 6 - L.P.G. Cylinder stored outside, secured & upright 7 - Sufficient drinking water provided. Filters changed (as per manufacturer recommendation)? 8 - Sufficient toilets, washbasins, cleaned/disinfectant provided? 9 - Provision of First Aider 10 - Provision of Nurse 11 - Provision of First Aid Kit 12 - Provision of site clinic with required first aid equipment and items. 13 - Provision of shaded area on the workplace 14 - Provision of Ambulance or an equal arrangement in place" 15 - Smoking area is Prohibited other than designated smoking areas, clear of flammable and combustible materials? 16 - All toilets, washing, rest and eating facilities to be kept clean, hygienic and be well maintained at all times? 17 - Waste Management - Covered bins, emptied daily, close proximity, color coded etc.? 18 - Are the monitoring, including integrated air sampling, noise dosimetry and other exposure assessments, being carried out? 19 - Are the Physical, chemical, and biological stresses, being identified, results are taken with action level to prevent sickness, impaired health, significant discomfort, or inefficiency in workers? 20 - Are WEL, LEL, OEL PEL & TLV linked to control workers airborne exposure to a chemical in a concentration above which is likely to cause death or immediate or delayed permanent adverse health effects or prevent escape from such an environment, if bening implemented?
Note on C20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Is the hierarchy of Control is beng carried out on the following and recorded; 1 - Exposure to Chemical; e.g. - Dust, Gas, Mist, Vapor 2 - Exposure to Radiation; e.g. - Pipe radiography etc. 3 - Exposure to Biological Hazard; e.g. - Bloodborne pathogens / Legionella / Leptospirosis 4 - Exposure to noise; e.g. Loss of hearing / Physical damage to hearing mechanism 5 - Heat and cold stress work; e.g. - Heat-stroke, Heat stress / Frostbite / 6 - Repetitive Motion Work; e.g. - Musculoskeletal disorder, awkward position etc. 7 - Is the risk assessment carried out on the hazardous material and covering the following; > Allowable exposure limits, > Exposure monitoring requirements, > Methods of compliance for potential over exposure conditions, > Medical surveillance program, > Hazard communication, employee training requirements, 8- Is the IH Surveillance Plan should being implemented and have rocored on the following; > Which exposure groups require IH monitoring and medical surveillance > Specific substances or agents to be monitored, > The OELs to be used to evaluate results > The statistical basis to continue or cease monitoring > Specific medical testing/protocol to be implemented 9 - Do we've program on identifies work conditions such as the following, the exposure must first be mitigated or work shall not be performed. > Oxygen concentrations less than 19.5% or greater than 23.5%, or > Atmospheres greater than 1% of the Lower Explosive Limit, or > Atmospheres that are >50% of Immediately Dangerous to Life or Health (IDLH) concentrations, or > Work with sensitizers or known human carcinogens, mutagens, or teratogens without process isolation or fully encapsulating personal protection, or > Work with highly infectious biological agents without process isolation
Note on T20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are all dispensing areas diked or properly graded to control drainage of spilled fuel? 2 - are all workers and operatives are trained to use spill response kit? 3 - Is the procedure in place for collecting and/or containing, and disposing of spilled materials? 4 - All tanks & vessels areas are diked to contain accidental spills?. 5 - Do measures taken to prevent an accidental contaminated runoff from construction , operation, maintenance, plant and storage areas? 6 - Do measures taken to control on deposits of oils, greases and fuels, from site plant and vehicle operations, mechanical failures, spillages and discharges to ground or drains and the dispersion of unattended spills by plant / vehicle movements?. 7 - Do measures taken to control on fuels, oils and other hazardous chemicals spilled on site during re-fueling, storage or transport operations?. 8 - Do we have an Emergency Response Procedure will be followed in the event of environmental emergency such as an oil or chemical spill? 9 - Is there a procedure for concrete wash, clean and dispose to prevent ground contamination, such as; Concrete wash pits with leak proof sedimentation tanks will be provided for washing concrete mixer trucks. The design and location of such wash pits shall be agreed with the Project Manager prior to its construction on site. Concrete dumping or spillages of any kind shall not be allowed in any other location on site? 10 - Is there a procedure to used in the situation of a major spills that will have an impact on the surrounding environment will be promptly reported to the Fire Brigade? 11 - Are there a procedure of disposing off any damage/leakage drums or containers shall be removed in accordance with the local requirements? 12 - Are there a procedure of dealing with spilled contaminated soils, resulted and remediated, accordingly? 13 - Are all personnel trained in the use of spill procedure and response and the adequate spill kits are available on site?
Note on C21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - All electrical extension cords are equipped with nonconductive plugs 2 - Cords must not be spliced or draped over nails, metal objects 3 - The use of extension cords by means of multiple outlet plugs from single outlets is prohibited 4 - All electrical service removals, alterations and equipment installations are performed by an authorized electrician 5 - Faulty electrical installation 6 - Electrical supply disruption 7 - Exposed cables 8 - Trip / fall hazards from installed cables 9 - Fire hazard Electrical overload 10 - electrocution 11 - Electrical (short circuit) - Contact with exposed conductors or a device that is incorrectly or inadvertently grounded, such as when a metal ladder comes into contact with power lines 12 - Electrical - (static discharge) 13 - Electrical Fire - Use of electrical power that results in electrical overheating or arcing to the point of combustion or ignition of flammables, or electrical component damage 14 - Improper grounding 15 - Damaged insulation 16 - Exposed electrical parts 17 - Overloaded circuits 18 - Inadequate wiring 19 - Wet conditions 20 - Overhead power lines 21 - Damaged tools and equipment
Note on T21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a meaningful and an effective consultation and communication on health and safety matters being implemented through out the project? 2 - Is the Consultation and communication on health and safety matters in place through the following mechanisms: > Project specific induction - (prior to commencement of contracted work) > Work activity Induction (in SWMS or equivalent) - (prior to commencement any construction work) > Toolbox Meetings - (Monthly intervals or generally when there is the introduction of a new process (SWMS) or when discussing OHS issues/topics). > Subcontractor Meetings - (weekly) > Project team meetings - (weekly) > HSE Committee Meeting - (as agreed with the HSE Committee) > OHS Report - (monthly) > Project Notice Board and general signage - (as required) 3 - Is there a method of communication is to be established in the work procedures to allow constant monitoring of those persons working in the confined space? 4 - Is there a material safety data sheets and appropriate hazard communication training for affected employees is in place? 5 - Are all environmental aspects and impacts been communicated to employees? 6 - Dose the notice
Note on C22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1- Check that all the workers are using safe hand tools/power tools and instruct them to operate and maintain the same in safe manner 2 - Ensure power tools and hand tools are checked prior to issue 3 - Damaged tools and equipment 4 - Electrical tools or electrical equipment are not to be issued for use until inspected. 5 - Electrical tools or electrical equipment are not to be issued for use until inspected. 6 - "Defective" electrical tools and equipment are to be tagged and removed from service until repaired and inspected 7 - The frequency for inspection of construction electrical tools and electrical equipment shall be monthly and inspection indicated by attached color-coded tape or color- coded tie wraps and a color coded inspection tag with Contractor‘s name, the supervisor, the inspection date, equipment number and signature of competent inspector displayed on the tag. 8 - Checking the cords for worn or cracked insulation. 9 - Checking the cords entry to plug and tool housing for frayed or worn insulation and strain relief. 10 - Checking the plug prongs for damage. 11 - Checking the plug for exposed connectors 12 - Checking the equipment housing for damage. 13 - Checking trigger locks to ensure they have been removed 14 - Checking the leads for signs of wear, poor connections at probes, etc. 15 - Checking the housing and the readout window for cracks, loose screws, etc. 16 - Check all Ground Fault Circuit Interrupters (GFCI) during the monthly inspections. 17 - Machines are free from any defects / damage. 18 - Pressure switch and safety guards in place where applicable. 19 - Leads are fitted with correct plugs & sockets and free from damages. 20 - Leads wires are free from joints, cuts and other defects. 21 - Leads are suitably rated for the electric current. 22 - Machines / Tools are equipped with properly functioning dead man switch. 23 - Tools issue and maintenance record is properly maintained. 24 - Tools are correctly stored. 25 - Discarded Tools / cords are marked and stored separately.
Note on T22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is the Project HSE Plan presents actions, responsibilities, protocol, conformance, verification and containment activities to be undertaken by project staff and sub-contractors at all times during the construction phase of the project. 2 - Is the implementation of the HSE plan is being monitored, evaluated for accuracy and any changes made communicated to all relevant personnel. 3 - Is the HSE Plan, CEMP, Security Plan, HAZcomm., standards & procedures are updated, signed, approved and distributed, acknowledged to the construction team's responsible individuals? 4 -Is the project overall safety risk register developed, approved and being implemented?
Note on C23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Immediate Postural and Load Factor; 1- Is the body position stable? 2 - Is the trunk of the body straight (not twisted)? 3 - Is the operation carried out by one person? 4 - Is the load kept close to the body? 5 - Can the handler avoid stretching upwards? 6 - Can the handler avoid a prolonged period in one posture? 7 - Can the handler perform the task without overreaching? 8 - Are both hands used for grasping? 9 - Are the hands less than a shoulder width apart? 10 - Is the load positioned centrally in front of the body? 11 - Is the load reasonably symmetrical? 12 - Is the load stable and easy to grasp? 13 - Can handlers move and position themselves freely? Environmental Risk Factor; 1 - Too hot? 2 - Too cold? 3 - Too bright? 4 - Too dark? 5 - Too noisy to allow effective communication? 6 - Too wet? 7 - Slippery underfoot? 8 - Does any personal protective equipment interfere with the task? Carrying; 1 - Is the load carried at knuckle height? 2 - Is the load carried at arm's length from the body? 3 - Is the load carried for more than 10 meters? Seated Work; 1 - Is the load lifted from below thigh height? 2 - Is the load lifted to above shoulder height? 3 - Is the load lifted at arm's length from the body? 4 - Does the handler have to twist significantly to the side? 5 - Is the load heavier than 5kg? Pushing and Pulling; 1 - Does the pushing and pulling take place below knuckle height? 2 - Does the pushing and pulling take place above shoulder height? 3 - Is the initial or maximum force required to push or pull the load more than 25kg? 4 - Is the continuous force required to keep the load in motion more than 10kg?
Note on T23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a system of proper HSE reporting in place, such as; all work-related incidents including near misses, injuries, illnesses, property damage, environmental incidents, security events and motor vehicle incidents, using proper protocol followed? 2 - Is the HSE incidents, accident, near misses, unsafe acts/conditions and dangerous occurrences are being reporting in timely manner and in the approved company format? 3 - Are the workers informed, trained in reporting all near misses, unsafe acts/conditions to the appropriate authority or line of manager? 4 - Is the Weekly / Monthly HSE Statistics data, including (leading & lagging) indicators, reviewed by the senior management?
Note on C24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: CHECKS; 1 - Plant guarding is in place and in good condition to prevent injury from parts disintegrating or failing 2 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 3 - Operator's seat and controls are in good condition and all safety devices (limiters and indicators) are labelled and fully operational. 4 - Operator's manual / instructions supplied by the manufacturer of the plant are available in the plant. 5 - Hazards with the use of the plant are identified, i.e. Safe working limits on batters, operator safety instructions etc., are displayed clearly in the cabin of the plant for operator reference. I.E. PLANT SPECIFIC RISK ASSESSMENT. 6 - Hazard controls, i.e. seat belts must be worn and hearing protection must be worn, caution/danger signs (counter weight slewing area, excavators and cranes) etc. are displayed in the cabin or on the plant in a position relevant to the hazard. 7 - Operator cabin/work platform access is clean and free of debris, loose tools, equipment, grease oil and is in an orderly condition. 8 - Plant is clean and free from oil leaks and oil build up. 9 - Plant Pre Start inspection is complete and a record of the inspection will be provided at commencement on the site. 10 - Certification of operator / proof of competency. 11 - Operational Noise Level - Statement of conforming emission level. 12 - Plant has no areas of excessive wear or damage. Mobile plant required to have; 1 - Plant is fitted with a Roll Over Protection Structure (R.O.P.S.) and operator restraint. 2 - Plant is fitted with a front horn and reversing beeper. 3 - Plant is fitted with a rotating or flashing amber beacon. Plant used to lift Material and equipment; Backhoes, excavators, cranes and loaders used as crane from designed lifting points. The Safe Working Load of the plant item is displayed on the plant as: EITHER; A Crane Chart supplied by the manufacturer specific to the plant item in the cabin of the plant for operator reference OR; The Safe Working Load of the equipment on the boom of the loader bucket and of the dipper arm of excavators - a combination of both is required for backhoes e.g. SWL 1.2ton. Personal Lifting Equipment - (Cherry Pickers, boom lift and elevated platform) 1 - Safety Working Load is displayed on work bucket / platform. 2 - Fully body harnesses and lanyards are to be provided for personnel using the equipment. 3 - Safety Instruction for the operation of the equipment is clearly displayed in the work bucket / platform. 4 - The supplier have provided training for personnel using the platform in the safe use of the equipment
Note on T24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Do all personnel have the correct information, instruction and training according to their role and responsibilities? 2 - Is the contractor promoting awareness of company standards and regulations among their employees on a regular basis, or when it is necessary? 3 - Do all personnel have completed basic relevant awareness training, such as; Fire Awareness Training, Heat Stress awareness Training, Safety Signs and Color Code awareness Training, Environmental Awareness Training, Using Fire Extinguisher Awareness Training, Emergency reporting Awareness Training, Unsafe Act/Conditions reporting awareness training, Evacuation Procedure Awareness Training?
Note on C25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Crane Inspected 2 - Operator certified 3 - Lift Plan approved 4 - PTW obtained 5 - lifting equipment is suitable for the use it is being put to, marked with safe working load, properly maintained and inspected, and receives a periodic thorough examination. 6 - Are all members of the lifting operations team including the Appointed Person, Crane Drivers and Slingers / Signalers / Banksmen will be competent and have such practical and theoretical knowledge and experience as is necessary to carry out their duties. 7 - Bank man is available and certified 8 - The crane operator have a practical and theoretical knowledge of lifting operations 9 - Lifting operations will be undertaken by a minimum of three competent people the crane operator, slinger / signaler (slinger and signaler can be one person) / banks man / flagman (banks man and flagmen can be one person) and Supervisor 10 - Certification of Lifting Equipment / Lifting Gear / Lifting Devices 11 - Lifting plan prepared/approved/communicated 12 - Lifting gear (Chain sling, shackle, webbing sling, lifting clamps etc.) / devices (Chain block, Winch, Monorail etc.) are checked, inspected & tagged - ( size, length, dia, width, SWL,Condition & defects. 13 - All lifting equipment / gears have valid test certificates and are in good condition.
Note on T25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there process of SBO for leadership to identify and reinforce safe work practices/behaviors? 2 - Is there process of SBO for leadership to identify and improve on at-risk practices? 3 - Is there process of SBO for leadership to identify and improve on practices, conditions, controls, and compliance that eliminate or reduce hazards? 4 - Is there a process of SBO for leadership to make positive, corrective, cooperative, collaborative feedback/recommendations? 5 - Is there a training program for BBST, that how to identify critical safety behavior and how to provide feedback and the number of personnel trained. 6 - Is there a program for the leadership to carry out SBO once a month or twice (depends project scope of work), and record available?

## HSE-Stat
Safety Statistics
Category | Item |  | This Week | This Month | Year to Date | Cumulative
Category | Total Hours Worked |  | 3480 | 11400 | 143630 | 143630 |  |  | 64 | 64
| Safe Hours Worked |  | 3480 | 11400 | 143630 | 143630 |  |  |  | 0
Reactive | LTI |  | 0 | 0 | 0 | 0
| MTC (Healed w/o Disability) |  | 0 | 0 | 0 | 0
| MTC (Healed w/ Disability) |  | 0 | 0 | 0 | 0
| Near Miss |  | 0 | 0 | 0 | 0
| First Aid Cases |  | 0 | 0 | 0 | 0
| Fatality |  | 0 | 0 | 0 | 0
| Fire Incident Cases |  | 0 | 0 | 0 | 0
| Vehicle Incident |  | 0 | 0 | 0 | 0
| Property Damages |  | 0 | 0 | 0 | 0
Proactive | Induction Training |  | 0 | 7 | 11 | 11
| No.of Internal Training |  | 0 | 4 | 5 | 5
| No.of Internal Audit |  | 0 | 1 | 5 | 5
| No. of Toolbox Talks |  | 0 | 18 | 23 | 23
| Safety Awards/Incentives |  | 0 | 0 | 0 | 0
[7 empty] | Category | Item |  | This Week | This Month | Year to Date | Cumulative
Consultant Safety Inspection (Weekly Basis) | [6 empty] | Overall Average | 75.5%
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Overall Score | Date Closed | Closure Duration | This Week Score | 78.85%
Week-1 | 2026-03-02 | 2026-02-19 | 7 | 66% | 2026-03-02
Week-2 | 2026-03-09 | 2026-02-28 | 5 | 66% | 2026-03-03
Week-3 | 2026-03-16 | 2026-02-28 | 5 | 66% | 2026-03-03
Week-4 | 2026-03-23 | 2026-03-28 | 6 | 66% | 2026-03-29
Week-5 | 2026-03-30 | 2026-03-27 | 6 | 66% | 2026-04-04
Week-6 | 2026-04-06 | 2026-03-27 | 5 | 66% | 2026-04-11
Week-7 | 2026-04-13 | 2026-04-07 | 6 | 66% | 2026-04-11
Week-8 | 2026-04-19 | 2026-03-28 | 7 | 66% | 2026-04-17
Week-9 | 2026-04-27 | 2026-04-26 | 4 | 78% | 2026-04-26
Week-10 | 2026-05-04 | 2026-05-03 | 1 | 79% | 2026-05-04
Week-11 | 2026-05-11 | 2026-05-09 | 2 | 79% | 2026-05-10
Week-12 | 2026-05-18 | 2026-05-17 | 2 | 79% | 2026-05-18
Week-13 | 2026-05-24 | 2026-05-21 | 2 | 79% | 2026-05-24
Week-14 | 2026-06-01 | 2026-05-31 | 1 | 79% | 2026-05-31
Week-15 | 2026-06-08 | 2026-06-07 | 2 | 79% | 2026-06-08
Week-16 | 2026-06-15 | 2026-06-14 | 2 | 79% | 2026-06-14
Week-17 | 2026-06-22 | 2026-06-21 | 2 | 79% | 2026-06-21
Week-18 | 2026-06-29 | 2026-06-28 | 2 | 79% | 2026-06-28
Week-19 | 2026-07-06 | 2026-07-05 | 1 | 79% | 2026-07-06
Week-20 | 2026-07-13 | 2026-07-12 | 1 | 79% | 2026-07-13
Week-21 | 2026-07-20 | 2026-07-19 | 1 | 79% | 2026-07-19
Week-22 | 2026-07-27 | 2026-07-27 | 2 | 79% | 2026-07-27
Week-23 | 2026-08-03 | 2026-08-02 | 2 | 79% | 2026-08-03
Week-24 | 2026-08-10 | 2026-08-09 | 2 | 79% | 2026-08-09
Week-25 | 2026-08-17 | 2026-08-16 | 2 | 79% | 2026-08-16
Week-26 | 2026-08-24 | 2026-08-23 | 2 | 79% | 2026-08-23
Week-27 | 2026-08-31 | 2026-08-30 | 1 | 79% | 2026-08-31
Week-28 | 2026-09-07 | 2026-09-06 | 1 | 79% | 2026-09-07
Week-29 | 2026-09-14 | 2026-09-13 | 1 | 79% | 2026-09-14
Week-30 | 2026-09-21 | 2026-09-20 | 1 | 79% | 2026-09-21
Week-31
Week-32
Week-33
Week-34
Week-35
Week-36
Week-37
Week-38
Week-39
Week-40
Week-41
Week-42
Week-43
Week-44
Week-45
Week-46
Week-47
Week-48
Week-49
Week-50
Week-51
Week-52
Week-53
Week-54
Week-55
Week-56
Week-57
Week-58
Week-59
Week-60
Week-61
Week-62
Week-63
Week-64
Week-65
Week-66
Week-67
Week-68
Week-69
Week-70
Week-71
Week-72
Week-73
Week-74
Week-75

## Major Quantities
BOQ Number | Description of Item | Total Quantity | Unit of Measurement | Plan To Date | Actual To Date | Remaining Total | Variance | Variance % | Notices
2.1.1 | Excavation | 1503 | M3 | 1503 | 629.42 | 873.58 | 873.58 | 41.88% |  |  | 41.88%
2.1.3 | Backfilling | 20258.76 | M3 | 20258.76 | 14724.77 | 5533.99 | 5533.99 | 72.68% |  |  | 72.68%
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
Activity ID | Activity Name | Resource Name | Price / Unit | Budgeted Units | Actual Units | Budgeted Cost | Budgeted Cost | Actual | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-18 | 2024-05-19 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-25 | 2024-05-26 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-22 | 2024-06-23 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-06-29 | 2024-06-30 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-06 | 2024-07-07 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-13 | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-07-28 | 2024-07-29 | 2024-07-30 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-17 | 2024-08-18 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12 | 2024-10-13 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-19 | 2024-10-20 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-26 | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29 | 2024-12-30 | 2024-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 45998 | 45999 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18
Total |  |  |  | 102031 | 23531.31 | 45093675 | 45093675 | 23531.31 | 21.55 | 21.55 | 21.55 | 21.55 | 21.55 |  | 21.83 | 21.83 | 21.83 | 0.27 | 0.27 | 1.46 |  | 1.46 | 1.46 | 70.33 | 70.33 | 70.33 | 112.19 |  | 112.19 | 112.19 | 59.21 | 59.21 | 59.21 |  |  | 35.32 | 35.32 | 16.44 | 16.85 | 16.85 | 0.87 |  | 0.27 | 0.27 | 0 | 0 | 0 | 189.2 |  | 189.2 | 189.2 | 141.9 | 141.9 | 141.9 | 141.9 |  | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 |  | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 |  | 141.9 | 141.9 | 141.9 | 141.9 | 127.2 | 126.6 |  | 126.6 | 126.6 | 126.6 | 126.6 | [5 empty] | 168.8 | 168.8 | 168.8 | 168.8 |  | 168.8 | 168.8 | 168.8 | 168.8 | 168.8 | 168.8 |  | 168.8 | 168.8 | 168.8 | 176.59 | 184.37 | 184.37 |  | 184.37 | 184.37 | 184.37 | 184.37 | 184.48 | 184.59 |  | 184.59 | 184.59 | 184.59 | 188.22 | 191.86 | 191.87 |  | 192.51 | 193.15 | 189.52 | 173.9 | 161.91 | 162.5 |  | 164.88 | 167.11 | 167.57 | 167.58 | 166.99 | 168.41 |  | 169.07 | 168.89 | 170.07 | 170.1 | 168.12 | 166.1 |  | 173.18 | 181.19 | 182.12 | 182.19 | 182.26 | 715.97 |  | 1253.81 | 1257.95 | [5 empty] | 1259.46 | 1260.97 | 1261.4 | 1257.71 | 1256.27 | 1258.96 |  | 1258.8 | 1259.08 | 1257.81 | 1253.41 | 1250.72 | 1250.72 |  | 1256.66 | 1261.05 | 1261.24 | 1262.99 | 1262.99 | 1396.73 |  | 1526.57 | 1521.77 | 1520.73 | 1520.58 | 1520.58 | 1518.2 |  | 1516.6 | 1522.61 | 1531.64 | 1535.45 | 785.51 | 35.59 |  | 28.78 | 21.94 | 21.94 | 23.84 | 25.12 | 24.42 |  | 24.2 | 36.24 | 48.4 | 52.11 | 55.84 | 55.69 |  | 42.55 | 28.38 | 33.58 | 40.48 | 41.01 | 41.81 |  | 72.51 | 274.38 | 459.01 | 471.56 | 471.46 | 467.45 |  | 464.26 | 452.44 | 444.04 | 448.3 | 448.19 | 445.73 |  | 444.97 | 442.3 | 438.04 | 260.54 | 83.03 | 78.29 |  | 43.88 | 13.3 | 197.77 | 383.29 | 383.45 | 381.68 |  | 380 | 194.34 | 8.59 | 8.59 | 8.77 | 8.69 |  | 8.43 | 8.44 |  | 8.28 | 8.96 | 9.8 |  | 9.74 | 11.69 | 13.68 | 14.81 | 15.72 | 15.51 |  | 14.14 | 15.53 | 19.42 | 22.57 | 24.53 | 27.69 |  | 35.94 | 41.52 | 42.66 | 42.76 | 53.47 | 69.64 |  | 62.96 | 58.15 | 72.8 | 112.27 | 142.58 | 129.26 |  | 127.31 | 144.73 | 105.34 | 57.11 | 64.4 | 64.56 |  | 46.25 | 41.41 | 50.63 | 54.8 | 49.72 | 44.52 |  | 47.52 | 50.57 | 39.97 | 29.71 | 37.26 | 44.53 |  | 39.58 | 33.69 | 51.95 | 91.66 | 108.72 | 106.4 |  | 107.85 | 99.66 | 92.65 | 83.03 | 72.46 | 60.56 |  | 48.38 | 45.24 | 44.94 | 57.38 | 66.43 | 97.63 |  | 122.69 | 88.44 | 64.32 | 139.59 | 214.39 | 219.2 |  | 217.1 | 215.73 | 224.41 | 153.08 | 75.72 | 77.28 |  | 77.93 | 79.36 | 76.9 | 73.16 | 71.12 | 78.67 |  | 87.82 | 87.1 | 77.2 | 62.8 | 63.13 | 66.81 |  | 64.95 | 63.67 | 51.03 | 37.85 | 33.5 | 29.9 |  | 29.85 | 28.91 | 27.97 | 23.83 | 38.57 | 58.66 |  | 38.82 | 17.75 | 17.73 | 16.56 | 15.49 | 15.6 |  | 15.6 | 15.6 | 15.59 | 15.58 | 15.59 | 14.44 |  | 18.24 | 23.21 | 23.26 | 23.31 | 23.31 | 23.31 |  | 32.13 | 40.95 | 40.95 | 44.56 | 44.66 | 41.15 |  | 41.15 | 37.19 | 33.23 | 40.64 | 48.13 | 48.21 |  |  | 49.78 | 51.42 | 51.48 | 55.47 | 49.97 |  | 30.38 | 30.4 | 42.94 | 42.94 | 42.62 | 41.99 |  | 39.52 | 39.62 | 38.85 | 37.2 | 41.88 | 39.29 |  | 38 | 38 | 36.57 | 34.12 | 32.89 | 32.89 |  | 38.78 | 34.91 | 33.02 | 33.11 | 33.11 | 33.11 |  | 33.11 |  |  |  |  | 44.87 |  | 41.58 | 25.17 | 25.17 | 24.87 | 23.97 | 21.96 |  | 26.95 | 59.98 | 59.98 | 57.9 | 51.64 | 51.68 |  | 67.07 | 112.2 | 110.21 | 105.83 | 105.85 | 93.69 |  | 57.03 | 57.06 | 60.03 | 73 | 85.47 | 84.59 |  | 84.59 | 83.47 | 74.96 | 65.16 | 87.05 | 96.26 |  | 81.82 | 88.54 | 92.61 | 92.47 | 92.47 | 88.12 |  | 93.15 | 80.89 | 77.48 | 77.44 | 71.49 | 77.95 |  | 109.23 | 94.06 | 48.46 | 57.19 | 82.65 | 70.88 |  | 33.17 | 23.85 | 26.07 | 23.38 | 15.24 | 15.09 | [5 empty] | 15.39 | 15.14 |  | 14.41 | 15.11 | 18.47 | 23.22 | 23.21 | 23.18 |  | 31.08 | 54.77 | 54.77 | 54.77 | 58.18 | 75.04 |  | 95.06 | 128.25 | 226.95 | 228.05 | 188.29 | 69 |  | 67.01 | 57.64 | 47.52 | 46.01 | 42.06 | 43.71 |  | 43.57 | 43.5 | 43.11 | 43.31 | 43.29 | 41.84 |  | 32.36 | 16.67 | 15.57 | 18.25 | 27.31 | 29.33 |  | 29.03 | 31.79 | 29.01 | 73.54 | 71.55 | 35.98 |  | 36.5 | 38.47 | 41.74 | 49.19 | 69.2 | 126.69 |  | 100.17 | 39.12 | 41.31 | 52.36 | 55.87 | 32.83 |  | 32.65 | 32.1 | 32.1 | 33.15 | 36.26 | 36.38 |  | 36.5 | 33.19 | 23.46 | 24.23 | 23.62 | 20.59 |  | 20.57 | 31.85 | 67.01 | 82.05 | 118.49 | 121.05 |  | 117.22 | 148.48 | 243.82 | 243.97 | 242.68 | 242.22 |  | 230.75 | 238.39 | 352.51 | 355.95 | 362.35 | 359.99 |  | 359.75 | 365.12 | 378.86 |  | 321.98 | 172.61 |  | 172.81 | 173.28 | 176.82 | 182.75 | 182.4 | 190.28 |  | 207.41 | 208.55 | 188.07 | 150.81 | 207.66 | 171.87 |  | 72.23 | 98.64 | 176.75 | 173.92 | 164.68 | 135.94 |  | 135.06 | 135.74 | 134.42 | 170 | 300.86 | 333.41 |  | 335.99 | 379.73 | 335.5 | 202 | 200.23 | 241.61 |  | 366.26 | 364.93 | 373.75 | 440.86 | 526.67 | 526.62 |  | 527.57 | 500.4 | 404.75 | 388.18 | 388.38 | 351.31 |  | 231.37 | 217.45 | 244.64 | 247.28 | 254.64 | 235.11 |  | 181.35 | 181.02 | 166.1 | 123.29 | 123.29 | 121.71 |  | 108.76 | 84.11 | 83.53 | 82.26 | 82.26 | 82.26 |  | 82.26 | 96.75 | 140.23 | 140.23 | 140.23 | 140.23 |  | 140.23 | 140.23 | 140.23 | 140.23 | 140.23 | 105.17
2 Way PVC |  |  |  | 90 | 0 | 42300 | 42300 | 0 | [584 empty] | 1.23 | 3.68 |  |  | 0.73 | 2.94 | 2.94 | 2.94 | 2.94 |  | 2.51 | 1.23 | 1.23 | 1.23 | 0.92 | [21 empty] | 0.21 |  | 0.85 | 0.85 | 0.85 | 0.85 | 2.5 | 7.45 |  | 7.59 | 8.02 | 6.87 | 3.41 | 4.07 | 5.34 |  | 3.21 | 3.21 | 3.21 | 2.64 | 0.92 | 0.92 |  | 0.92 | 0.92 | 0.69
3-outlet Fire Hydrant (2 x 2.5 inch and 1 x 4 inch) |  |  |  | 60 | 1.8 | 1043400 | 1043400 | 1.8 | [30 empty] | 0.6 | 0.6 | 0.6 | [360 empty] | 0.07 | 0.13 | 0.13 | 0.13 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 |  |  |  |  | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.23 | 0.5 | 0.5 |  | 0.5 | 0.56 | 0.75 | 1.09 | 2.1 | 2.19 |  | 2.44 | 2.44 | 2.44 | 2.1 | 1.09 | 1.09 | [5 empty] | 1.09 | 1.03 |  | 0.84 | 0.74 | 0.38 | 0.13 | 0.2 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.36 | 0.26 |  | 0.26 | 0.42 | 0.9 | 0.9 | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  | 0.9 | 0.75 | 0.29 | 0.29 | 0.29 | 0.29 |  | 0.29 | 0.29 | 0.29 | 0.22 | [14 empty] | 0.05 | 0.2 |  | 0.25 | 0.4 | 0.43 | 0.51 | 0.44 | 0.23 |  | 0.23 | 0.23 | 0.18 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.02 | [83 empty] | 0.19 | 0.75 | 0.75 |  | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.56
300 mm diameter pipe |  |  |  | 925 | 0 | 342250 | 342250 | 0 | [202 empty] | 12.68 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 |  | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 |  | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 |  | 12.68 | [21 empty] | 0.57 | 1.14 | 1.14 | 1.14 | 1.14 |  | 0.57 | [16 empty] | 9.58 | 19.16 | 19.16 |  | 19.16 | 20.97 | 13.21 | 3.63 | 3.63 | 1.81 | [18 empty] | 6.5 | 13 | 13 |  | 13 | 6.5 | [10 empty] | 7.54 |  | 15.09 | 7.54 |  | 18.02 | 36.04 | 36.04 |  | 36.04 | 36.04 | 36.04 | 18.02 | [28 empty] | 10.13 | 20.25 |  | 10.13 | [20 empty] | 1.69 | 3.38 | 3.38 | 3.38 | 1.69
4 Way PVC |  |  |  | 102 | 0 | 95880 | 95880 | 0 | [632 empty] | 0.85 | 3.4 | 3.4 |  | 6.12 | 14.28 | 14.28 | 14.28 | 14.28 | 12.41 |  | 6.8 | 6.8 | 5.1
400 mm diameter pipe |  |  |  | 1231 | 0 | 689360 | 689360 | 0 | [202 empty] | 14.86 | 29.73 | 29.73 | 29.73 | 29.73 | 29.73 |  | 29.73 | 29.73 | 29.73 | 29.73 | 29.73 | 29.73 |  | 29.73 | 29.73 | 29.73 | 29.73 | 29.73 | 29.73 |  | 14.86 | [21 empty] | 0.67 | 1.34 | 1.34 | 1.34 | 1.34 |  | 0.67 | [16 empty] | 12.29 | 24.58 | 24.58 |  | 24.58 | 26.9 | 16.94 | 4.65 | 4.65 | 2.33 | [18 empty] | 11.8 | 23.6 | 23.6 |  | 23.6 | 11.8 | [10 empty] | 12.63 |  | 25.26 | 12.63 |  | 30.17 | 60.33 | 60.33 |  | 60.33 | 60.33 | 60.33 | 30.17 | [28 empty] | 7.65 | 15.3 |  | 7.65 | [20 empty] | 1.27 | 2.55 | 2.55 | 2.55 | 1.27
500 mm diameter pipe |  |  |  | 625 | 0 | 468750 | 468750 | 0 | [202 empty] | 2.98 | 5.96 | 5.96 | 5.96 | 5.96 | 5.96 |  | 5.96 | 5.96 | 5.96 | 5.96 | 5.96 | 5.96 |  | 5.96 | 5.96 | 5.96 | 5.96 | 5.96 | 5.96 |  | 2.98 | [21 empty] | 0.13 | 0.27 | 0.27 | 0.27 | 0.27 |  | 0.13 | [16 empty] | 15.53 | 31.05 | 31.05 |  | 31.05 | 34 | 21.41 | 5.88 | 5.88 | 2.94 | [18 empty] | 3.05 | 6.1 | 6.1 |  | 6.1 | 3.05 | [10 empty] | 9.04 |  | 18.09 | 9.04 |  | 21.6 | 43.2 | 43.2 |  | 43.2 | 43.2 | 43.2 | 21.6 | [28 empty] | 3.34 | 6.68 |  | 3.34 | [20 empty] | 0.56 | 1.11 | 1.11 | 1.11 | 0.56
Acess Entrace Ramp |  |  |  | 2 | 0 | 70500 | 70500 | 0 | [219 empty] | 0.2 | 0.4 | 0.4 |  | 0.4 | 0.4 | 0.2
Air V CH On pipes Dia. 160 mm |  |  |  | 3 | 0 | 28680 | 28680 | 0 | [452 empty] | 0.02 |  | 0.08 | 0.08 | 0.08 | 0.09 | 0.15 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.14 |  | 0.1 | 0.1 | 0.18 | 0.4 | 0.4 | 0.3
Air V CH On pipes Dia. 250 mm |  |  |  | 3 | 0 | 28680 | 28680 | 0 | [477 empty] | 0.01 | 0.03 | 0.03 | 0.05 |  | 0.1 | 0.1 | 0.1 | 0.09 | 0.05 | 0.1 |  | 0.25 | 0.23 | 0.15 | 0.16 | 0.2 | 0.18 | [5 empty] | 0.13 | 0.12 |  | 0.11 | 0.23 | 0.23 | 0.2 | 0.15
Air V CH On pipes Dia. 315 mm |  |  |  | 1 | 0 | 9560 | 9560 | 0 | [536 empty] | 0.01 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 | 0.03 |  | 0.03 | 0.06 | 0.13 | 0.13 | 0.1
Air valve chamber; on 160 mm dia pipeline Depth 1.5- 3 m |  |  |  | 7 | 0 | 66990 | 66990 | 0 | [539 empty] | 0.03 | 0.1 | 0.1 | 0.11 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 |  | 0.13 | 0.08 | 0.08 | 0.08 | 0.13 | 0.3 |  | 0.3 | 0.3 | 0.22 | [9 empty] | 0.01 |  | 0.05 | 0.05 | 0.05 | 0.06 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.09 | 0.16 | 0.16 | 0.17 | 0.2 |  | 0.2 | 0.17 | 0.07 |  | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.06 | 0.16 | 0.16 |  | 0.16 | 0.16 | 0.12
Chain link fence |  |  |  | 650 | 0 | 113750 | 113750 | 0 | [644 empty] | 4.88 | 19.5 | 19.5 | 19.5 | 19.5 |  | 20.43 | 23.21 | 23.21 | 23.21 | 23.21 | 23.21 |  | 23.21 | 31.34 | 55.71 | 55.71 | 55.71 | 55.71 |  | 55.71 | 55.71 | 41.79
Conc. lining, incl PC & Expansion Joints |  |  |  | 3000 | 0 | 4935000 | 4935000 | 0 | [618 empty] | 27.69 | 110.77 | 83.07 |  |  | 27.69 | 110.77 | 110.77 | 99.69 | 66.46 |  | 66.46 | 66.46 | 66.46 | 105.23 | 221.53 | 221.53 |  | 221.53 | 221.53 | 177.22 | 44.31 | 44.31 | 68.83 |  | 142.39 | 131.32 | 98.09 | 98.09 | 98.09 | 98.09 |  | 98.09 | 73.56
Double Catch basin |  |  |  | 20 | 0 | 483000 | 483000 | 0 | [11 empty] | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [48 empty] | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.03 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.05 | 0.05 |  | 0.05 | 0.05 |  | 0.08 | 0.1 | 0.1 |  | 0.1 | 0.06 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.08 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.16 |  | 0.19 | 0.19 | 0.19 | 0.31 | 0.44 | 0.44 |  | 0.44 | 0.23 | 0.02 | 0.02 | 0.02 | 0.04 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.04 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.01 |  |  |  | 0.27 | 0.54 |  | 0.54 | 0.67 | 0.8 | 1.41 | 2.01 | 1 |  |  | 0.1 | 0.2 | 0.2 | 0.2 | 0.1 | [40 empty] | 0.02 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.06 | 0.07 |  | 0.07 | 0.07 | 0.12 | 0.17 | 0.17 | 0.17 |  | 0.08 |  |  |  | 0.01 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01 | [251 empty] | 0.06 |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.25 | 0.19
Double swing main entrance gate |  |  |  | 2 | 0 | 117500 | 117500 | 0 | [666 empty] | 0.17 | 0.67 | 0.67 | 0.5
Drawpit incl. cover |  |  |  | 23 | 0 | 135700 | 135700 | 0 | [581 empty] | 0.05 | 0.2 | 0.2 | 0.24 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.39 | 0.45 | 0.45 | 0.45 | 0.42 | 0.27 |  | 0.12 | 0.2 | 0.45 |  | 0.42 | 0.3 |  | 0.2 | 0.2 | 0.17 | 0.07 | 0.07 | 0.05 |  |  | 0.28 | 0.83 |  |  | 0.46 |  | 1.93 | 2.13 | 1.65 | 1.1 | 1.1 | 0.92 |  | 0.45 | 0.7 | 0.61 | 0.33 | 0.33 | 0.33 |  | 0.32 | 0.3 | 0.3 | 0.3 | 0.25 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.06
Earthing |  |  |  | 13 | 0 | 152750 | 152750 | 0 | [654 empty] | 0.33 | 0.98 |  |  | 0.76 | 3.03 | 3.03 | 2.49 | 0.87 |  | 0.87 | 0.65
Excavation |  |  |  | 37125 | 22506.58 | 2227500 | 2227500 | 22506.58 | [39 empty] | 189.2 |  | 189.2 | 189.2 | 141.9 | 141.9 | 141.9 | 141.9 |  | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 |  | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 | 141.9 |  | 141.9 | 141.9 | 141.9 | 141.9 | 120.97 | 120.97 |  | 120.97 | 120.97 | 120.97 | 120.97 | [5 empty] | 161.29 | 161.29 | 161.29 | 161.29 |  | 161.29 | 161.29 | 161.29 | 161.29 | 161.29 | 161.29 |  | 161.29 | 161.29 | 161.29 | 168.11 | 174.92 | 174.92 |  | 174.92 | 174.92 | 174.92 | 174.92 | 174.92 | 174.92 |  | 174.92 | 174.92 | 174.92 | 174.92 | 174.92 | 174.92 |  | 174.92 | 174.92 | 174.92 | 162.89 | 150.86 | 150.86 |  | 150.86 | 150.86 | 150.86 | 150.86 | 150.86 | 150.86 |  | 150.86 | 150.86 | 150.86 | 150.86 | 150.86 | 150.86 |  | 150.86 | 150.86 | 150.86 | 150.86 | 150.86 | 691.69 |  | 1232.52 | 1232.52 | [5 empty] | 1232.52 | 1232.52 | 1232.52 | 1232.52 | 1232.52 | 1232.52 |  | 1232.52 | 1232.52 | 1232.52 | 1232.52 | 1232.52 | 1232.52 |  | 1232.52 | 1232.52 | 1232.52 | 1232.52 | 1232.52 | 616.26
Filling |  |  |  | 16500 | 0 | 825000 | 825000 | 0 | [165 empty] | 750 |  | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 |  | 1500 | 1500 | 1500 | 1500 | 750
Filling with imported Material |  |  |  | 1856 | 0 | 129920 | 129920 | 0 | [225 empty] | 185.6 | 371.2 | 371.2 | 371.2 |  | 371.2 | 185.6
Flow meter chamber on 630 mm dia pipeline Depth 0- 1.5 m |  |  |  | 1 | 0 | 9570 | 9570 | 0 | [27 empty] | 0.01 | 0.01 | 0.01 | [586 empty] | 0.01 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 | 0.02 |  | 0.02 | 0.04 | 0.12 | 0.12 | 0.12 | 0.09 | [27 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01
LED Lumin 110 W |  |  |  | 193 | 0 | 675500 | 675500 | 0 | [18 empty] | 0.97 |  | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | [492 empty] | 0.14 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.41 | [13 empty] | 1.27 | 5.06 |  | 6.07 | 9.08 | 9.08 | 9.08 | 8.08 | 5.9 |  | 8.41 | 7.15 | 2.51 | [19 empty] | 1.82 | 7.27 | 7.27 | 7.27 | 7.27 |  | 7.27 | 7.27 | 5.45 | [9 empty] | 0.56 |  | 2.23 | 2.23 | 1.68 | [12 empty] | 0.48 | 1.93 | 1.93 | 1.93 | 1.93 |  | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.45
Outfall 1000 |  |  |  | 1 | 0 | 18800 | 18800 | 0 | [185 empty] | 0.03 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.18 | 0.3 | 0.16 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.01
Outfall 1400 |  |  |  | 1 | 0 | 23500 | 23500 | 0 | [179 empty] | 0.03 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.18 | 0.3 |  | 0.16 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01
Pipe encasement dia 200mm |  |  |  | 215 | 0 | 202100 | 202100 | 0 | [316 empty] | 1.89 | 3.77 | 3.77 | 3.77 |  | 3.77 | 3.77 | 8.17 | 12.57 | 12.57 | 7.79 |  | 3.02 | 3.02 | 3.02 | 3.02 | 5 | 6.98 |  | 6.98 | 6.98 | 6.98 | 6.98 | 9.31 | 11.63 |  | 11.63 | 11.63 | 11.63 | 11.63 | 8.14 | 4.65 |  | 4.65 | 4.65 | 4.65 | 4.65 | 2.33
Pipe encasement dia 250mm |  |  |  | 215 | 0 | 202100 | 202100 | 0 | [288 empty] | 0.64 | 1.29 | 1.29 | 1.29 |  | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | 2.02 |  | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 |  | 1.86 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 |  | 0.97 | 0.97 | 0.48 | [6 empty] | 3.61 | 7.21 | 7.21 | 7.21 |  | 7.21 | 7.21 | 9.62 | 12.02 | 12.02 | 12.02 |  | 12.02 | 12.02 | 8.42 | 4.81 | 4.81 | 4.81 |  | 4.81 | 4.81 | 2.4 | [51 empty] | 0.97 |  | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 |  | 6.03 | 6.03 | 4.42 | 1.21 | 1.21 | 1.21 |  | 1.21 | 1.21
Pipe encasement dia 315mm |  |  |  | 215 | 0 | 202100 | 202100 | 0 | [324 empty] | 1.08 | 2.17 | 2.17 |  | 2.17 | 2.17 | 2.17 | 4.7 | 7.22 | 7.22 |  | 4.48 | 1.73 | 1.73 | 1.73 | 1.73 | 0.87 | [44 empty] | 3.22 | 6.44 | 6.44 | 6.44 | 6.44 |  |  | 6.44 | 6.44 | 6.44 | 10.37 | 14.31 |  | 10.73 | 10.73 | 10.73 | 10.73 | 10.73 | 10.73 |  | 3.68 | 3.68 | 3.68 | 3.68 | 3.68 | 3.68 |  | 3.68 | 3.68 | 3.68 | 1.23
Pot Air V on pipes with dia(160) mm. |  |  |  | 4 | 0.11 | 11280 | 11280 | 0.11 | [22 empty] | 0.02 | 0.02 | 0.02 |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | [336 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 |  |  |  |  | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 |  | 0.07 | 0.07 | 0.07 | 0.09 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.13 |  | 0.09 | 0.09 | 0.16 | 0.37 | 0.37 | 0.28 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 |  | 0.01 | [156 empty] | 0.01 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04
Pot Air V on pipes with dia(250) mm. |  |  |  | 2 | 0.05 | 5640 | 5640 | 0.05 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.01 | 0.02 | 0.02 | 0.03 |  | 0.05 | 0.05 | 0.05 | 0.04 | 0.03 | 0.05 |  | 0.12 | 0.1 | 0.07 | 0.08 | 0.09 | 0.09 | [5 empty] | 0.06 | 0.06 |  | 0.05 | 0.1 | 0.1 | 0.09 | 0.07 | [152 empty] | 0.01 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02
Pot Air V on pipes with dia(315) mm. |  |  |  | 1 | 0.03 | 2820 | 2820 | 0.03 | [22 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | [32 empty] | 0.01 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.04 |  | 0.04 | 0.06 | 0.09 | 0.09 | 0.07 | [103 empty] | 0 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Pot Butterfly Valves Dia. 315 mm |  |  |  | 1 | 0.03 | 13630 | 13630 | 0.03 | [22 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0.02 | 0.05 | 0.01 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 |  | 0.04 | 0.06 | 0.14 | 0.1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | [156 empty] | 0 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Pot Gate Valves Dia. 160 mm |  |  |  | 12 | 0.32 | 36720 | 36720 | 0.32 | [22 empty] | 0.05 | 0.05 | 0.05 |  |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | [336 empty] | 0.01 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 |  |  |  |  | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.26 | 0.96 | 0.96 |  | 0.96 | 0.79 | 0.26 | 0.26 | 0.26 | 0.2 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.16 |  | 0.56 | 0.46 | 0.16 | 0.12 | 0.02 | 0.02 |  | 0.06 | 0.16 | 0.16 | 0.16 | 0.13 | 0.06 |  | 0.06 | 0.06 | 0.05 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 |  | 0.02 | [45 empty] | 0.09 | 0.36 |  | 0.36 | 0.29 | 0.09 | 0.09 | 0.07 | [103 empty] | 0.04 | 0.15 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.11
Pot Gate Valves Dia. 200 mm |  |  |  | 2 | 0.05 | 8460 | 8460 | 0.05 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0.07 | 0.27 |  | 0.27 | 0.27 | 0.22 | 0.07 | 0.07 | 0.07 |  | 0.05 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | [156 empty] | 0.01 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02
Pot Gate Valves Dia. 225 mm |  |  |  | 3 | 0.08 | 18330 | 18330 | 0.08 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [336 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.14 | 0.54 | 0.44 | 0.14 | 0.11 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 |  | 0 | [21 empty] | 0.03 | 0.13 | 0.13 | 0.13 | 0.11 |  | 0.03 | 0.03 | 0.03 | 0.03 | [125 empty] | 0.01 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03
Pot Gate Valves Dia. 250 mm |  |  |  | 3 | 0.08 | 21150 | 21150 | 0.08 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [336 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.07 | 0.27 | 0.22 |  | 0.07 | 0.06 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.07 | 0.27 | 0.27 | 0.27 |  | 0.22 | 0.07 | 0.07 | 0.07 | 0.06 | 0.01 | [5 empty] | 0.01 | 0.01 |  | 0 | [156 empty] | 0.01 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03
Pot Gate Valves Dia. 280 mm |  |  |  | 1 | 0.03 | 8225 | 8225 | 0.03 | [22 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.04 | 0.14 | 0.14 | 0.14 | 0.11 | 0.04 | [5 empty] | 0.04 | 0.04 |  | 0.03 | [156 empty] | 0 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Pot HDPE 160mm 0.0 to 1.5m |  |  |  | 300 | 9 | 96000 | 96000 | 9 | [18 empty] | 1.13 |  | 1.13 | 1.13 | 1.13 | 1.13 | 1.13 |  |  | 1.13 | 1.13 | [341 empty] | 0.33 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 |  |  |  |  | 0.67 |  | 0.67 | 0.67 | 0.67 | 1.76 | 5.04 | 5.04 |  | 4.68 | 3.59 | 3.59 | 5.04 | 9.42 | 9.42 |  | 9.42 | 9.42 | 7.96 | 3.59 | 3.59 | 3.51 |  | 3.29 | 3.29 | 3.29 | 7.55 | 15.4 | 0.67 |  | 0.67 | 2.08 | 6.34 | 12.01 | 29.03 | 23.36 |  | 6.34 | 7.05 | 9.17 | 7.05 | 0.67 | 0.67 |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.5 | [172 empty] | 0.94 | 3.75 | 3.75 |  | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 2.81
Pot HDPE 160mm 1.5 to 3.0m |  |  |  | 2300 | 69 | 1081000 | 1081000 | 69 | [18 empty] | 8.63 |  | 8.63 | 8.63 | 8.63 | 8.63 | 8.63 |  |  | 8.63 | 8.63 | [341 empty] | 2.56 | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 |  | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 |  | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 |  |  | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 |  | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 |  | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 |  | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 |  | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 |  | 3.83 |  |  |  |  | 5.11 |  | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 |  | 16.49 | 50.61 | 50.61 | 46.82 | 35.45 | 35.45 |  | 50.62 | 96.12 | 96.12 | 96.12 | 96.12 | 84.03 |  | 47.76 | 47.76 | 47 | 44.73 | 49.34 | 63.19 |  | 63.19 | 56.36 | 31.27 | 17.43 | 16.19 | 12.5 |  | 12.5 | 12.5 | 12.5 | 10.65 | 5.11 | 5.11 |  | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 |  | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 | 3.83 | [17 empty] | 1.54 | 6.16 | 6.16 | 6.16 |  | 5.65 | 4.11 | 4.11 | 4.11 | 6.51 | 13.69 |  | 13.69 | 13.69 | 13.69 | 13.69 | 11.3 | 4.11 |  | 4.11 | 4.11 | 4.11 | 4.11 | 4.11 | 4.11 |  | 4.11 | 4.11 | 3.08 | [7 empty] | 2.75 | 11.02 | 11.02 |  | 13.77 | 16.53 | 13.77 | 55.09 | 43.15 | 7.35 |  | 7.35 | 7.58 | 8.26 | 8.26 | 8.26 | 6.2 | [102 empty] | 7.19 | 28.75 | 28.75 |  | 28.75 | 28.75 | 28.75 | 28.75 | 28.75 | 21.56
Pot HDPE 200mm 1.5 to 3.0m |  |  |  | 750 | 22.5 | 412500 | 412500 | 22.5 | [18 empty] | 2.81 |  | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 |  |  | 2.81 | 2.81 | [341 empty] | 0.83 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  |  | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |  | 1.25 |  |  |  |  | 1.67 |  | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 |  | 1.67 | 1.67 | 5.33 | 16.31 | 16.31 | 16.31 |  | 16.31 | 17.26 | 19.56 | 17.94 | 24.04 | 42.52 |  | 43.06 | 43.78 | 45.94 | 45.22 | 36.96 | 18.75 |  | 19.02 | 17.73 | 13.87 | 13.87 | 13.87 | 13.87 |  | 13.87 | 10.82 | 1.67 | 1.67 | 1.67 | 1.25 | [172 empty] | 2.34 | 9.38 | 9.38 |  | 9.38 | 9.38 | 9.38 | 9.38 | 9.38 | 7.03
Pot HDPE 225mm 1.5 to 3.0m |  |  |  | 550 | 16.5 | 324501.3 | 324501.3 | 16.5 | [18 empty] | 2.06 |  | 2.06 | 2.06 | 2.06 | 2.06 | 2.06 |  |  | 2.06 | 2.06 | [341 empty] | 0.61 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 |  | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 |  | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 |  | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 |  | 0.92 |  |  |  |  | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 |  | 1.22 | 1.22 | 1.22 | 1.22 | 1.22 | 4.22 |  | 13.2 | 13.2 | 13.2 | 14.19 | 17.19 | 33.15 |  | 81.05 | 65.08 | 17.19 | 19.18 | 25.17 | 18.88 | [22 empty] | 0.46 | 1.84 | 1.84 | 1.84 | 1.79 | 1.64 |  | 1.64 | 2.46 | 4.92 | 4.92 | 4.92 | 4.92 |  | 4.1 | 1.64 | 1.64 | 1.6 | 1.48 | 1.48 |  | 1.48 | 1.48 | 1.11 | [126 empty] | 1.72 | 6.88 | 6.88 |  | 6.88 | 6.88 | 6.88 | 6.88 | 6.88 | 5.16
Pot HDPE 250mm 1.5 to 3.0m |  |  |  | 850 | 25.5 | 552498.7 | 552498.7 | 25.5 | [18 empty] | 3.19 |  | 3.19 | 3.19 | 3.19 | 3.19 | 3.19 |  |  | 3.19 | 3.19 | [341 empty] | 0.94 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 |  | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 |  | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 |  | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 | 1.42 |  | 1.42 |  |  |  |  | 1.89 |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 |  | 1.89 | 5.23 | 15.25 | 15.25 | 15.25 | 15.25 |  | 15.62 | 16.74 | 16.74 | 22.3 | 39.01 | 39.01 |  | 39.01 | 39.01 | 39.01 | 36.46 | 28.81 | 23.25 |  | 6.54 | 10.27 | 21.46 | 27.66 | 46.27 | 39.6 |  | 16.23 | 6.98 | 9.31 | 6.98 | [167 empty] | 2.66 | 10.63 | 10.63 |  | 10.63 | 10.63 | 10.63 | 10.63 | 10.63 | 7.97
Pot HDPE 280mm 1.5 to 3.0m |  |  |  | 110 | 3.3 | 79200 | 79200 | 3.3 | [18 empty] | 0.41 |  | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 |  |  | 0.41 | 0.41 | [341 empty] | 0.12 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 |  | 0.18 |  |  |  |  | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 1.63 | 5.77 | 5.31 | 3.93 | 7.61 | 18.67 |  | 14.98 | 3.93 | 4.39 | 5.77 | 4.39 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.18 | [172 empty] | 0.34 | 1.38 | 1.38 |  | 1.38 | 1.38 | 1.38 | 1.38 | 1.38 | 1.03
Pot HDPE 315mm 0.0 to 1.5m |  |  |  | 175 | 5.25 | 112000 | 112000 | 5.25 | [18 empty] | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  |  | 0.66 | 0.66 | [341 empty] | 0.19 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 |  | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 |  | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 |  | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 |  | 0.29 |  |  |  |  | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.29 | [26 empty] | 1.1 | 4.4 |  | 4.4 | 4.4 | 4.76 | 5.86 | 9.28 | 19.54 |  | 19.54 | 16.12 | 5.86 | 4.4 | [5 empty] | 1.47 | 5.86 | 5.86 | 4.4 | [123 empty] | 0.55 | 2.19 | 2.19 |  | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 1.64
Pot Wash out valve with dia (160) mm |  |  |  | 2 | 0.05 | 6200 | 6200 | 0.05 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0.04 |  | 0.1 | 0 | 0 | 0 | 0 | 0.02 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.05 |  | 0.14 | 0.14 | 0.14 | 0.1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | [156 empty] | 0.01 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02
Pot Wash out valve with dia (200) mm |  |  |  | 1 | 0.03 | 4580 | 4580 | 0.03 | [22 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [336 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0.01 | 0.04 |  | 0.04 | 0.07 | 0.07 | 0.07 | 0.06 | 0.04 |  | 0.04 | 0.07 | 0.07 | 0.07 | 0.05 | 0 | [5 empty] | 0 | 0 |  | 0 | [156 empty] | 0 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Pot Wash out valve with dia (250) mm |  |  |  | 3 | 0.08 | 21510 | 21510 | 0.08 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [336 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.03 | 0.03 | 0.04 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.09 | 0.17 | 0.13 | 0.06 |  | 0.14 | 0.14 | 0.14 | 0.12 | 0.07 | 0.12 | [5 empty] | 0.27 | 0.21 |  | 0 | [156 empty] | 0.01 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03
Riprap |  |  |  | 5000 | 0 | 1300000 | 1300000 | 0 | [203 empty] | 178.57 | 357.14 | 357.14 | 357.14 | 357.14 |  | 357.14 | 357.14 | 357.14 | 357.14 | 357.14 | 357.14 |  | 357.14 | 357.14 | 357.14 | 178.57
Sewer Dia 200 mm; Depth : 1.5m - 2.5m |  |  |  | 600 | 18 | 282000 | 282000 | 18 | [22 empty] | 2.25 | 2.25 | 2.25 |  |  | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | [233 empty] | 0.67 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.93 | 2.54 | 2.54 | 2.54 |  | 2.54 | 2.54 | 2.23 | 1.93 | 1.93 | 1.93 |  | 1.93 | 1.93 | 2.83 | 3.74 | 3.74 | 3.74 |  | 3.74 | 3.74 | 2.53 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.63 | 1.93 | 1.93 | 1.93 | 1.93 |  | 1.93 | 2.23 | 2.54 | 2.54 | 2.54 | 2.54 |  | 2.54 | 1.93 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 4.73 | 8.13 | 8.13 | 8.13 | 8.13 | 8.13 |  | 8.13 | 8.13 | 8.13 | 7.12 | 6.1 | 6.1 |  | 6.1 | 6.1 | 6.1 | 13.51 | 20.91 | 20.91 |  |  | 20.91 | 20.91 | 20.91 | 20.91 | 10.46 | [12 empty] | 4.58 | 4.58 |  | 4.58 | 4.58 | 4.58 | 4.58 | 4.58 | 4.58 |  | 7.84 | 7.84 | 7.84 | 7.84 | 7.84 | 7.84 |  | 7.84 |  |  |  |  | 10.46 |  | 7.84 | [217 empty] | 1.88 | 7.5 | 7.5 | 7.5 | 7.5 |  | 7.5 | 7.5 | 7.5 | 5.63
Sewer Dia 250 mm; Depth : 1.5m - 2.5m |  |  |  | 715 | 21.45 | 357500 | 357500 | 21.45 | [22 empty] | 2.68 | 2.68 | 2.68 |  |  | 2.68 | 2.68 | 2.68 | 2.68 | 2.68 | [233 empty] | 0.79 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 2.69 | 3.79 | 3.79 |  | 3.79 | 3.79 | 3.79 | 3.36 | 2.93 | 2.93 |  | 2.93 | 2.93 | 4.17 | 5.41 | 5.41 | 5.41 |  | 5.41 | 5.41 | 5.41 | 3.5 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 2.07 | 2.54 |  | 2.54 | 2.54 | 2.54 | 2.54 | 2.54 | 2.07 |  | 1.59 | 1.59 | 1.59 | 2.69 | 3.79 | 3.79 |  | 3.79 | 3.79 | 3.79 | 2.69 | 1.59 | 1.59 |  | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 | 1.59 |  | 0.79 | [9 empty] | 4.59 | 9.17 | 9.17 |  | 9.17 | 9.17 | 9.17 | 9.17 | 9.17 | 9.17 |  |  | 8.02 | 6.87 | 6.87 | 6.87 | 6.87 |  | 5.15 | 5.15 | 17.69 | 17.69 | 17.69 | 17.69 |  | 17.69 | 17.69 | 17.69 | 17.69 | 17.69 | 10.02 |  | 6.18 | 6.18 | 6.18 | 6.18 | 6.18 | 6.18 |  | 8.84 | 8.84 | 8.84 | 8.84 | 8.84 | 8.84 |  | 8.84 |  |  |  |  | 11.79 |  | 8.84 | [217 empty] | 2.23 | 8.94 | 8.94 | 8.94 | 8.94 |  | 8.94 | 8.94 | 8.94 | 6.7
Sewer Dia 315 mm; Depth : 2.5m - 3.5m |  |  |  | 950 | 28.5 | 631750 | 631750 | 28.5 | [22 empty] | 3.56 | 3.56 | 3.56 |  |  | 3.56 | 3.56 | 3.56 | 3.56 | 3.56 | [224 empty] | 1.9 |  | 3.81 | 3.81 | 3.81 | 3.81 | 3.81 | 3.81 |  | 4.86 | 5.92 | 5.92 | 5.92 | 5.18 | 4.44 |  | 4.44 | 4.44 | 4.44 | 4.44 | 4.44 | 4.44 |  | 4.44 | 9.25 | 14.07 | 14.07 | 14.07 | 14.07 |  | 14.07 | 14.07 | 8.09 | 2.11 | 2.11 | 2.11 |  | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 |  | 2.11 | 2.11 | 4.2 | 6.3 | 6.3 | 6.3 |  | 6.3 | 6.3 | 7.46 | 7.75 | 6.88 | 6.88 |  | 6.88 | 6.88 | 6.88 | 11.44 | 16 | 16.74 |  | 17.48 | 17.48 | 17.48 | 12.59 | 7.34 | 6.96 |  | 6.96 | 6.96 | 6.96 | 6.96 | 6.63 | 6.3 |  | 6.3 | 6.3 | 7.52 | 8.74 | 6.65 | 4.55 |  | 4.55 | 4.55 | 5.42 | 6.3 | 6.3 | 6.3 |  | 6.3 | 6.3 | 6.3 | 4.2 | 2.63 | 3.16 |  | 3.16 | 3.16 | 3.16 | 3.16 | 3.53 | 3.91 |  | 3.91 | 3.91 | 3.91 | 3.91 | 3.91 | 3.01 |  | 1.06 | [21 empty] | 2.72 | 5.45 | 5.45 | 5.45 | 5.45 |  | 4.09 | 4.09 | 4.09 | 4.09 | 3.81 | 3.27 |  | 3.27 | 3.27 | 3.27 | 3.27 | 3.27 | 8.35 |  | 10.9 | 10.9 | 10.9 | 10.9 | 10.9 | 10.9 |  | 10.9 | 5.81 | 3.27 | 3.27 | 3.27 | 3.27 |  | 3.27 |  |  |  |  | 5.08 |  | 7.27 | 7.27 | 7.27 | 7.27 | 7.27 | 5.45 | [212 empty] | 2.97 | 11.88 | 11.88 | 11.88 | 11.88 |  | 11.88 | 11.88 | 11.88 | 8.91
Sewer Dia 315 mm; Depth : 3.5m - 4.5m |  |  |  | 1150 | 34.5 | 920000 | 920000 | 34.5 | [22 empty] | 4.31 | 4.31 | 4.31 |  |  | 4.31 | 4.31 | 4.31 | 4.31 | 4.31 | [233 empty] | 1.28 | 2.56 | 2.56 | 2.56 | 8.06 | 13.56 |  | 13.56 | 13.56 | 13.56 | 13.56 | 13.56 | 13.56 |  | 13.56 | 13.56 | 13.56 | 13.56 | 13.56 | 13.56 |  | 12.87 | 12.19 | 12.19 | 12.19 | 12.19 | 12.19 |  | 12.19 | 12.19 | 24.49 | 36.8 | 36.8 | 36.8 |  | 36.8 | 36.8 | 36.8 | 36.8 | 36.8 | 19.68 |  | 2.56 | 2.56 | 6.84 | 11.12 | 11.12 | 11.12 |  | 11.12 | 11.12 | 11.12 | 11.12 | 11.12 | 13.84 |  | 16.56 | 16.56 | 16.56 | 16.56 | 16.56 | 16.56 |  | 16.56 | 16.56 | 16.56 | 16.56 | 9.56 | 2.56 |  | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 |  | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 |  | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 |  | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 |  | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 |  | 1.28 | [280 empty] | 3.59 | 14.38 | 14.38 | 14.38 | 14.38 |  | 14.38 | 14.38 | 14.38 | 10.78
Sewer Dia 315 mm; Depth : 4.5m - 5.5m |  |  |  | 15 | 0.45 | 13725 | 13725 | 0.45 | [22 empty] | 0.06 | 0.06 | 0.06 |  |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | [233 empty] | 0.02 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.16 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.24 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.37 | 0.54 | 0.54 | 0.54 |  | 0.54 | 0.54 | 0.54 | 0.54 | 0.36 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.25 |  | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 |  | 0.18 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.02 | [280 empty] | 0.05 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | 0.14
Sewer Dia 400 mm; Depth : 3.5m - 4.5m |  |  |  | 420 | 12.6 | 390600 | 390600 | 12.6 | [22 empty] | 1.58 | 1.58 | 1.58 |  |  | 1.58 | 1.58 | 1.58 | 1.58 | 1.58 | [233 empty] | 0.47 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 3.28 | 5.62 | 5.62 | 5.62 |  | 5.62 | 5.62 | 5.62 | 5.62 | 5.62 | 5.62 |  | 5.62 | 5.62 | 5.62 | 5.62 | 5.62 | 5.62 |  | 5.62 | 5.62 | 11.32 | 17.01 | 17.01 | 17.01 |  | 17.01 | 17.01 | 17.01 | 10.73 | 4.45 | 4.45 |  | 4.45 | 4.45 | 4.45 | 4.45 | 4.45 | 5.82 |  | 7.19 | 7.19 | 7.19 | 7.19 | 7.19 | 7.19 |  | 7.19 | 7.19 | 4.06 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  | 0.47 | [280 empty] | 1.31 | 5.25 | 5.25 | 5.25 | 5.25 |  | 5.25 | 5.25 | 5.25 | 3.94
Sewer Dia 400 mm; Depth : 4.5m - 5.5m |  |  |  | 375 | 11.25 | 397500 | 397500 | 11.25 | [22 empty] | 1.41 | 1.41 | 1.41 |  |  | 1.41 | 1.41 | 1.41 | 1.41 | 1.41 | [233 empty] | 0.42 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 2.93 |  | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 |  | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 | 4.72 |  | 4.01 | 3.59 | 3.59 | 3.59 | 3.59 | 3.59 |  | 8.97 | 14.36 | 14.36 | 14.36 | 14.36 | 14.36 |  | 14.36 | 7.18 | [21 empty] | 0.79 | 2.36 | 2.36 | 2.36 |  | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 |  | 2.36 | 3.58 | 4.19 | 4.19 | 4.19 | 4.19 |  | 4.19 |  |  |  |  | 5.58 |  | 5.58 | 5.58 | 5.58 | 4.19 | [214 empty] | 1.17 | 4.69 | 4.69 | 4.69 | 4.69 |  | 4.69 | 4.69 | 4.69 | 3.52
Sewer Manhole Dia 1200 mm, Depth: 1.5 - 2.5m |  |  |  | 22 | 0 | 325600 | 325600 | 0 | [27 empty] | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | [243 empty] | 0.11 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 |  | 0.35 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.32 | 0.16 | 0.16 |  | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 |  | 0.15 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.09 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.12 | 0.19 |  |  | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.16 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.29 | 0.34 | 0.34 | 0.3 | 0.3 |  | 0.3 | 0.3 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 |  |  |  |  | 0.1 |  | 0.08 | [217 empty] | 0.07 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.21
Sewer Manhole Dia 1200 mm, Depth: 2.5 - 3.5m |  |  |  | 27 | 0 | 617760 | 617760 | 0 | [27 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | [253 empty] | 0.04 | 0.09 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 |  | 0.12 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 |  | 0.16 | 0.16 | 0.22 | 0.3 | 0.32 | 0.32 |  | 0.32 | 0.32 | 0.32 | 0.25 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.23 | 0.26 | 0.26 |  | 0.26 | 0.26 | 0.22 | 0.18 | 0.21 | 0.23 |  | 0.2 | 0.17 | 0.17 | 0.17 | 0.14 | 0.1 |  | 0.09 | 0.09 | 0.09 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.07 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.26 | 0.35 | 0.35 | 0.35 |  | 0.35 |  |  |  |  | 0.47 |  | 0.58 | 0.93 | 0.93 | 0.93 | 0.93 | 0.74 |  | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 |  | 0.18 | 0.23 | 0.23 | 0.23 | 0.23 | 0.17 | [198 empty] | 0.08 | 0.34 | 0.34 | 0.34 | 0.34 |  | 0.34 | 0.34 | 0.34 | 0.25
Sewer Manhole Dia 1200 mm, Depth: 3.5 - 4.5m |  |  |  | 7 | 0 | 226800 | 226800 | 0 | [27 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | [264 empty] | 0.06 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.2 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.18 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.04 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [242 empty] | 0.02 | 0.09 | 0.09 | 0.09 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.07
Sewer Manhole Dia 1200 mm, Depth: 4.5 - 5.5m |  |  |  | 6 | 0 | 237600 | 237600 | 0 | [27 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | [264 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.05 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.1 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.16 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.22 | 0.22 | 0.16 | 0.13 |  | 0.17 | 0.17 | 0.13 | 0.09 | 0.09 | 0.07 |  | 0.05 | 0.05 | 0.05 | 0.06 | 0.07 | 0.07 |  | 0.07 | 0.05 | 0.02 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [242 empty] | 0.02 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.06
Sewer Manhole Dia 1200 mm, Depth: 5.5 - 6.5m |  |  |  | 2 | 0 | 93400 | 93400 | 0 | [27 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | [264 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.02 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.07 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.06 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.02 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [242 empty] | 0.01 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.02
Sewer Manhole Dia 1200 mm; Depth < 1.5m |  |  |  | 8 | 0 | 98240 | 98240 | 0 | [27 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | [233 empty] | 0.03 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.1 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.09 | 0.03 | 0.03 |  | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.03 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.06 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.12 | 0.14 |  |  | 0.14 | 0.14 | 0.14 | 0.19 | 0.25 |  | 0.19 | 0.19 | 0.19 | 0.19 | 0.15 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | [233 empty] | 0.03 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.08
Single Catch basin |  |  |  | 217 | 0 | 1944320 | 1944320 | 0 | [11 empty] | 1.09 |  | 1.09 | 1.09 | 1.09 | 1.09 | 1.09 | [48 empty] | 0.17 | 0.17 |  | 0.17 | 0.17 | 0.17 | 0.17 | [5 empty] | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.61 | 0.99 | 0.99 | 0.99 | 0.99 |  | 0.99 | 0.99 | [5 empty] | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 | 0.99 |  | 0.99 | 0.89 | 0.79 | 0.79 | 0.79 | 0.79 |  | 0.79 | 0.79 | 0.79 | 0.79 | 0.79 | 0.79 |  | 0.79 | 0.79 | 0.79 | 0.79 | 0.79 | 0.79 |  | 0.79 | 0.79 | 1.12 | 1.45 | 1.45 | 1.45 |  | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 |  | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 |  | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 |  | 0.84 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.42 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 |  | 0.42 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.54 | 0.86 |  | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.99 |  | 1.11 | 1.11 | 1.11 | 1.11 | 1.78 | 2.44 |  | 2.44 | 2.44 | 2.44 | 1.33 | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.45 | 0.67 | 0.67 | 0.67 |  | 0.67 | 0.45 | 0.23 | 0.36 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.63 | 0.76 | 0.76 |  | 1.17 | 1.57 | 2.29 | 2.34 | 1.67 | 1.67 |  | 1.55 | 1.52 | 1.6 | 1.6 | 2.03 | 2.47 |  | 2.39 | 2.3 | 2.3 | 3.55 | 4.8 | 4.8 |  | 4.8 | 4.8 | 4.8 | 2.4 | [6 empty] | 0.36 | 0.72 | 0.72 |  | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.36 | [9 empty] | 0.1 | 0.2 | 0.2 | 0.2 | 0.3 |  | 0.4 | 0.54 | 0.67 | 0.67 | 0.34 |  |  | 0.07 | 0.13 | 0.13 | 0.07 | [281 empty] | 0.68 |  | 2.71 | 2.71 | 2.71 | 2.71 | 2.71 | 2.71 |  | 2.71 | 2.03
SL Pole 12 M |  |  |  | 193 | 0 | 2354600 | 2354600 | 0 | [15 empty] | 0.97 | 0.97 | 0.97 | 0.97 |  | 0.97 | 0.97 | [483 empty] | 0.14 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.74 | 1.31 |  | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 |  | 1.31 | 1.25 | 1.08 | 1.08 | 1.08 | 1.08 |  | 0.94 | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 |  | 0.53 | 0.73 | 1.68 | 2.73 | 2.61 | 2.23 |  | 2.23 | 2.23 | 2.23 |  | 2.23 | 2.23 |  | 2.23 | 2.6 | 4.07 | 4.83 | 3.21 | 2.17 |  | 2.92 | 1.59 | 1.93 | 2.93 | 3.08 | 3.08 |  | 1.61 | 1.52 | 1.89 | 1.6 | 1.6 | 1.6 |  | 1.6 | 1.6 | 1.6 | 1.55 | 1.97 | 3.73 |  | 3.58 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 |  | 3.11 | 2.33 |  | 0.05 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.41 | 1.05 | 1.05 | 1.05 |  | 1.05 | 1.23 | 1.77 | 1.77 | 1.77 | 1.33 |  |  |  | 0.05 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.15 | [6 empty] | 0.48 | 1.93 | 1.93 | 1.93 | 1.93 |  | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 1.45
Stand. Arm. 1C 10MM2 |  |  |  | 5900 | 177 | 737500 | 737500 | 177 | [15 empty] | 29.5 | 29.5 | 29.5 | 29.5 |  | 29.5 | 29.5 | [559 empty] | 4.92 | 19.67 | 19.67 | 19.67 | 19.67 |  | 19.67 | 34.75 | 80.01 | 80.01 | 80.01 | 80.01 |  | 80.01 | 98.87 | 155.44 | 155.44 | 155.44 | 155.44 |  | 155.44 | 158.73 | 168.59 |  | 143.7 | 69.03 |  | 69.03 | 69.03 | 74.19 | 89.69 | 89.69 | 89.69 |  | 89.69 | 89.69 | 80.64 | 45.03 | 19.67 | 21.31 |  | 26.24 | 26.24 | 26.24 | 26.24 | 26.24 | 26.24 |  | 26.24 | 26.24 | 26.24 | 26.24 | 31.71 | 46.47 |  | 44.13 | 51.9 | 51.9 | 51.9 | 51.9 | 51.9 |  | 51.9 | 61.2 | 89.08 | 95.24 | 113.71 | 113.71 |  | 113.71 | 113.71 | 112.51 | 108.91 | 108.91 | 89.29 |  | 30.81 | 31.95 | 31.95 | 31.95 | 31.95 | 28.07 |  | 16.4 | 22.77 | 41.89 | 41.89 | 41.89 | 41.89 |  | 37.79 | 25.49 | 22.09 | 11.9 | 11.9 | 11.9 |  | 11.9 | 23.67 | 59 | 59 | 59 | 59 |  | 59 | 59 | 59 | 59 | 59 | 44.25
Stand. Arm. 1C 16MM2 |  |  |  | 910 | 27.3 | 118300 | 118300 | 27.3 | [15 empty] | 4.55 | 4.55 | 4.55 | 4.55 |  | 4.55 | 4.55 | [559 empty] | 0.76 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 6.42 | 16.58 | 16.58 | 16.58 | 16.58 | 16.58 |  | 16.58 | 16.58 | 16.58 | 24.63 | 48.76 | 48.76 |  | 48.76 | 48.76 | 48 | 45.73 | 45.73 | 39.38 |  | 20.32 | 20.32 | 20.32 | 20.32 | 20.32 | 15.24 | [16 empty] | 2.28 | 9.1 | 9.1 | 9.1 | 9.1 |  | 9.1 | 9.1 | 9.1 | 9.1 | 9.1 | 6.83
Stand. Arm. 4C 16MM2 |  |  |  | 5900 | 177 | 1091500 | 1091500 | 177 | [15 empty] | 29.5 | 29.5 | 29.5 | 29.5 |  | 29.5 | 29.5 | [559 empty] | 4.92 | 19.67 | 19.67 | 19.67 | 19.67 |  | 19.67 | 34.75 | 80.01 | 80.01 | 80.01 | 80.01 |  | 80.01 | 98.87 | 155.44 | 155.44 | 155.44 | 155.44 |  | 155.44 | 158.73 | 168.6 |  | 143.7 | 69.03 |  | 69.03 | 69.03 | 65.74 | 55.87 | 55.87 | 65.74 |  | 95.33 | 95.33 | 86.28 | 59.12 | 59.12 | 50.9 |  | 26.24 | 26.24 | 26.24 | 26.24 | 26.24 | 26.24 |  | 26.24 | 26.24 | 26.24 | 26.24 | 31.71 | 46.47 |  | 44.13 | 51.9 | 51.9 | 51.9 | 51.9 | 51.9 |  | 51.9 | 46.44 | 44.8 | 95.23 | 113.7 | 113.7 |  | 113.7 | 113.7 | 112.51 | 108.91 | 108.91 | 104.05 |  | 81.46 | 57.45 | 57.45 | 57.45 | 57.45 | 53.56 |  | 41.89 | 35.52 | 16.4 | 16.4 | 16.4 | 16.4 |  | 12.3 |  | 2.97 | 11.9 | 11.9 | 11.9 |  | 11.9 | 23.67 | 59 | 59 | 59 | 59 |  | 59 | 59 | 59 | 59 | 59 | 44.25
Stand. Arm. 4C 25MM2 |  |  |  | 910 | 27.3 | 200200 | 200200 | 27.3 | [15 empty] | 4.55 | 4.55 | 4.55 | 4.55 |  | 4.55 | 4.55 | [559 empty] | 0.76 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 |  | 6.42 | 16.58 | 16.58 | 16.58 | 16.58 | 16.58 |  | 16.58 | 16.58 | 16.58 | 24.63 | 48.76 | 48.76 |  | 48.76 | 48.76 | 48 | 45.73 | 45.73 | 39.38 |  | 20.32 | 20.32 | 20.32 | 20.32 | 20.32 | 15.24 | [16 empty] | 2.28 | 9.1 | 9.1 | 9.1 | 9.1 |  | 9.1 | 9.1 | 9.1 | 9.1 | 9.1 | 6.83
Stand. Arm. 4C 35MM2 |  |  |  | 15 | 0.45 | 3750 | 3750 | 0.45 | [15 empty] | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | [559 empty] | 0.01 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.11 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 |  | 0.27 | 0.27 | 0.27 | 0.43 | 0.91 | 0.91 |  | 0.91 | 0.91 | 0.9 | 0.86 | 0.65 | 0.08 |  | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.25 | [16 empty] | 0.04 | 0.15 | 0.15 | 0.15 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.11
Storm 1000 mm depth: 1.5 - 2.5m |  |  |  | 485 | 14.55 | 1100950 | 1100950 | 14.55 | 1.82 | 1.82 | 1.82 | 1.82 | 1.82 |  | 1.82 | 1.82 | 1.82 | [57 empty] | 0.45 | 0.45 |  | 0.45 | 0.45 | 0.45 | 0.45 | [5 empty] | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | [5 empty] | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 4.09 | 7.57 | 7.57 | 7.57 |  | 7.57 | 7.57 | 7.57 | 8.15 | 8.73 | 8.73 |  | 8.73 | 20.92 | 33.1 | 33.1 | 33.1 | 33.1 |  | 20.1 | 7.11 | 7.11 | 7.11 | 7.11 | 7.92 |  | 8.73 | 8.73 | 8.73 | 8.73 | 8.73 | 4.67 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 |  | 0.3 | [375 empty] | 1.52 |  | 6.06 | 6.06 | 6.06 | 6.06 | 6.06 | 6.06 |  | 6.06 | 4.55
Storm 1000 mm depth: 2.5 - 3.5m |  |  |  | 410 | 12.3 | 1016800 | 1016800 | 12.3 | 1.54 | 1.54 | 1.54 | 1.54 | 1.54 |  | 1.54 | 1.54 | 1.54 | [57 empty] | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | [5 empty] | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | [5 empty] | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 2.57 | 4.63 | 4.63 |  | 4.63 | 4.63 | 4.63 | 4.22 | 3.81 | 3.81 |  | 3.81 | 3.81 | 10.4 | 16.98 | 16.98 | 16.98 |  | 16.98 | 10.4 | 3.81 | 3.81 | 3.81 | 3.81 |  | 4.63 | 5.45 | 5.45 | 5.45 | 5.45 | 2.98 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 |  | 0.26 | [37 empty] | 2.06 | 4.12 | 4.12 |  | 4.12 | 4.81 | 5.5 | 11.91 | 18.33 | 18.33 |  | 11.91 | 5.5 | 5.5 | 5.5 | 5.5 | 2.75 | [321 empty] | 1.28 |  | 5.13 | 5.13 | 5.13 | 5.13 | 5.13 | 5.13 |  | 5.13 | 3.84
Storm 1000 mm depth: 3.5 - 4.5m |  |  |  | 35 | 1.05 | 93800 | 93800 | 1.05 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | [57 empty] | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.02 | [42 empty] | 0.29 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 2.25 |  | 3.91 | 3.91 | 2.25 | 0.59 | 0.59 | 0.59 |  | 0.73 | 0.88 | 0.88 | 0.88 | 0.44 | [308 empty] | 0.11 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.33
Storm 1100 mm depth: 1.5 - 2.5m |  |  |  | 50 | 1.5 | 130000 | 130000 | 1.5 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | [57 empty] | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.03 | [56 empty] | 0.84 | 1.68 | 1.68 | 1.68 | 1.68 |  | 3.63 | 5.58 | 5.58 | 3.35 | 1.12 | 1.12 |  | 1.19 | 1.26 | 1.26 | 1.26 | 0.63 | [301 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47
Storm 1100 mm depth: 2.5 - 3.5m |  |  |  | 472 | 14.16 | 1331040 | 1331040 | 14.16 | 1.77 | 1.77 | 1.77 | 1.77 | 1.77 |  | 1.77 | 1.77 | 1.77 | [57 empty] | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | [5 empty] | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | [5 empty] | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 4.54 | 8.5 | 8.5 |  | 8.5 | 8.5 | 8.5 | 7.71 | 6.91 | 6.91 |  | 6.91 | 6.91 | 19.56 | 32.21 | 32.21 | 32.21 |  | 32.21 | 19.56 | 6.91 | 6.91 | 6.91 | 6.91 |  | 8.5 | 10.08 | 10.08 | 10.08 | 10.08 | 5.33 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  | 0.29 | [375 empty] | 1.48 |  | 5.9 | 5.9 | 5.9 | 5.9 | 5.9 | 5.9 |  | 5.9 | 4.43
Storm 1100 mm depth: 3.5 - 4.5m |  |  |  | 300 | 9 | 912000 | 912000 | 9 | 1.13 | 1.13 | 1.13 | 1.13 | 1.13 |  | 1.13 | 1.13 | 1.13 | [57 empty] | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | [5 empty] | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | [5 empty] | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 1.7 | 3.03 | 3.03 |  | 3.03 | 3.03 | 3.03 | 2.77 | 2.5 | 2.5 |  | 2.5 | 2.5 | 6.76 | 11.01 | 11.01 | 11.01 |  | 11.01 | 6.76 | 2.5 | 2.5 | 2.5 | 2.5 |  | 3.03 | 3.57 | 3.57 | 3.57 | 3.57 | 1.97 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.19 | [49 empty] | 1.18 | 2.37 | 2.37 | 2.37 | 2.37 |  | 2.37 | 2.37 | 2.37 | 2.37 | 2.37 | 9.07 |  | 15.77 | 15.77 | 9.07 | 2.37 | 2.37 | 2.37 |  | 2.96 | 3.55 | 3.55 | 3.55 | 1.77 | [301 empty] | 0.94 |  | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 |  | 3.75 | 2.81
Storm 1200 mm depth: 2.5 - 3.5m |  |  |  | 50 | 1.5 | 144000 | 144000 | 1.5 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | [57 empty] | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.03 | [59 empty] | 0.84 | 1.68 |  | 1.68 | 1.68 | 1.68 | 3.63 | 5.58 | 5.58 |  | 3.35 | 1.12 | 1.12 | 1.4 | 1.68 | 1.68 |  | 0.84 | [298 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47
Storm 1200 mm depth: 3.5 - 4.5m |  |  |  | 220 | 6.6 | 682000 | 682000 | 6.6 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 |  | 0.83 | 0.83 | 0.82 | [57 empty] | 0.21 | 0.21 |  | 0.21 | 0.21 | 0.21 | 0.21 | [5 empty] | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | [5 empty] | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.44 | 0.6 | 0.6 |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.65 |  | 0.71 | 0.71 | 0.71 | 1.57 | 2.44 | 2.44 |  | 2.44 | 1.53 | 0.62 | 0.62 | 0.62 | 0.62 |  | 0.71 | 0.79 | 0.79 | 0.79 | 0.79 | 0.53 |  | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 |  | 0.14 | [56 empty] | 1.63 | 3.25 | 3.25 | 3.25 | 3.25 |  | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 12.47 |  | 21.68 | 21.68 | 12.47 | 3.25 | 3.25 | 3.25 |  | 2.51 | 1.77 | 1.77 | 1.77 | 1.77 | 1.77 |  | 1.77 | 1.77 | 1.77 | 1.77 | 1.77 | 0.89 | [286 empty] | 0.69 |  | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 |  | 2.75 | 2.06
Storm 1200 mm depth: 4.5 - 5.5m |  |  |  | 35 | 1.05 | 116900 | 116900 | 1.05 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | [57 empty] | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.08 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.26 | 0.4 | 0.4 |  | 0.4 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.08 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.3 | 0.56 | 0.56 |  | 0.54 | 0.52 | 0.52 | 0.6 | 0.69 | 0.69 |  | 2.06 | 3.44 | 3.44 | 1.98 | 0.52 | 0.52 |  | 0.52 | 0.64 | 0.77 | 0.77 | 0.77 | 0.39 | [356 empty] | 0.11 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.33
Storm 1400 mm depth: 2.5 - 3.5m |  |  |  | 100 | 3 | 362000 | 362000 | 3 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | [57 empty] | 0.09 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.09 | [5 empty] | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | [5 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.06 | [63 empty] | 1.68 | 3.35 | 3.35 | 3.35 | 3.35 |  | 7.26 | 11.17 | 11.17 | 6.7 | 2.23 | 2.23 |  | 2.79 | 3.35 | 3.35 | 1.68 | [295 empty] | 0.31 |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |  | 1.25 | 0.94
Storm 1400 mm depth: 3.5 - 4.5m |  |  |  | 250 | 7.5 | 970000 | 970000 | 7.5 | 0.94 | 0.94 | 0.94 | 0.94 | 0.94 |  | 0.94 | 0.94 | 0.94 | [57 empty] | 0.23 | 0.23 |  | 0.23 | 0.23 | 0.23 | 0.23 | [5 empty] | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | [5 empty] | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 |  | 0.16 | [66 empty] | 3.14 | 6.28 |  | 6.28 | 6.28 | 7.33 | 8.38 | 14.66 | 20.94 |  | 20.94 | 20.94 | 13.26 | 5.58 | 5.58 | 5.93 |  | 6.28 | 6.28 | 6.28 | 3.14 | [288 empty] | 0.78 |  | 3.13 | 3.13 | 3.13 | 3.13 | 3.13 | 3.13 |  | 3.13 | 2.34
Storm 1400 mm depth: 4.5 - 5.5m |  |  |  | 35 | 1.05 | 249550 | 249550 | 1.05 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | [57 empty] | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.02 | [71 empty] | 0.35 | 0.7 | 0.7 | 0.7 |  | 0.7 | 0.94 | 1.17 | 2.05 | 2.93 | 2.93 |  | 2.93 | 1.86 | 0.78 | 0.78 | 0.68 | 0.59 |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.29 | [280 empty] | 0.11 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.33
Storm 400 mm depth: 1.5 - 2.5m |  |  |  | 355 | 10.65 | 237850 | 237850 | 10.65 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |  | 1.33 | 1.33 | 1.33 | [57 empty] | 0.33 | 0.33 |  | 0.33 | 0.33 | 0.33 | 0.33 | [5 empty] | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 1.42 | 2.39 | 2.39 |  | 2.39 | 2.39 | 2.39 | 2.39 | 2.32 | 2.26 |  | 2.26 | 2.26 | 2.26 | 5.89 | 9.51 | 9.51 |  | 9.51 | 9.51 | 5.89 | 2.26 | 2.26 | 2.26 |  | 2.26 | 2.71 | 3.16 | 3.16 | 3.16 | 3.16 |  | 1.8 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | [5 empty] | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 4.12 |  | 7.8 | 7.8 | 7.8 | 7.8 | 22.52 | 37.23 |  | 22.29 | 7.36 | 9.2 | 11.04 | 5.52 | [371 empty] | 1.11 |  | 4.44 | 4.44 | 4.44 | 4.44 | 4.44 | 4.44 |  | 4.44 | 3.33
Storm 400 mm depth: 2.5 - 3.5m |  |  |  | 95 | 2.85 | 78375 | 78375 | 2.85 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 |  | 0.36 | 0.36 | 0.36 | [57 empty] | 0.09 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.09 | [5 empty] | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.26 | 0.4 |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 |  | 0.41 | 0.42 | 0.42 | 0.42 | 0.42 | 1.01 |  | 1.6 | 1.6 | 1.6 | 1.6 | 1.01 | 0.42 |  | 0.42 | 0.42 | 0.42 | 0.45 | 0.49 | 0.49 |  | 0.49 | 0.49 | 0.49 | 0.3 | 0.12 | 0.12 |  | 0.12 | 0.12 | [5 empty] | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.28 | 0.43 |  | 0.43 | 0.43 |  | 0.43 | 0.45 | 0.47 |  | 0.47 | 1.17 | 1.86 | 1.86 | 1.3 | 0.73 |  | 0.73 | 0.73 | 0.6 | 0.49 | 0.51 | 0.71 |  | 1.68 | 2.47 | 2.96 | 2.44 | 1.41 | 1.41 |  | 1.52 | 1.7 | 4.44 | 7.1 | 4.44 | 1.55 |  | 1.67 | 2 | 1 | [366 empty] | 0.3 |  | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 |  | 1.19 | 0.89
Storm 500 mm depth: 1.5 - 2.5m |  |  |  | 380 | 12.21 | 357200 | 357200 | 12.21 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 |  | 1.43 | 1.43 | 1.43 | [57 empty] | 0.36 | 0.36 |  | 0.36 | 0.36 | 0.36 | 0.36 | [5 empty] | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 1.11 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 |  | 1.61 | 1.48 | 1.48 | 1.48 | 1.48 | 3.5 |  | 5.52 | 5.52 | 5.52 | 5.52 | 3.5 | 1.48 |  | 1.48 | 1.48 | 1.48 | 1.74 | 1.99 | 1.99 |  | 1.99 | 1.99 | [5 empty] | 1.23 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 |  | 0.48 | 1.29 | 2.1 |  | 2.1 | 2.1 | 2.1 | 1.97 | 1.83 | 1.83 |  | 1.83 | 4.55 | 7.26 | 7.26 | 7.26 | 4.55 |  | 1.83 | 1.83 | 1.83 | 2.17 | 2.51 | 2.51 |  | 4.06 | 4.6 | 3.58 | 3.58 | 4.18 | 4.77 |  | 14.32 | 23.87 | 14.32 | 4.77 | 5.97 | 7.16 |  | 3.58 | [27 empty] | 1.36 | 2.72 | 2.72 | 2.72 | 2.72 | 5.88 |  | 9.05 | 9.05 | 5.43 | 1.81 | 1.81 | 2.26 |  | 2.72 | 2.72 | 1.36 | [317 empty] | 1.19 |  | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 | 4.75 |  | 4.75 | 3.56
Storm 500 mm depth: 2.5 - 3.5m |  |  |  | 110 | 3.3 | 118800 | 118800 | 3.3 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 |  | 0.41 | 0.41 | 0.41 | [57 empty] | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | [5 empty] | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.07 |  |  |  | 1.38 | 2.76 |  | 2.76 | 2.76 | 3.22 | 3.69 | 11.06 | 18.43 |  | 11.06 | 3.69 | 4.61 | 5.53 | 2.76 | [357 empty] | 0.34 |  | 1.38 | 1.38 | 1.38 | 1.38 | 1.38 | 1.38 |  | 1.38 | 1.03
Storm 500 mm depth: 3.5 - 4.5m |  |  |  | 50 | 1.5 | 61250 | 61250 | 1.5 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | [57 empty] | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.03 | [8 empty] | 0.63 | 1.26 | 1.26 | 1.26 |  | 1.47 | 1.68 | 5.03 | 8.38 | 5.03 | 1.68 |  | 2.09 | 2.51 | 1.26 | [352 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47
Storm 600 mm depth: 1.5 - 2.5m |  |  |  | 465 | 25.3 | 492900 | 492900 | 25.3 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 |  | 1.74 | 1.74 | 1.74 | [57 empty] | 0.44 | 0.44 |  | 0.44 | 0.44 | 0.44 | 0.44 | [5 empty] | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 2.49 | 4.4 | 4.4 | 4.4 | 4.4 | 4.4 |  | 4.4 | 4.27 | 4.14 | 4.14 | 4.14 | 4.14 |  | 11.26 | 18.38 | 18.38 | 18.38 | 18.38 | 11.26 |  | 4.14 | 4.14 | [5 empty] | 4.14 | 4.14 | 4.59 | 5.03 | 5.03 | 5.03 |  | 5.03 | 5.03 | 2.81 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 |  | 0.58 | 0.58 | 0.58 | 1.84 | 3.1 | 3.1 |  | 3.1 | 3.1 | 2.89 | 2.68 | 2.68 | 2.68 |  | 6.89 | 11.09 | 11.09 | 11.09 | 6.89 | 2.68 |  | 2.39 | 2.1 | 2.63 | 3.15 | 3.15 | 3.15 |  | 1.58 | [6 empty] | 0.93 | 1.85 | 1.85 | 1.85 | 2.16 | 2.47 |  | 7.42 | 12.36 | 7.42 | 2.47 | 2.47 | 2.47 |  | 2.47 | 1.24 | [346 empty] | 1.45 |  | 5.81 | 5.81 | 5.81 | 5.81 | 5.81 | 5.81 |  | 5.81 | 4.36
Storm 600 mm depth: 2.5 - 3.5m |  |  |  | 110 | 3.3 | 24200 | 24200 | 3.3 | 0.41 | 0.41 | 0.41 | 0.41 | 0.41 |  | 0.41 | 0.41 | 0.41 | [57 empty] | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | [5 empty] | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.07 | [17 empty] | 1.38 | 2.76 |  | 2.76 | 2.76 | 3.22 | 3.69 | 11.06 | 18.43 |  | 11.06 | 3.69 | 3.69 | 3.69 | 3.69 | 1.84 | [342 empty] | 0.34 |  | 1.38 | 1.38 | 1.38 | 1.38 | 1.38 | 1.38 |  | 1.38 | 1.03
Storm 600 mm depth: 3.5 - 4.5m |  |  |  | 50 | 1.5 | 68500 | 68500 | 1.5 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | [57 empty] | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.03 | [22 empty] | 0.63 | 1.26 | 1.26 | 1.26 |  | 1.47 | 1.68 | 5.03 | 8.38 | 5.03 | 1.68 |  | 1.68 | 1.68 | 1.68 | 0.84 | [337 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47
Storm 700 mm depth: 1.5 - 2.5m |  |  |  | 300 | 16.33 | 420000 | 420000 | 16.33 | 1.13 | 1.13 | 1.13 | 1.13 | 1.13 |  | 1.13 | 1.13 | 1.13 | [57 empty] | 0.28 | 0.28 |  | 0.28 | 0.28 | 0.28 | 0.28 | [5 empty] | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 1.67 | 2.96 | 2.96 | 2.96 | 2.96 |  | 2.96 | 2.7 | 2.44 | 2.44 | 2.44 | 2.44 |  | 6.57 | 10.71 | [5 empty] | 10.71 | 10.71 | 10.71 | 6.57 | 2.44 | 2.44 |  | 2.44 | 2.44 | 2.96 | 3.47 | 3.47 | 3.47 |  | 3.47 | 1.92 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  | 0.38 | 0.38 | 1.84 | 3.31 | 3.31 | 3.31 |  | 3.31 | 3.06 | 2.82 | 2.82 | 2.82 | 7.7 |  | 12.4 | 12.21 | 12.21 | 7.33 | 2.44 | 2.44 |  | 2.44 | 3.05 | 3.66 | 3.66 | 3.66 | 1.83 | [363 empty] | 0.94 |  | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 |  | 3.75 | 2.81
Storm 700 mm depth: 2.5 - 3.5m |  |  |  | 530 | 15.9 | 832100 | 832100 | 15.9 | 1.99 | 1.99 | 1.99 | 1.99 | 1.99 |  | 1.99 | 1.99 | 1.99 | [57 empty] | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | [5 empty] | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 1.43 | 2.2 | 2.2 | 2.2 | 2.2 |  | 2.2 | 2.2 | [5 empty] | 2.33 | 2.46 | 2.46 | 2.46 | 5.15 | 7.85 |  | 7.85 | 7.85 | 7.85 | 5.15 | 2.46 | 2.46 |  | 2.46 | 2.46 | 2.46 | 2.46 | 2.46 | 2.46 |  | 2.46 | 1.56 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 |  | 0.66 | 0.66 | 0.66 | 2.61 | 4.56 | 4.56 |  | 4.56 | 4.56 | 4.56 | 4.56 | 4.56 | 4.56 |  | 4.23 | 11.69 | 19.49 | 19.49 | 19.49 | 11.04 |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.97 |  | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 |  | 1.67 | [6 empty] | 1.91 | 3.82 | 3.82 | 3.82 | 3.82 | 5.09 |  | 6.37 | 19.11 | 31.84 | 19.11 | 6.37 | 6.37 |  | 6.37 | 6.37 | 3.18 | [331 empty] | 1.66 |  | 6.63 | 6.63 | 6.63 | 6.63 | 6.63 | 6.63 |  | 6.63 | 4.97
Storm 700 mm depth: 3.5 - 4.5m |  |  |  | 50 | 1.5 | 87000 | 87000 | 1.5 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | [57 empty] | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.03 | [44 empty] | 0.84 | 1.68 | 1.68 |  | 1.68 | 1.68 | 3.63 | 5.58 | 5.58 | 3.35 |  | 1.12 | 1.12 | 1.4 | 1.68 | 1.68 | 0.84 | [314 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47
Storm 800 mm depth: 1.5 - 2.5m |  |  |  | 280 | 8.4 | 459200 | 459200 | 8.4 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |  | 1.05 | 1.05 | 1.05 | [57 empty] | 0.26 | 0.26 |  | 0.26 | 0.26 | 0.26 | 0.26 | [5 empty] | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | [5 empty] | 2.36 | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 |  | 4.37 | 4.24 | 4.1 | 4.1 | 4.1 | 4.1 |  | 10.04 | 15.98 | 15.98 | 15.98 | 15.98 | 15.98 |  | 9.73 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 |  | 4.26 | 5.04 | 5.04 | 5.04 | 5.04 | 5.04 |  | 2.7 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.17 | [375 empty] | 0.88 |  | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 |  | 3.5 | 2.63
Storm 800 mm depth: 2.5 - 3.5m |  |  |  | 160 | 8.08 | 291200 | 291200 | 8.08 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 |  | 0.6 | 0.6 | 0.6 | [57 empty] | 0.15 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | [5 empty] | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | [5 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.88 | 1.56 | 1.56 | 1.56 | 1.56 |  | 1.56 | 1.56 | 1.67 | 1.79 | 1.79 | 1.79 |  | 4.17 | 6.55 | 6.55 | 6.55 | 6.55 | 4.17 |  | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 |  | 1.79 | 1.79 | 1.79 | 0.99 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 1.02 | 1.84 | 1.84 | 1.84 | 1.75 |  | 1.56 | 1.46 | 4.37 | 7.28 | 7.28 | 4.08 |  | 0.87 | 0.87 | 0.87 | 0.87 | 0.98 | 1.09 |  | 1.09 | 1.09 | 1.09 | 1.09 | 0.55 | [357 empty] | 0.5 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 1.5
Storm 800 mm depth: 3.5 - 4.5m |  |  |  | 50 | 1.5 | 100000 | 100000 | 1.5 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.19 | 0.19 | [57 empty] | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [5 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.03 | [48 empty] | 1.26 | 2.51 | 2.09 | 1.68 | 5.03 | 8.38 |  | 4.75 | 1.12 | 1.12 | 1.4 | 1.68 | 1.68 |  | 0.84 | [312 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47
Storm 900 mm depth: 1.5 - 2.5m |  |  |  | 195 | 5.85 | 390000 | 390000 | 5.85 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 |  | 0.73 | 0.73 | 0.73 | [57 empty] | 0.18 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | [5 empty] | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | [5 empty] | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 1.88 | 3.51 | 3.51 | 3.51 |  | 3.51 | 3.51 | 3.18 | 2.86 | 2.86 | 2.86 |  | 2.86 | 8.08 | 13.31 | 13.31 | 13.31 | 13.31 |  | 8.08 | 2.86 | 2.86 | 2.86 | 2.86 | 2.78 |  | 2.69 | 2.69 | 2.69 | 2.69 | 2.69 | 2.69 |  | 2.69 | 1.47 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  | 0.12 | [375 empty] | 0.61 |  | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 |  | 2.44 | 1.83
Storm 900 mm depth: 2.5 - 3.5m |  |  |  | 90 | 2.7 | 198000 | 198000 | 2.7 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 |  | 0.34 | 0.34 | 0.34 | [57 empty] | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.08 | [5 empty] | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | [5 empty] | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.3 | 0.48 | 0.48 | 0.48 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 |  | 1.21 | 1.95 | 1.95 | 1.95 | 1.18 | 0.41 |  | 0.41 | 0.41 | 0.41 | 0.48 | 0.55 | 0.55 |  | 0.55 | 0.55 | 0.33 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.06 | [32 empty] | 0.86 |  | 1.71 | 1.71 | 1.71 | 2 | 2.28 | 6.84 |  | 11.41 | 6.84 | 2.28 | 2.28 | 2.28 | 2.28 |  | 1.14 | [326 empty] | 0.28 |  | 1.13 | 1.13 | 1.13 | 1.13 | 1.13 | 1.13 |  | 1.13 | 0.84
Storm 900 mm depth: 3.5 - 4.5m |  |  |  | 35 | 1.05 | 84000 | 84000 | 1.05 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | [57 empty] | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | [5 empty] | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.02 | [53 empty] | 0.88 |  | 1.76 | 1.47 | 1.17 | 2.54 | 3.91 | 3.91 |  | 2.34 | 0.78 | 0.78 | 0.98 | 1.17 | 1.17 |  | 0.59 | [305 empty] | 0.11 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  | 0.44 | 0.33
Storm Manhole Dia 1200 mm, Depth: 1.5 - 2.5m |  |  |  | 9 | 0 | 133200 | 133200 | 0 | [6 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | [51 empty] | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.04 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.13 | 0.17 | 0.17 |  | 0.17 | 0.17 | 0.11 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.03 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 |  | 0.01 | 0.03 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.08 | 0.1 |  | 0.1 | 0.14 | 0.19 | 0.19 | 0.12 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.13 |  | 0.2 | 0.19 | 0.17 | 0.14 | 0.14 | 0.14 |  | 0.34 | 0.55 | 0.34 | 0.14 | 0.14 | 0.14 |  | 0.08 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0 | [340 empty] | 0.03 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.08
Storm Manhole Dia 1200 mm, Depth: 2.5 - 3.5m |  |  |  | 3 | 0 | 68640 | 68640 | 0 | [6 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | [51 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0.01 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.04 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.04 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 | 0.01 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0.02 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.04 | 0.05 | 0.05 |  | 0.07 | 0.09 | 0.09 | 0.06 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.04 | 0.05 | 0.05 | 0.05 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.09 | 0.14 |  | 0.09 | 0.04 | 0.04 | 0.04 | 0.02 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [340 empty] | 0.01 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.03
Storm Manhole Dia 1200 mm; Depth < 1.5m |  |  |  | 1 | 0 | 12280 | 12280 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [51 empty] | 0.2 | [193 empty] | 0.02 | 0.04 | 0.04 | 0.04 |  | 0.03 | 0.03 | 0.03 | 0.08 | 0.13 | 0.08 |  | 0.03 | 0.03 | 0.03 | 0.02 | [365 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01
Storm Manhole Dia 1500 mm, Depth: 1.5 - 2.5m |  |  |  | 18 | 0 | 290700 | 290700 | 0 | [6 empty] | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | [51 empty] | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.08 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.18 | 0.21 | 0.21 | 0.21 | 0.21 |  | 0.21 | 0.21 | [5 empty] | 0.34 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 |  | 0.3 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.07 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.07 | 0.13 | 0.13 |  | 0.13 | 0.13 | 0.16 | 0.2 | 0.2 | 0.29 |  | 0.38 | 0.38 | 0.23 | 0.09 | 0.09 | 0.09 |  | 0.18 | 0.26 | 0.26 | 0.24 | 0.19 | 0.15 |  | 0.15 | 0.35 | 0.55 | 0.35 | 0.15 | 0.15 |  | 0.15 | 0.09 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.01 | [340 empty] | 0.06 |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 |  | 0.23 | 0.17
Storm Manhole Dia 1500 mm, Depth: 2.5 - 3.5m |  |  |  | 9 | 0 | 178200 | 178200 | 0 | [6 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | [51 empty] | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.04 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.09 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.17 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.14 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.04 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.02 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.05 | 0.05 | 0.08 | 0.12 | 0.14 |  | 0.14 | 0.11 | 0.07 | 0.13 | 0.18 | 0.18 |  | 0.22 | 0.26 | 0.26 | 0.19 | 0.12 | 0.22 |  | 0.32 | 0.21 | 0.11 | 0.11 | 0.11 | 0.06 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0 | [340 empty] | 0.03 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.08
Storm Manhole Dia 1500 mm, Depth: 3.5 - 4.5m |  |  |  | 1 | 0 | 29400 | 29400 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [51 empty] | 0.2 | [213 empty] | 0.02 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.08 | 0.13 | 0.08 |  | 0.03 | 0.03 | 0.03 | 0.02 | [344 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01
Storm Manhole Dia 2000 mm, Depth > 5.5m |  |  |  | 1 | 0 | 65750 | 65750 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [51 empty] | 0.2 | [147 empty] | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.04 |  | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.03 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0 | [381 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01
Storm Manhole Dia 2000 mm, Depth: 1.5 - 2.5m |  |  |  | 4 | 0 | 104400 | 104400 | 0 | [6 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | [51 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0.03 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.08 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.17 | 0.22 | 0.22 | 0.22 | 0.22 |  | 0.14 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.03 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [340 empty] | 0.01 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.04
Storm Manhole Dia 2000 mm, Depth: 2.5 - 3.5m |  |  |  | 8 | 0 | 274240 | 274240 | 0 | [6 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | [51 empty] | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.04 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.09 | 0.12 | 0.12 | 0.12 | 0.12 | 0.17 |  | 0.22 | 0.22 | 0.22 | 0.22 | 0.14 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.04 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.08 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.34 | 0.54 | 0.34 | 0.14 | 0.14 |  | 0.14 | 0.07 | [339 empty] | 0.03 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.08
Storm Manhole Dia 2000 mm, Depth: 3.5 - 4.5m |  |  |  | 15 | 0 | 702000 | 702000 | 0 | [6 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | [51 empty] | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.06 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.14 |  | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 |  | 0.31 | 0.44 | 0.44 | 0.44 | 0.44 | 0.27 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.11 |  | 0.06 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.11 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.23 | 0.25 | 0.25 | 0.25 |  | 0.59 | 0.94 | 0.59 | 0.23 | 0.2 | 0.16 |  | 0.16 | 0.08 | [332 empty] | 0.05 |  | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  | 0.19 | 0.14
Storm Manhole Dia 2000 mm, Depth: 4.5 - 5.5m |  |  |  | 4 | 0 | 225120 | 225120 | 0 | [6 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | [51 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0.05 | 0.09 | 0.09 |  | 0.09 | 0.09 | 0.09 | 0.14 | 0.18 | 0.18 |  | 0.27 | 0.36 | 0.36 | 0.22 | 0.07 | 0.07 |  | 0.07 | 0.06 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.02 | [339 empty] | 0.01 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.04
Street Lighting Panels |  |  |  | 1 | 0 | 82000 | 82000 | 0 | [31 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [542 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.02 | 0.05 |  |  | 0.01 | 0.04 | 0.04 | 0.07 | 0.16 | 0.16 |  | 0.12 | [21 empty] | 0 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
TSE Air V Dia (50) mm on pipes with dia(160) mm. |  |  |  | 9 | 0.2 | 27495 | 27495 | 0.2 | [22 empty] | 0.05 | 0.05 | 0.05 |  |  | 0.05 | 0.05 | 0.05 | [421 empty] | 0.01 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.04 | 0.09 | 0.09 | 0.1 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.11 | 0.07 | 0.07 | 0.07 | 0.11 | 0.22 |  | 0.22 | 0.22 | 0.17 | [9 empty] | 0.01 |  | 0.05 | 0.05 | 0.05 | 0.06 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.09 | 0.16 | 0.16 | 0.17 | 0.2 |  | 0.2 | 0.17 | 0.07 |  | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.06 | 0.16 | 0.16 |  | 0.16 | 0.16 | 0.12 | [37 empty] | 0.03 |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  | 0.11 | 0.08
TSE Gate valves dia (160) mm |  |  |  | 7 | 0.15 | 22190 | 22190 | 0.15 | [22 empty] | 0.04 | 0.04 | 0.04 |  |  | 0.04 | 0.04 | 0.04 | [421 empty] | 0 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | [5 empty] | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.02 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.06 | 0.1 | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.09 | 0.1 | 0.12 |  | 0.1 | 0.03 | 0.04 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.05 | 0.02 | 0.02 | 0.03 | 0.04 | 0.04 |  | 0.06 | 0.12 | 0.12 | 0.11 | 0.13 | 0.1 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.04 |  | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.05 |  | 0.1 | 0.11 | 0.1 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.03 | 0.09 | 0.09 | 0.07 | [41 empty] | 0.02 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 |  | 0.09 | 0.07
TSE Gate valves dia (200) mm |  |  |  | 1 | 0.02 | 4465 | 4465 | 0.02 | [22 empty] | 0.01 | 0.01 | 0.01 |  |  | 0.01 | 0.01 | 0 | [421 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [35 empty] | 0 | 0.02 | 0.02 |  | 0.02 | 0.02 | 0.03 |  | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.03 | [42 empty] | 0 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01
TSE Gate valves dia (90) mm |  |  |  | 16 | 0.35 | 37600 | 37600 | 0.35 | [22 empty] | 0.08 | 0.08 | 0.08 |  |  | 0.08 | 0.08 | 0.08 | [421 empty] | 0.01 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | [5 empty] | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.07 | 0.19 |  | 0.19 | 0.18 | 0.15 | 0.15 | 0.15 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.14 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 |  | 0.09 | 0.12 | 0.21 | 0.21 | 0.21 | 0.21 |  | 0.24 | 0.31 | 0.2 | 0.17 | 0.18 | 0.22 |  | 0.18 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 |  | 0.04 | 0.04 | 0.06 | 0.09 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.1 | 0.19 | 0.23 | 0.23 |  | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.13 | 0.13 | 0.13 | 0.14 | 0.16 | 0.15 |  | 0.11 | 0.11 | 0.1 |  | 0.1 | 0.1 |  | 0.1 | 0.11 | 0.13 | 0.13 | 0.13 | 0.13 |  | 0.13 | 0.15 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.15 | [45 empty] | 0.05 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.15
TSE HDPE 160mm 0.0 to 1.5m |  |  |  | 220 | 6.6 | 66000 | 66000 | 6.6 | [18 empty] | 1.1 |  | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | [462 empty] | 0.16 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | [5 empty] | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 | 0.63 |  | 0.63 | 0.47 | [7 empty] | 1.11 | 4.42 | 4.42 | 4.42 |  | 4.42 | 4.05 | 2.95 | 2.95 | 2.95 | 2.95 |  | 4.84 | 10.53 | 10.53 | 10.53 | 10.53 | 10.53 |  | 10.53 | 8.63 | 2.95 |  | 2.95 | 2.95 |  | 2.95 | 3 | 3.16 | 3.16 | 3.16 | 3.16 |  | 3.16 | 3.16 | 2.37 | [51 empty] | 0.69 |  | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 |  | 2.75 | 2.06
TSE HDPE 160mm 1.5 to 3.0m |  |  |  | 4100 | 123 | 1845000 | 1845000 | 123 | [18 empty] | 20.5 |  | 20.5 | 20.5 | 20.5 | 20.5 | 20.5 | [462 empty] | 2.93 |  | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 | [5 empty] | 11.71 | 11.71 |  | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 |  | 19.89 | 44.42 | 44.42 | 44.42 | 44.42 | 49.87 |  | 66.22 | 98.02 | 193.41 | 193.41 | 152.53 | 29.88 |  | 29.88 | 29.88 | 29.88 | 29.88 | 30.45 | 32.16 |  | 32.16 | 32.16 | 32.16 | 32.16 | 32.16 | 32.16 |  | 27.04 | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 |  | 11.71 | 11.71 | 11.71 | 14.78 | 23.99 | 23.99 |  | 23.99 | 23.99 | 26.03 | 32.17 | 52.62 | 113.98 |  | 93.53 | 32.17 | 34.73 | 46.22 | 50.03 | 27.02 |  | 27.02 | 27.02 | 27.02 | 27.02 | 27.02 | 27.02 |  | 27.02 | 24.09 | 15.48 | 16.03 | 16.03 | 16.03 |  | 16.03 | 16.03 | 16.03 | 27.61 | 62.34 | 62.34 |  | 62.34 | 63.52 | 67.05 | 67.05 | 67.05 | 66.66 |  | 53.9 | 19.17 | 19.17 | 21.52 | 28.59 | 28.59 |  | 28.59 | 29.25 | 28.9 |  | 21.84 | 21.84 |  | 21.84 | 21.84 | 21.84 | 21.84 | 21.84 | 17.17 |  | 3.14 | 2.35 | [52 empty] | 12.81 |  | 51.25 | 51.25 | 51.25 | 51.25 | 51.25 | 51.25 |  | 51.25 | 38.44
TSE HDPE 90mm 0.0 to 1.5m |  |  |  | 320 | 9.6 | 70400 | 70400 | 9.6 | [18 empty] | 1.6 |  | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | [462 empty] | 0.23 |  | 0.91 | 0.91 | 0.91 | 0.91 | 0.91 | 0.91 | [5 empty] | 0.91 | 0.91 |  | 0.91 | 1.6 | 3.66 | 3.66 | 3.66 | 3.66 |  | 3.43 | 2.74 | 2.74 | 2.74 | 2.74 | 3.92 |  | 7.45 | 7.45 | 7.45 | 7.45 | 7.45 | 7.45 |  | 6.27 | 2.74 | 2.74 | 2.74 | 2.74 | 2.71 |  | 2.63 | 2.63 | 2.63 | 2.63 | 2.63 | 2.63 |  | 2.63 | 2.2 | 0.91 | 0.91 | 1.89 | 3.85 |  | 0.91 | 0.91 | 0.91 | 1.13 | 1.79 | 1.79 |  | 2.38 | 4.18 | 4.6 | 5.86 | 5.15 | 3.03 |  | 3.03 | 3.03 | 3.03 | 2.94 | 2.71 | 2.87 |  | 2.87 | 2.87 | 2.87 | 3.95 | 7 | 6.51 |  | 6.51 | 6.29 | 5.6 | 5.74 | 5.14 | 2.12 |  | 2.12 | 2.12 | 2.06 | 1.97 | 2.27 | 2.27 |  | 2.27 | 2.27 | 2.48 | 2.62 | 1.15 | 1.15 |  | 1.15 | 1.15 | 1.15 | 1.15 | 0.94 | 0.31 |  | 0.31 | 0.31 | 0.31 |  | 0.31 | 0.32 |  | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 |  | 0.35 | 0.26 | [52 empty] | 1 |  | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 3
TSE Washout Dia (100) mm on pipes with dia (160) mm |  |  |  | 3 | 0.07 | 8460 | 8460 | 0.07 | [22 empty] | 0.02 | 0.02 | 0.02 |  |  | 0.02 | 0.02 | 0.02 | [421 empty] | 0 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [5 empty] | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.05 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.05 | 0.1 |  | 0.1 | 0.1 | 0.09 | 0.09 | 0.07 |  |  |  |  | 0.02 | 0.05 |  | 0.01 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.03 | 0.07 | 0.07 |  | 0.07 | 0.05 | [73 empty] | 0.01 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.04 | 0.03
Unit Substation 13.8/0.4 KV |  |  |  | 1 | 0 | 458000 | 458000 | 0 | [20 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [462 empty] | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | [11 empty] | 0.02 | 0.05 |  |  | 0.01 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.06 | 0.16 | 0.16 |  | 0.12 | [14 empty] | 0 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
V Ch On pipes Dia. 160 mm |  |  |  | 16 | 0 | 24480 | 24480 | 0 | [525 empty] | 0.03 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.11 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 |  | 0.14 | 0.14 | 0.12 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.11 | 0.22 | 0.22 |  | 0.22 | 0.22 | 0.22 | 0.22 | 0.24 | 0.3 |  | 0.24 | 0.08 | 0.09 | 0.12 | 0.12 | 0.12 |  | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 |  | 0.1 | 0.05 | 0.05 | 0.07 | 0.11 | 0.11 |  | 0.16 | 0.3 | 0.28 | 0.26 | 0.33 | 0.27 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.11 | 0.2 |  | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.28 |  | 0.5 | 0.54 | 0.55 | 0.25 | 0.25 | 0.24 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.18 | 0.13 |  | 0.13 | 0.13 | 0.26 | 0.67 | 0.67 | 0.5
V Ch On pipes Dia. 200 mm |  |  |  | 1 | 0 | 1530 | 1530 | 0 | [597 empty] | 0.01 | 0.03 | 0.03 |  | 0.03 | 0.03 | 0.05 |  | 0.05 | 0.05 |  | 0.05 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.05
V Ch On pipes Dia. 90 mm |  |  |  | 16 | 0 | 24480 | 24480 | 0 | [521 empty] | 0.06 | 0.23 |  | 0.23 | 0.22 | 0.18 | 0.18 | 0.18 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 |  | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.15 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 |  | 0.09 | 0.13 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.3 | 0.4 | 0.25 | 0.25 | 0.27 | 0.33 |  | 0.27 | 0.08 | 0.08 | 0.08 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.08 | 0.13 | 0.11 | 0.11 |  | 0.11 | 0.11 | 0.15 | 0.29 | 0.34 | 0.34 |  | 0.29 | 0.14 | 0.14 | 0.14 | 0.14 | 0.16 |  | 0.19 | 0.19 | 0.19 | 0.21 | 0.24 | 0.22 |  | 0.17 | 0.17 | 0.15 |  | 0.15 | 0.15 |  | 0.15 | 0.16 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.23 | 0.3 | 0.3 | 0.3 | 0.3 |  | 0.3 | 0.23
Wash out chamber; on 160 mm dia pipeline |  |  |  | 3 | 0 | 135000 | 135000 | 0 | [531 empty] | 0.01 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  | 0.03 | 0.04 | 0.08 | 0.08 | 0.08 | 0.08 |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.07 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.06 | 0.13 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.1 |  |  |  |  | 0.03 | 0.08 |  | 0.01 |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 |  | 0.02 | 0.02 | 0.02 | 0.04 | 0.1 | 0.1 |  | 0.1 | 0.08
Washout Chambers on pipes Dia. 160 mm |  |  |  | 3 | 0 | 147000 | 147000 | 0 | [445 empty] | 0.05 |  | 0.15 |  |  |  |  | 0.02 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.07 |  | 0.2 | 0.2 | 0.2 | 0.15 | 0.01 | 0.05 |  | 0.06 | 0.1 | 0.1 | 0.1 | 0.09 | 0.05 |  | 0.06 | 0.1 | 0.1 | 0.1 | 0.08
Washout Chambers on pipes Dia. 250 mm |  |  |  | 3 | 0 | 147000 | 147000 | 0 | [473 empty] | 0.01 |  | 0.03 | 0.03 | 0.05 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.09 | 0.13 | 0.24 | 0.19 | 0.08 |  | 0.2 | 0.2 | 0.2 | 0.18 | 0.1 | 0.18 | [5 empty] | 0.4 | 0.3

## Risk Register
Department: | [8 empty] | Status Date:
Program | [8 empty] | 2026-09-21
Project: |  |  | Factories Low-process Unit (HAFR Al Batin)
Project No.: |  |  | HFR1-05-03
Project Location: |  |  | HAFR AL BATIN
[16 empty] | Before Treatment | [10 empty] | Post Treatment
Risk Data | [5 empty] | Category |  |  | Risk Description |  |  | Risk Control Dates |  | Risk Manageability | Risk Proximity | Most Likely |  |  | Risk Owner | Risk Response & Treatment Action |  |  |  | Treatment Control Dates |  |  | Most Likely |  |  | Treatment Status
Risk ID | Region | Section / Group | City | Project ID | Risk Status | T/O/I | Internal/External | Category | Cause / Source | Risk | Consequence / Effect | Identified | Closed |  |  | Liklihood | Impact | Risk Score |  | Risk Response Strategy | Treatment Action | Treatment Acton Description | Treatment Action Owner | Start | Due | Closed | Liklihood | Impact | Risk Score
Site prepartion | Block-1 & 2 | General Area | Hafar albatin | HFR1-05-003 | Close | Threat | Internal | Safety / Quality | TUV on equipment. | Take Time due to Certificate | Potential delay in some activities/Add cost | 2026-04-20 | 2026-04-25 | Ease | Imminent | Medium | Medium | 2 | PM. Ahmed maher | Treat | Control | know Certificate is available | Contractor | 2026-04-20 | 5 day | 2026-04-25 | Low | Low | 1 | Close
Work at heights | OFFICE AREA | General Area | Hafar albatin | HFR1-05-003 | Close | Threat | Internal | Safety / Quality | OPEN HOLE | _Falls into hole _collapse of excavation sides | _serious injury __damge | 2026-04-23 | 2026-04-23 | Ease | Imminent | High | High | 3 | PM Ahmed maher | Treat | Control | _install barricades _sing bord _backfill the hole | site engineer | 2026-04-23 | same day | 2025-04-23 | Low | Low | 1 | Close
Lack of PPE | Block-1 & 2 | General Area | Hafar albatin | HFR1-05-003 | Close | Threat | Internal | Safety / Quality | LACK OF PPE DURING CONCRETE WORK | _EYE INJURY FROM SPLASHES _SLIPS DUE TO WET SURFACE | _EYE DAMAGE _INJUIRY | 2026-05-02 | 2026-05-02 | Ease | Imminent | High | High | 3 | PM:AHMED MAHER | Treat | Control | _ENSURE FULL PPE USAGE _STOP WORK IF PPE IS NOT CMPLIANT _SUPERVISION BY SITE ENGINEER | site engineer | 2026-05-02 | same day | 2026-05-02 | Low | Low | 1 | Close
Lack of PPE | Block-1 | General Area | Hafar albatin | HFR1-05-003 | Close | Threat | Internal | Safety / Quality | LACK OF PPE DURING WELDING WORK | EYE INJURY _electric shoock _TOXIC FUME | 5. Physical Injuries Welders face risks of burns, cuts, crushed fingers or toes, and musculoskeletal injuries from handling heavy components. | 2026-05-07 | 2026-05-07 | Ease | Imminent | High | High | 3 | PM | Treat | Control | _ENSURE FULL PPE USAGE _STOP WORK IF PPE IS NOT CMPLIANT _SUPERVISION BY SITE ENGINEER | site engineer | 2026-05-07 | same day | 2026-05-07 | Low | Low | 1 | Close
Site Condition | Block-1 & 2 | General Area | Hafar albatin | HFR1-05-003 | Close | Threat | External | Safety / Quality | WIND SPEED DUST | EYE INJURY_ POOR VISAIBILITY _HEALTH PROBLEMS | RESPIRATORY DIESEASES_TRANSPREATION ACCIDENTS | 2026-05-13 | 2026-05-13 | Moderate | Imminent | Very High | Very High | 4 | EXTERNAL | Treat | Control | STOP THE WORK _WEAR PROTECTIVE EQUPMENT_FOLLOW SAFETY INSTRUCTIONS | ALL TEAM | 2026-05-13 | same day | 2026-05-13 | Low | Low | 1 | Close
NOTES:
Risk Status: 1.Open, 2.Closed, or 3.Realized
T/O/I: 1.Threat, 2.Opportunity, or 3.Issue
Category (select 1):
1. Political
2. Legal, Regulatory, Compliance
3. Funding, Finance, Budget
4. Management, Governance, Policies, KPI, Performance
5. Human Resources | [21 empty] | `
6. Stakeholders, Authorities, Approvals, Permits
7. Requirements, Specifications, Scope, Procurement, Contract
8. Process, Tools, Technique, Technology
9. Design, Engineering
10. Construction, Execution
11. Testing, Commissioning, Handover
12. Operation, Maintenance
Risk Description (add all 3):
1. Source/Cause
2. Event = Threat, Opportunity, or Issue
3. Consequence/Effect
Risk Response Strategy for Threats: 1.Terminate, 2.Tolerate, 3.Transfer, or 4.Treat
Risk Response Strategy for Opportunities: 1.Ignore, 2.Share, or 3.Enhance/Exploit
Treatment Action: 1.Mitigate, 2.Control, or 3.Fall Back
Treatment Status: 1.Unapproved, 2.Active, or 3.Closed
Risk Level/Score: Likelihood x Highest Impact (Safety, Cost, Schedule, Environment, Quality, or Reputation. See Risk Scoring Matrix tab)

## CCO (hidden)
CONTRACT CHANGE ORDER (CCO)
CCO No. | Date Added | Description of Change | Status | SR | Sch Impact (Months) | Date Approved | Duration (days)
1 | 2024-06-09 | Replacement Soil Under Foundation | Pending | 192000 | 2 |  | -45452
| 2024-06-09 | Extra Excavation Quantity & Backfilling | Pending | 1580000

## Invoice Log
Weekly Progress Report - Invoice Log | [31 empty] | Y
Project Value | [8 empty] | Payment Status | [7 empty] | Invoices Summary | [9 empty] | Average Invoices durations |  |  |  |  | N
Original Contract Value |  |  | 16496855.87 |  | O&M Value |  | 0 | EAC | Advance Payment % |  | 10% |  | Advance Payment (SAR) |  | 1649685.587 |  | No of Submitted Invoices |  | 5 |  | Submitted Invoices (SAR) |  | 10687825.21 |  | Submiited Invoice Peroid | 2026-08-20 | CM / PgM Average Approval duration |  | 0 | Average Invoice Value | 2137565.042
Revised Contract Value |  | 21100000 | 16496855.87 | EAC | Revised O&M Value |  | 0 | #REF! | Retention % |  | 0% |  | Retention (SAR) |  | 0 |  | No of Approved Invoices (CM) |  | 5 |  | Approved Invoices (CM) (SAR) |  | 10687825.21 |  |  |  | MODON PM & Accounts Average Approval duration |  | #DIV/0!
Estimate At Completion Value |  | 20900000 | 16496855.87 | #REF! | Submitted Invoices (Gross Value) |  | 10687825.21 |  | Penalties and deduction % |  | 0.8547% |  | AP Recovery (SAR) |  | -1068782.521 |  | No of Approved Invoices (PM) |  | 0 |  | Approved Invoices (PM) (SAR) |  | 0 |  | Invoice Submitted Compared to Contract Value | 64.79% | Payments Average Duration |  | #DIV/0!
Potential Changes |  | 200000 | 0 |  | Total Deduction |  | -1209782.521 |  | Penalties and deduction (SAR) |  | -141000 |  | Retention Cumulative (SAR) |  | 0 |  | No of Paid Invoices |  | 0 |  | Paid Invoices (SAR) |  | 281548.46 |  |  |  | Invoices Average total Duration
Invoice Reference |  |  |  | Invoice Value |  |  |  |  | Period Covered |  | CM / PgM Approval Timeline |  |  |  | Modon PM & Accounts Approval | [6 empty] | Payment Status |  |  |  |  | Total Invoice Duration | Remarks
# | Invoice No. | Doc Control reference | Submittal Rev. # | Gross Value | AP Recovery | Retention | Deduction / Penalties | Amount (net) + VAT 15% | Start Date | End Date | Date to CM / PgM | CM / PgM Approval (Yes/No) | CM / PgM Reply Date | Days Elapsed | Date to PM | PM Approval (Yes/No) | PM Reply Date | Date to Accounts | Accounts Approval (Yes/No) | Accounts Approval Date | Days Elapsed | Date Paid | Amount Paid | Paid % | Payment Period (d) | Amount Pending
1 | 1 | HFR1-05-003-SAK-TS9-1-DSF-IPC-0001-00 | 0 | 281548.46 | -28154.846 | 0 | -30000 | 261402.6561 | 2025-11-18 | 2026-01-28 | 2026-02-02 | Y | 2026-02-02 | 0 | [8 empty] | 281548.46 | 100% |  | -20145.8039
2 | 2 | HFR1-05-003-SAK-TS9-1-DSF-IPC-0002-00 | 0 | 3060385.14 | -306038.514 | 0 | -100000 | 3067498.6199 | 2026-02-02 | 2026-05-09 | 2026-05-12 | Y | 2026-05-12 | 0 | [9 empty] | 0%
3 | 3 | HFR1-05-003-SAK-TS9-1-DSF-IPC-0003-00 | 0 | 3339046.68 | -333904.668 | 0 | -10000 | 3445913.3138 | 2026-05-13 | 2026-06-29 | 2026-07-01 | Y | 2026-07-01 | 0 | [9 empty] | 0%
4 | 4 | HFR1-05-003-SAK-TS9-1-DSF-IPC-0004-00 | 0 | 2061406.25 | -206140.625 | 0 | 0 | 2133555.4688 | 2026-06-30 | 2026-07-28 | 2026-07-29 | Y | 2026-07-29 | 0 | [9 empty] | 0%
5 | 5 | HFR1-05-003-SAK-TS9-1-DSF-IPC-0005-00 | 0 | 1945438.68 | -194543.868 | 0 | -1000 | 2012529.0338 | 2026-07-29 | 2026-08-20 | 2026-08-25 | Y | 2026-08-25 | 0 | [9 empty] | 0%
6 |  |  | 0
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
|  |  | TOTAL | 10687825.21 | -1068782.521 | 0 | -141000 | 10920899.0924 | [17 empty] | -20145.8039
Note on I3: Without O&M Cost
Note on B4: Without O&M Cost
Note on E4: Without O&M Cost

## Procurement
39045
|  | HFR1-05-03 | Procurement Log- Long Lead Items | [13 empty] | 2026-09-21
Sr. NO. | ACT # in P6 | Item Description | BOQ. No. | Unit | Quantity | Proc. Qty | Required P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Method of Shipping | Required on Job | E.D.A. to Site | A.D.A. to Site | Lead Time | Approval Status | Remarks
1 |  | Fire Pump (3 pumps) | 15.1.1 | Set | 1 | 1 | 17-01-2026 | 22-01-2026 |  | WILO | Truck |  | 31-5-2026 | 25-06-26 |  | Approval Status | Delivered
2 |  | Domestic-water packaged booster pumps (2 pumps | 15.2.7 | Set | 1 | 1 | 17-01-2026 | 22-01-2026 |  | Al Muhaidib | Truck |  | 31-3-2026 | 31-3-2026 |  | Approval Status | Delivered
3 |  | GRP Tanks (10x8x4m) (1 Tank) | 15.2.8 | Nos. | 1 | 1 | 17-01-2026 | 21-1-2026 |  | Al Muhaidib | Truck |  | 15-4-2026 | 15-4-26 |  | Approval Status | Delivered
4 |  | solar plant (24 Station) | 16.16 | Set | 24 | 24 | 17-01-2026 | 22-01-2026 |  | ASASYAT AL TAQA | Truck |  | 2026-05-25 | 2026-06-15 |  | Approval Status | Delivered
5 |  | panel boards (83 panel) | 16.8 | Nos. | 83 | 83 | 17-01-2026 | 22-01-2026 |  | ASCON | Truck |  | 2026-05-29 | 2026-06-20 |  | Approval Status | Delivered
6 |  | lighting system (415) | 16.1 | Nos | 415 | 415 | 17-01-2026 | 22-01-2026 |  | PAN | Truck |  | 30-5-2026 | 2026-10-06 |  | Approval Status | Delivered
7 |  | Steet lighting poles (33 pole) | 16.3.2 | Nos | 33 | 33 | 17-01-2026 | 22-01-2026 |  | Al Babtin | Truck |  | 15-4-2026 | 15-04-26 |  | Approval Status | Delivered
8 |  | Steel Structure | 5 | Nos | 2 | 2 | 17-01-2026 | 30-01-2026 |  | Kirby | Truck |  | 31-03-2026 | 31-03-26 |  | Approval Status | Delivered
9 |  | Sandwich Panel | 11.1.1 | Nos | 2 | 2 | 17-01-2026 | 30-01-2026 |  | BECOM | Truck |  | 30-04-2026 | 30-04-26 |  | Approval Status | Delivered
#REF!
Note on D9: HP:

## Manpower
Head-Count ( Non Manual)
MONTHS | 2025-01-07 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30
Plan - Monthly | [10 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Planned - Cumulative | [10 empty] | 12 | 24 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 120 | 132
Actual - Monthly | [10 empty] | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 10 | 10 | 10 | 10
Actual Cumulative | [10 empty] | 6 | 12 | 19 | 26 | 33 | 40 | 47 | 57 | 67 | 77 | 87
Forecast - Monthly
Saudi Monthly - Actual
Head-Count (Manual)
MONTHS | 2025-01-07 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30
Plan - Monthly | [10 empty] | 0 | 3 | 32 | 49 | 61 | 89 | 92 | 81 | 76 | 57 | 34
Planned - Cumulative | [10 empty] | 0 | 3 | 35 | 84 | 145 | 234 | 326 | 407 | 483 | 540 | 574
Actual - Monthly | [10 empty] | 15 | 21 | 22 | 30 | 35 | 51 | 54 | 67 | 57 | 63 | 58
Actual Cumulative | [10 empty] | 15 | 36 | 58 | 88 | 123 | 174 | 228 | 295 | 352 | 415 | 473
Forecast - Monthly | [10 empty] | 0 | 18 | 17 | 40 | 53 | 75 | 82 | 85 | 81 | 75 | 72
Saudi - Actual
Head-Count (Non-Manual) | [24 empty] | Month | 2026-09-30 | 2026-10-31
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff
12 | 10 |  | -2 |  | #N/A |  | 0
Head-Count (Manual) | [10 empty] | 12: Man Power by Trade
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff |  |  |  | 12: Key Trade; 36: General Labor; 60: Carpenter; 84: Plumber; 108: Operator; 132: Steel Fixer | Mason | Others | Total
34 | 58 |  | 24 |  | #N/A |  | 0 |  |  |  | 12: Plan; 36: 10; 60: 4; 84: 3; 108: 0; 132: 4 | 2 | 11 | 34
[11 empty] | 12: Actual; 36: 12; 60: 4; 84: 4; 108: 13; 132: 4 | 2 | 19 | 58
Equipment
MONTHS | 2025-01-07 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30
Plan - Monthly | [10 empty] | 0 | 11 | 18 | 18 | 23 | 24 | 26 | 22 | 17 | 16
Planned - Cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 29 | 47 | 70 | 94 | 120 | 142 | 159 | 175
Actual - Monthly | [10 empty] | 0 | 5 | 8 | 14 | 8 | 13 | 16 | 15 | 12 | 11 | 13
Actual Cumulative | 0 | 0 | 0 | 0 | [6 empty] | 0 | 5 | 13 | 27 | 35 | 48 | 64 | 79 | 91 | 102 | 115
Forecast - Monthly | [10 empty] | 48: 10; 60: 16; 72: 18; 84: 24; 96: 20; 108: 21
Equipment Count
Planned | Actual |  | Idle |  | Variance |  | Forecast Next Month
0 | 13 |  |  |  | 13 |  | #N/A
Type | Excavator | Fork lift | Loader | Dumper | Dozer | Grader | Dumper |  | Crane |  | 12: Grader; 36: Other; 60: Total
Plan | 0 | [9 empty] | 12: 0; 60: 0
Actual | 1 |  | 2 |  | 0 |  | 2 |  | 1 |  | 12: 1; 36: 6; 60: 13
Idle | [10 empty] | 60: 0

## Issues
[8 empty] | 2026-09-21 | Status | Responsibility
[9 empty] | Open | Contractor
[9 empty] | Closed | Consultant
Modon
Third Party
Other
Issue Log
Issue No | Date Identified | Issue Description | Responsibility | Action Taken | Current Status | Expected/Actual Closure | Duration Elapsed
1 | 14/06/2026 | Workers at height during lifting operations without proper coordination. | Contractor | Work sequence revised, lifting and work-at-height activities separated, supervision increased. | Closed | 14/06/2026 | 0 days
2 | 14/06/2026 | Workers were exposed to suspended load during lifting operations due to inadequate barricading and unsafe work positioning. | Contractor | Lifting activity stopped, exclusion zone established, barricades installed, workers relocated from the danger area, toolbox talk conducted, and tag lines provided. | Closed | 14/06/2026 | 0 days
3 | 14/06/2026 | Lack of proper isolation of lifting area. | Contractor | Barricades and warning signs installed, access restricted to authorized personnel only. | Closed | 14/06/2026 | 0 days
4 | 29-06-2026 | Poor House keeping obsered in work zone area | Contractor | Site house keeping team has been instruted to clean area immediately and maintain daily monitoring | Open | 2026-09-22
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Milestones
Milestones Factories Low-process Unit (HAFR Al Batin)
Item No. | Milestones | Original (Baseline) | Latest | Forecast |  | Days Change
| Contract Duration Current Contract Weeks : 43 of 57 | 43.2857 | 57 | 48 |  | 63 | 43 | 57
1 | Award Date | 2025-10-15 | 2025-10-15 | 2025-10-15 | A | 0
2 | Contract Sign Date | 2025-11-16 | 2025-11-16 | 2025-11-16 | A | 0
3 | Site Handover Date | 2025-11-27 | 2025-11-27 | 2025-11-27 | A | 0
4 | Complete Mobilization | 2025-12-28 | 2025-12-28 | 2025-12-28 | A | 0
5 | Complete Existing Condition Surveying Final Report | 2026-09-14 | 2026-09-14 | 2026-09-14 | A | 0
6 | Complete Submittals and place order for all Log lead items | 2026-07-22 | 2026-11-08 | 2026-09-17 | F | 52
7 | Complete Earthworks | 2026-03-22 | 2026-04-04 | 2026-04-04 | F | 0
8 | Complete Civil & Arch Works | 2025-07-16 | 2026-11-14 | 2026-10-11 | F | 34
9 | Complete Electrical Works | 2025-09-02 | 2026-11-07 | 2026-10-17 | F | 21
10 | Complete Mechanical Works | 2025-09-26 | 2026-12-02 | 2026-10-29 | F | 34
11 | Complete Finishing Works | 2026-09-26 | 2026-11-29 | 2026-10-29 | F | 31
12 | Project Handover | 2026-09-26 | 2026-12-28 | 2026-11-07 | F | 51

## Schedule
Primavera P6 Schedule Status | [9 empty] | Data Date | 2026-09-21
Project Activities Overview
Schedule Statistics |  |  |  |  | Active Schedule Activities
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag
902 | 9 | 40 | 854 | 94.68% | 40 | 29 | 14 | 15 | 28
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities
|  |  | Greater Than 14 Days |  | Less Than 14 Days
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag
12 | 2 | 10 | 41 | 41 | -80 | -36 | 11 | 10 | 1

## EV-Chart Data
| 16496855.85 |  |  | 0
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Value |  |  | Gross Paid Value |  |  | Forecast |  |  | Actual/Fcst vs Plan
Month | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | C um |  | Month | Cum
2025-11-30 | 0 | 0 | 0% |  |  |  | 0 | 0 |  | 1649686 | 1649686 | 10% |  |  |  | 0 | 0 | Actuals thru previous month
2025-12-31 | 1728 | 1728 | 0.01047% |  |  |  | 1296 | 1296 | 0.007856% | 0 | 1649686 | 10% |  |  |  | 1728 | 1728
2026-01-31 | 888056.73 | 889784.73 | 5.394% |  |  |  | 1023867.84 | 1025163.84 | 6.214% | 0 | 1649686 | 10% |  |  |  | 868988.57 | 870716.57
2026-02-28 | 489987.12 | 1379771.85 | 8.364% |  |  |  | 966393.4 | 1991557.24 | 12.07% | 281548.46 | 1931234.46 | 11.71% |  |  |  | 403522.29 | 1274238.85
2026-03-31 | 2766054.64 | 4145826.5 | 25.13% |  |  |  | 1973028.2 | 3964585.44 | 24.03% |  | 1931234.46 | 11.71% |  |  |  | 847257.56 | 2121496.41 | Forecast current and future months
2026-04-30 | 4776280.72 | 8922107.22 | 54.08% |  |  |  | 4610932.87 | 8575518.31 | 51.98% |  | 1931234.46 | 11.71% |  |  |  | 1296097.17 | 3417593.58
2026-05-31 | 2330404.74 | 11252511.96 | 68.21% |  |  |  | 2078708.68 | 10654226.99 | 64.58% | 3060385.14 | 4991619.6 | 30.26% |  |  |  | 3819096.85 | 7236690.43
2026-06-30 | 2174640.66 | 13427152.63 | 81.39% |  |  |  | 1655276.04 | 12309503.03 | 74.62% |  | 4991619.6 | 30.26% |  |  |  | 2936216.4 | 10172906.83
2026-07-31 | 1335002.18 | 14762154.81 | 89.48% |  |  |  | 1531594.26 | 13841097.29 | 83.9% | 5400452.93 | 10392072.53 | 62.99% | 1691078.59 | 11863985.42 | 71.92% | 1691078.59 | 11863985.42
2026-08-31 | 688239.89 | 15450394.7 | 93.66% |  |  |  | 1349687.61 | 15190784.9 | 92.08% | 1945438.68 | 12337511.21 | 74.79% | 764534.42 | 12628519.85 | 76.55% | 764534.42 | 12628519.85
2026-09-30 | 1046461.17 | 16496855.87 | 100% |  |  |  | 1004675.16 | 16195460.06 | 98.17% |  |  |  | 1238797.41 | 13867317.25 | 84.06% | 1238797.41 | 13867317.25
2026-10-31 | [12 empty] | 501575.85 | 14368893.1 | 87.1% | 501575.85 | 14368893.1
2026-11-30 | [12 empty] | 729132.18 | 15098025.29 | 91.52% | 729132.18 | 15098025.29
2026-12-31 | [12 empty] | 540629.41 | 15638654.7 | 94.8% | 540629.41 | 15638654.7
2027-01-31 | [12 empty] | 822014.02 | 16460668.72 | 99.78% | 822014.02 | 16460668.72
2027-02-28 | [12 empty] | 24374.35 | 16496855.87 | 100% | 24374.35 | 16496855.87
2027-03-31
2027-04-30
2027-05-31 | [18 empty] | Extended Duration
2027-06-30
2027-07-31
2027-08-31
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.

## Physical-Chart Data
| 146581 |  |  | 0
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Effort % |  |  | Forecast |  |  | Achieved/Fcst vs Plan
Week | Monthly Effort | Cum Effort | Plan Wt.% | Weekly Effort | Cum Effort | Plan Wt.% | Weekly Wt. | Cum Wt. | Achieved Wt.% | Monthly Wt. | Cum Wt. | Wt.% | Weekly Wt. | Cum Wt.
2025-11-30 | 549 | 549 | 0.3745% |  |  |  | 619 | 619 | 0.4223% |  |  |  | 549 | 549 |  | Actuals thru previous month
2025-12-31 | 6943 | 7492 | 5.111% |  |  |  | 5550 | 6169 | 4.209% |  |  |  | 4614 | 5163
2026-01-31 | 7784 | 15276 | 10.42% |  |  |  | 8771 | 14940 | 10.19% |  |  |  | 5234 | 10397
2026-02-28 | 7274 | 22550 | 15.38% |  |  |  | 10438 | 25377 | 17.31% |  |  |  | 5706 | 16103
2026-03-31 | 20730 | 43280 | 29.53% |  |  |  | 23648 | 49025 | 33.45% |  |  |  | 6829 | 22933 |  | Forecast current and future months
2026-04-30 | 27867 | 71147 | 48.54% |  |  |  | 22229 | 71254 | 48.61% |  |  |  | 7293 | 30226
2026-05-31 | 19580 | 90727 | 61.9% |  |  |  | 12856 | 84111 | 57.38% |  |  |  | 25240 | 55466
2026-06-30 | 18520 | 109247 | 74.53% |  |  |  | 12562 | 96673 | 65.95% |  |  |  | 21959 | 77425
2026-07-31 | 22171 | 131418 | 89.66% |  |  |  | 18239 | 114912 | 78.39% | 16479 | 93904 | 64.06% | 16479 | 93904
2026-08-31 | 6310 | 137728 | 93.96% |  |  |  | 17361 | 132273 | 90.24% | 14977 | 108881 | 74.28% | 14977 | 108881
2026-09-30 | 8853 | 146580 | 100% |  |  |  | 11399 | 143672 | 98.02% | 12223 | 121104 | 82.62% | 12223 | 121104
2026-10-31 | [9 empty] | 6406 | 127509 | 86.99% | 6406 | 127509
2026-11-30 | [9 empty] | 6160 | 133669 | 91.19% | 6160 | 133669
2026-12-31 | [9 empty] | 5939 | 139608 | 95.24% | 5939 | 139608
2027-01-31 | [9 empty] | 5742 | 145350 | 99.16% | 5742 | 145350
2027-02-28 | [9 empty] | 1230 | 146580 | 100% | 1230 | 146580
2027-03-31
2027-04-30
2027-05-31 | [16 empty] | Extended Duration
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
Activity ID | Activity Name | Original Duration | Activity Count | BL Project Start | BL Project Finish | Start | Finish | Budgeted Total Cost | Schedule % Complete | Performance % Complete | Planned Value Cost | Earned Value Cost | Spreadsheet Field | 2024-01-07 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31
Total |  | 623.25 | 1116 | 2024-01-07 | 46028 | 07-Jan-24 A | 46062 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Estimate At Completion Cost |  | 89262.65 | 1911931.82 | 282648.53 | 246858.68 | 564120.09 | 1772932.97 | 2179308.35 | 4118493.87 | 2271044.62 | 1437956.02 | 2452392.69 | 3948810.12 | 2512836.57 | 363490.57 | 762209.57 | 1242485.79 | 856531.3 | 1697232.2 | 1294517.64 | 969126.01 | 1701986.37 | 3605162.36 | 7624604.71 | 1187731.59
Total |  | 623.25 | 1116 | 2024-01-07 | 46028 | 07-Jan-24 A | 46062 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Cum Estimate At Completion Cost |  | 89262.65 | 2001194.47 | 2283843 | 2530701.69 | 3094821.78 | 4867754.74 | 7047063.1 | 11165556.97 | 13436601.59 | 14874557.61 | 17326950.3 | 21275760.41 | 23788596.99 | 24152087.56 | 24914297.13 | 26156782.92 | 27013314.22 | 28710546.42 | 30005064.06 | 30974190.07 | 32676176.44 | 36281338.81 | 43905943.51 | 45093675.1 | 45093675.1
Total |  | 623.25 | 1116 | 2024-01-07 | 46028 | 07-Jan-24 A | 46062 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Estimate At Completion - Labor Units | 4258.35 | 5320.49 | 12033.87 | 66595.68 | 6938 | 7946 | 20793.2 | 18887.2 | 21579.2 | 20134 | 28380 | 42502 | 49328 | 28920 | 7224 | 12504 | 17584 | 13032 | 19312 | 18744 | 18792 | 30416 | 28632 | 17200 | 4192 | 400
Total |  | 623.25 | 1116 | 2024-01-07 | 46028 | 07-Jan-24 A | 46062 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Cum Estimate At Completion - Labor Units | 4258.35 | 9578.83 | 21612.7 | 88208.38 | 95146.38 | 103092.38 | 123885.58 | 142772.78 | 164351.98 | 184485.98 | 212865.98 | 255367.98 | 304695.98 | 333615.98 | 340839.98 | 353343.98 | 370927.98 | 383959.98 | 403271.98 | 422015.98 | 440807.98 | 471223.98 | 499855.98 | 517055.98 | 521247.98 | 521647.98
Total |  | 623.25 | 1116 | 2024-01-07 | 2026-01-06 | 07-Jan-24 A | 2026-02-09 | 45093675 | 2.35% | 0.0414 | 105921808% | 186653732% | Budgeted Nonlabor Units | 1189.42 | 606.15 | 1737.15 | 2072.51 | 2091.06 | 3593.36 | 8082.69 | 6901.86 | 7849.97 | 7596.16 | 11505.04 | 17236.09 | 19232.06 | 10689.79 | 2811.98 | 3986.21 | 5583.06 | 3727.36 | 5367.49 | 5301.62 | 4827.08 | 7285.19 | 7781.94 | 5113.74 | 1176 | 168
Formulas:
Week = EOMONTH([Week, row above],1)

## Testing
Testing and Commissioning
Item | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
Test For Roads | 2026-09-13 | 2026-09-26 | 2026-06-23 | 2027-01-14 | 2026-06-23
Test For Electrical Works | 2026-09-03 | 2026-09-16 | 2026-06-22 | 2027-02-01 | 2026-06-22
T&C Water Supply System | 2025-04-01 | 2026-04-14 | 2026-04-26 | 2026-08-04 | 2026-04-26
T&C Fire Fighting System | 2026-09-03 | 2026-09-16 | 2026-06-14 | 2026-12-12 | 2026-06-14
T&C HVAC System | 2026-09-03 | 2026-09-16 | 2026-07-15 | 2026-12-18 | 2026-06-14
T&C Pumps System | 2025-07-21 | 2026-08-03 | 2026-06-14 | 2026-12-12 | 2026-06-14
Test For Water Utilities | 2025-04-01 | 2026-04-14 | 2026-04-26 | 2026-08-04 | 2026-04-26
Total | 2025-04-01 | 2026-09-26 | 2026-04-26 | 2027-02-01 | 2026-04-26 | 0 | #DIV/0! | 0 | 0
Formulas:
Planned Start Date = MIN(B3:[Planned Start Date, row above])
Planned Finish Date = MAX(C3:[Planned Finish Date, row above])
Forecast Start Date = MIN(D3:[Forecast Start Date, row above])
Forecast Finish Date = MAX(E3:[Forecast Finish Date, row above])
Actual Start Date = IFERROR(MIN(F3:[Actual Start Date, row above]),"")
Actual Finish Date = IFERROR(MAX(G3:[Actual Finish Date, row above]),"")

## FIR from Begining up to date
Project Name | Factories Low-process Unit (HAFR Al Batin)
Project ID | HFR1-05-03 |  |  | Project Budget |  | 16496855.87
Total FIR Approved Value (Cumulative) |  |  | 11743680.0968 | Remaining FIRs Value (Cumulative) |  | 4753175.7732
Date Period |  |  | 2025-11-27 | To |  | 2026-09-21
BOQ Item # | BOQ Description | FIR / DATE | FIR # | FIR Description | Status | Unit Rate | Current Period Quantity | Progress (%) | Total (SAR) | Remarks
7.3 | Supply and apply anti termite under all concrete in touch with earth for all buildings as per manufacture instructions, engineer approval | 2026-01-06 | HFR1-05-003-SAK-TS9-1-FIR-STU-0001-00 | Supply and apply anti-termite for lean concrete under footing B1 as shown attached drawing | Approved | 7 | 313.15 | 100% | 2192.05
7.2 | Supply and lay 250 micron thk polyethylene sheet under grade slab and footings | 2026-01-06 | HFR1-05-003-SAK-TS9-1-FIR-STU-0002-00 | Supply and install 250 micron polyethylene sheet under lean concrete for footing B1 | Approved | 6 | 313.15 | 100% | 1878.9
3.1.1 | Lean concrete under foundation and grade beams. | 2026-01-07 | HFR1-05-003-SAK-TS9-1-FIR-STU-0003-00 | Form work for Lean Concrete For Isolated Footing For Block 1 | Approved | 42 | 313.15 | 100% | 13152.3
3.2.1 | Cast in place reinforced concrete (Isolated Footing) | 2026-01-07 | HFR1-05-003-SAK-TS9-1-FIR-STU-0004-00 | Pouring Concrete For Isolated Footing For Block 1 | Approved | 862 | 64.39 | 100% | 55504.18
7.3 | Supply and apply anti termite under all concrete in touch with earth for all buildings as per manufacture instructions, engineer approval | 2026-01-07 | HFR1-05-003-SAK-TS9-1-FIR-STU-0005-00 | Supply and apply anti-termite for lean concrete under footing B1 as shown attached drawing | Approved | 7 | 313.15 | 100% | 2192.05
7.2 | Supply and lay 250 micron thk polyethylene sheet under grade slab and footings | 2026-01-07 | HFR1-05-003-SAK-TS9-1-FIR-STU-0006-00 | Supply and install 250 micron polyethylene sheet under lean concrete for footing B2 | Approved | 6 | 313.15 | 100% | 1878.9
3.1.1 | Lean concrete under foundation and grade beams. | 2026-01-07 | HFR1-05-003-SAK-TS9-1-FIR-STU-0008-00 | Pouring Lean Concrete For Isolated Footing For Block 1 | Approved | 42 | 313.15 | 100% | 13152.3
3.2.1 | Cast in place reinforced concrete (Isolated Footing) | 2026-01-13 | HFR1-05-003-SAK-TS9-1-FIR-STU-0011-00 | Pouring Concrete For Isolated Footing For Block 1 | Approved | 862 | 46.08 | 100% | 39720.96
3.2.1 | Cast in place reinforced concrete (Isolated Footing) | 2026-01-18 | HFR1-05-003-SAK-TS9-1-FIR-STU-0014-00 | Pouring Concrete For Isolated Footing For Block 2 | Approved | 862 | 51.36 | 100% | 44272.32
3.2.1 | Cast in place reinforced concrete (Isolated Footing) | 2026-01-19 | HFR1-05-003-SAK-TS9-1-FIR-STU-0015-00 | Pouring Concrete For Isolated Footing For Block 2 | Approved | 862 | 59.1 | 100% | 50944.2
3.2.4 | Cast in place reinforced concrete (Pedstel) | 2026-01-24 | HFR1-05-003-SAK-TS9-1-FIR-STU-0018-00 | Pouring Concrete NeckColumn (Pedstel) For Block 1 | Approved | 1218 | 36.11 | 100% | 43981.98
3.2.4 | Cast in place reinforced concrete (Pedstel) | 2026-01-29 | HFR1-05-003-SAK-TS9-1-FIR-STU-0021-00 | Pouring Concrete NeckColumn (Pedstel) For Block 2 | Approved | 1218 | 34.18 | 100% | 41631.24
7.1 | Provide and apply 2 coats of bitumen waterproofing paint on concrete surface in contact with soil | 2026-01-31 | HFR1-05-003-SAK-TS9-1-FIR-STU-0022-00 | Apply 2 coats of bitumen waterproofing paint on concrete surface in contact with soil.for footing & neck columns for block 1 & block 2 | Approved | 20 | 1286.09 | 100% | 25721.8
7.3 | Supply and apply anti termite under all concrete in touch with earth for all buildings as per manufacture instructions, engineer approval | 2026-02-11 | HFR1-05-003-SAK-TS9-1-FIR-STU-0023-00 | Supply and apply anti-termite under footing for pump room | Approved | 7 | 22.57 | 100% | 157.99 |  | 157.99
7.3 | Supply and apply anti termite under all concrete in touch with earth for all buildings as per manufacture instructions, engineer approval | 2026-02-11 | HFR1-05-003-SAK-TS9-1-FIR-STU-0024-00 | Supply and apply anti-termite under grade beams for B1 | Approved | 7 | 130.94 | 100% | 916.58 |  | 916.58
7.3 | Supply and apply anti termite under all concrete in touch with earth for all buildings as per manufacture instructions, engineer approval | 2026-02-22 | HFR1-05-003-SAK-TS9-1-FIR-STU-0025-00 | Supply and apply anti-termite under grade beams for B2 | Approved | 7 | 130.94 | 100% | 916.58 |  | 916.58
7.2 | Supply and lay 250 micron thk polyethylene sheet under grade slab and footings | 2026-02-12 | HFR1-05-003-SAK-TS9-1-FIR-STU-0026-00 | Supply and install 250 micron polyethylene sheet under footing for pump room | Approved | 6 | 22.57 | 100% | 135.42 |  | 135.42
7.2 | Supply and lay 250 micron thk polyethylene sheet under grade slab and footings | 2026-02-11 | HFR1-05-003-SAK-TS9-1-FIR-STU-0027-00 | Supply and install 250 micron polyethylene sheet under grade beams for B1 | Approved | 6 | 130.94 | 100% | 785.64
7.2 | Supply and lay 250 micron thk polyethylene sheet under grade slab and footings | 2026-02-23 | HFR1-05-003-SAK-TS9-1-FIR-STU-0028-00 | Supply and install 250 micron polyethylene sheet under grade beams for B2 | Approved | 6 | 130.94 | 100% | 785.64 |  | 2126.57
3.1.1 | Lean concrete under foundations and grade beams. | 2026-02-12 | HFR1-05-003-SAK-TS9-1-FIR-STU-0032-00 | Pouring Lean Concrete For For Pump Room | Approved | 42 | 22.57 | 100% | 947.94
3.1.1 | Lean concrete under foundations and grade beams. | 2026-02-23 | HFR1-05-003-SAK-TS9-1-FIR-STU-0033-00 | Pouring Lean Concrete For grade beams For Block 2 | Approved | 42 | 130.94 | 100% | 5499.48 |  | 0.01289%
3.1.1 | Lean concrete under foundations and grade beams. | 2026-02-12 | HFR1-05-003-SAK-TS9-1-FIR-STU-0034-00 | Pouring Lean Concrete For grade beams For Block 1 | Approved | 42 | 130.94 | 100% | 5499.48
3.2.2 | Cast in place reinforced concrete (grade beams) | 2026-01-24 | HFR1-05-003-SAK-TS9-1-FIR-STU-0039-00 | Pouring Concrete For grade beams For Block 2 | Approved | 988 | 10.12 | 100% | 9998.56
3.2.2 | Cast in place reinforced concrete (grade beams) | 2026-01-15 | HFR1-05-003-SAK-TS9-1-FIR-STU-0040-00 | Pouring Concrete For grade beams For Block 1 | Approved | 988 | 10.12 | 100% | 9998.56
3.2.1 | Cast in place reinforced concrete (Isolated Footing) | 2026-02-14 | HFR1-05-003-SAK-TS9-1-FIR-STU-0043-00 | Pouring Concrete For Isolated Footing For Pump room | Approved | 862 | 8.28 | 100% | 7137.36
3.2.4 | Cast in place reinforced concrete (Pedstel) | 2026-02-17 | HFR1-05-003-SAK-TS9-1-FIR-STU-0045-00 | Pouring Concrete for NeckColumn (Pedstel) For pump room | Approved | 1218 | 1.73 | 100% | 2107.14
3.2.2 | Cast in place reinforced concrete (grade beams) | 2026-03-05 | HFR1-05-003-SAK-TS9-1-FIR-STU-0062-00 | Pouring Concrete For grade beams For Block 1 As Shown As Drawing Attachement | Approved | 988 | 42.25 | 100% | 41743
3.2.2 | Cast in place reinforced concrete (grade beams) | 2026-03-10 | HFR1-05-003-SAK-TS9-1-FIR-STU-0067-00 | Pouring Concrete For grade beams For Block 2 As Shown As Drawing Attachement | Approved | 988 | 42.25 | 100% | 41743
3.2.4 | Cast in place reinforced concrete (Pedstel) | 2026-03-05 | HFR1-05-003-SAK-TS9-1-FIR-STU-0054-00 | Pouring Concrete for NeckColumn (Pedstel) For Block 1 | Approved | 1218 | 11.52 | 100% | 14031.36
3.2.4 | Cast in place reinforced concrete (Pedstel) | 2026-03-10 | HFR1-05-003-SAK-TS9-1-FIR-STU-0045-00 | Pouring Concrete for NeckColumn (Pedstel) For Block 2 | Approved | 1218 | 11.52 | 100% | 14031.36
7.3 | Supply and apply anti termite under all concrete in touch with earth for all buildings as per manufacture instructions, engineer approval | 2026-03-23 | HFR1-05-003-SAK-TS9-1-FIR-STU-0079-00 | Supply and Apply Anti-Termite For Under lean concrete footing GRP as shown attached drawing | Approved | 7 | 139.26 | 100% | 974.82
7.2 | Supply and lay 250 micron thk polyethylene sheet under grade slab and footings | 2026-03-23 | HFR1-05-003-SAK-TS9-1-FIR-STU-0080-00 | Supply and lay 250 micron thk polyethylene sheet lean concrete footing GRP as shown attached drawing | Approved | 6 | 139.26 | 100% | 835.56
3.1.1 | Lean concrete under foundations and grade beams. | 2026-03-24 | HFR1-05-003-SAK-TS9-1-FIR-STU-0081-00 | Pouring Lean Concrete For Under GRP Tank Foundation | Approved | 42 | 139.26 | 100% | 5848.92
3.3 | Provide and cast 150 mm thk concrete floor slab on grade with steel fiber including but not limited to construction joints, control joints, as per drawings and specification and as per the supplier design and the Engineer's Instructions. | 2026-05-03 | FIR -HFR1-05-003-SAK-TS9-1-FIR-STU-0155-00 | Pouring of Steel Fiber Concrete for SOG at Block No.01 as per attached highlighted drawing | Approved | 990 | 279.68 | 100% | 276883.2
3.3 | Provide and cast 150 mm thk concrete floor slab on grade with steel fiber including but not limited to construction joints, control joints, as per drawings and specification and as per the supplier design and the Engineer's Instructions. | 2026-05-03 | FIR -HFR1-05-003-SAK-TS9-1-FIR-STU-0157-00 | Pouring of Steel Fiber Concrete for SOG at Block-2 as per attached highlighted drawing | Approved | 990 | 279.68 | 100% | 276883.2
7.1 | Provide and apply 2 coats of bitumen waterproofing paint on concrete surface in contact with soil | 2026-03-01 | FIR -HFR1-05-003-SAK-TS9-1-FIR-STU-0153-00 | Provide and apply 2 coats of bitumen waterproofing paint Grade Beam & tie beam Block-2 as per attached highlighted drawing. | Approved | 20 | 1047.48 | 100% | 20949.6
7.1 | Provide and apply 2 coats of bitumen waterproofing paint on concrete surface in contact with soil | 2026-02-13 | FIR-HFR1-05-003-SAK-TS9-1-FIR-STU-0119-00 | Apply 2 coats of bitumen waterproofing paint on concrete or footing, Pedestals and Grade beams of Pump Shed | Approved | 20 | 86.16 | 100% | 1723.2
7.2 | Supply and lay 250 micron thk polyethylene sheet under grade slab and footings | 2026-05-03 | FIR -HFR1-05-003-SAK-TS9-1-FIR-STU-00154-00 | Supply and lay 250-micron thick polyethylene sheet at block-1 SOG (as per attached highlighted drawing) | Approved | 6 | 1825.91 | 100% | 10955.46
7.2 | Supply and lay 250 micron thk polyethylene sheet under grade slab and footings | 2026-05-03 | FIR -HFR1-05-003-SAK-TS9-1-FIR-STU-00156-00 | Supply and lay 250-micron thick polyethylene sheet at block-2 SOG (as per attached highlighted drawing) | Approved | 6 | 1825.91 | 100% | 10955.46
7.2 | Supply and lay 250 micron thk polyethylene sheet under grade slab and footings | 2026-04-26 | FIR -HFR1-05-003-SAK-TS9-1-FIR-STU-00161-00 | Supply and lay 250-micron thick polyethylene sheet at bathroom & Electrical room (Axis-A-N-1x3) as per attached highlighted drawing. | Approved | 6 | 38.4 | 100% | 230.4
7.3 | Supply and apply anti termite under all concrete in touch with earth for all buildings as per manufacture instructions, engineer approval | 2026-05-03 | FIR -HFR1-05-003-SAK-TS9-1-FIR-STU-00158-00 | Supply and apply anti termite at SOG Block-2 as per attached highlighted drawing. | Approved | 7 | 1825.91 | 100% | 12781.37
7.3 | Supply and apply anti termite under all concrete in touch with earth for all buildings as per manufacture instructions, engineer approval | 2026-05-03 | FIR -HFR1-05-003-SAK-TS9-1-FIR-STU-00159-00 | Supply and apply anti termite at SOG Block-1 as per attached highlighted drawing. | Approved | 7 | 1825.91 | 100% | 12781.37
7.3 | Supply and apply anti termite under all concrete in touch with earth for all buildings as per manufacture instructions, engineer approval | 2026-04-29 | FIR -HFR1-05-003-SAK-TS9-1-FIR-STU-00160-00 | Supply and apply anti termite at bathroom, Prayer room & Electrical room Block-1 as per attached highlighted drawing. | Approved | 7 | 38.4 | 100% | 268.8
11.1.1 | Supply and install the PEB for one block with an area 1990 square meter. The PEB Steel structure shall include epoxy painted 150 micron, and shall fully comply with drawings and specifications; | 2026-04-29 | FIR -HFR1-05-003-SAK-TS9-1-FIR-STU-00148-00 | Supply and install Column Beam And Purlins the PEB for two blocks | Approved | 950000 | 1 | 50% | 475000
15.3.1.1 | Sewage tank with dimensions (8x4x3m) | 2026-02-10 | HFR1-05-003-SAK-TS9-1-FIR-STU-0090-00 | Excavation for Tank Footing and Walls As Shown Drawing Attachments. | Approved | 82500 | 1 | 5% | 4125
15.3.1.1 | Sewage tank with dimensions (8x4x3m) | 2026-03-15 | HFR1-05-003-SAK-TS9-1-FIR-STU-0101-00 | Pouring Reinforcement concrete for Septic Tank Footing As Shown Drawing Attachments. | Approved | 82500 | 1 | 15% | 12375
15.3.1.1 | Sewage tank with dimensions (8x4x3m) | 2026-03-18 | HFR1-05-003-SAK-TS9-1-FIR-STU-0105-00 | Pouring Reinforcing concrete for Septic Tank Walls As Shown Drawing Attachments. | Approved | 82500 | 1 | 20% | 16500
15.3.1.1 | Sewage tank with dimensions (8x4x3m) | 2026-03-20 | HFR1-05-003-SAK-TS9-1-FIR-STU-0109-00 | Pouring Reinforcing concrete for Septic Tank Ceiling Slab As Shown Drawing Attachments. | Approved | 82500 | 1 | 20% | 16500
15.3.1.1 | Sewage tank with dimensions (8x4x3m) | 2026-05-03 | HFR1-05-003-SAK-TS9-1-FIR-STU-0163-00 | Supply and Install Backfilling for Sewage tank with dimensions (8x4x3m) | Approved | 82500 | 1 | 20% | 16500
16.2.7 | pipes for all telecom network at site | 2026-03-25 | HFR1-05-003-SAK-TS9-1-FIR-ELE-003-00 | Installation PIPES FOR TELECOMMUNICATION NETWORK HDPE 32MM | Approved | 103 | 600.14 | 100% | 61814.42
16.2.8 | pipes for all electrical network at site | 2026-05-03 | HFR1-05-003-SAK-TS9-1-FIR-ELE-0002-00 | Supply and Install pipes for all electrical network at site | Approved | 103 | 1209.34 | 100% | 124562.02
15.3.2.1 | 160 mm Pipe in trench not exceeding 2.00 m depth to invert | 2026-04-29 | HFR1-03-005-SAK-TS9-1-FIR-Mech-0005-00 | Supply and Install 160 mm Pipe in trench not exceeding 2.00 m depth to invert | Approved | 440 | 348.06 | 45% | 68915.88
15.3.3.1 | Manholes | 2026-04-29 | HFR1-05-003-SAK-TS9-1-FIR-STU-0124-00 | Supply and Install Manholes | Approved | 3850 | 21 | 60% | 48510
15.6.1.1 | Supply, install, test and commission uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification, Ø 4" | 2026-04-19 | FIR -HFR1-05-003-SAK-TS9-1-FIR-Mech-0003-00 | Excavation , bedding , installation and leak test of Plumbing drainage Pipes inside toilets for B1,B2 | Approved | 121 | 382.7 | 80% | 37045.36
15.6.1.3 | Supply, install, test and commission uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification, Ø 2" | 2026-04-19 | FIR -HFR1-05-003-SAK-TS9-1-FIR-Mech-0003-00 | Excavation , bedding , installation and leak test of Plumbing drainage Pipes inside toilets for B1,B2 | Approved | 61 | 124.32 | 80% | 6066.816
15.6.1.1 | Supply, install, test and commission uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification, Ø 4" | 2026-04-19 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0046-00 | Excavation , bedding , installation and leak test of Plumbing drainage Pipes inside toilets for B1,B2 | Approved | 121 | 382.7 | 20% | 9261.34
15.6.1.2 | Supply, install, test and commission uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification, Ø 3" | 2026-04-19 | FIR -HFR1-05-003-SAK-TS9-1-FIR-Mech-0004-00 | Excavation , bedding , installation and leak test of Plumbing drainage Pipes inside toilets for B1,B2 | Approved | 77 | 69.08 | 80% | 4255.328
15.6.1.3 | Supply, install, test and commission uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification, Ø 2" | 2026-04-19 | FIR -HFR1-05-003-SAK-TS9-1-FIR-Mech-0004-00 | Excavation , bedding , installation and leak test of Plumbing drainage Pipes inside toilets for B1,B2 | Approved | 61 | 103.32 | 80% | 5042.016
15.6.1.4 | Supply, install, test and commission uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification, Ø 1" | 2026-04-19 | HFR1-03-005-SAK-TS9-1-FIR-Mech-0003-00 | Install & test of uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification , Ø 1" | Approved | 44 | 458.88 | 80% | 16152.576
15.2.1.2 | Supply and installation of HDPE PE 100 PN16 pipes, for cold water supply piping system (underground) as specified on drawings and documents, 90 mm Ø | 2026-04-29 | FIR -HFR1-05-003-SAK-TS9-1-FIR-Mech-0006-00 | installation of HDPE PE 100 PN16 Pipes 90mm as attached AS SHOWN ATTACHED DRAWING. | Approved | 143 | 471.5 | 42% | 28318.29
15.2.1.4 | Supply and installation of HDPE PE 100 PN16 pipes, for cold water supply piping system (underground) as specified on drawings and documents, 50 mm Ø | 2026-04-29 | FIR -HFR1-05-003-SAK-TS9-1-FIR-Mech-0007-00 | Installation of HDPE PE 100 PN16 Pipes 50mm AS SHOWN ATTACHED DRAWING. | Approved | 99 | 123.12 | 36% | 4387.9968
3.2.5 | Concrete Pad | 2026-05-03 | HFR1-05-003-SAK-TS9-1-FIR-STU-0175-00 | Pouring Concrete for Concrete Pads as per attached highlighted drawing. | Approved | 891 | 3.21 | 100% | 2860.11
11.1.5 | Pump Shed | 2026-05-07 | HFR1-05-003-SAK-TS9-1-FIR-STU-0176-00 | Supply and install shed pump | Approved | 57200 | 1 | 100% | 57200
15.2.8.1 | Hot Press GRP Sectional Panel Water Tanks (10x8x4m) | 2026-05-07 | HFR1-05-003-SAK-TS9-1-FIR-STU-0177-00 | Supply and install GRP Tank | Approved | 275000 | 1 | 50% | 137500
16.2.4 | Complete Main Electrical Manhole with pipes | 2026-04-26 | HFR1-05-003-SAK-TS9-1FIR-STU-0183-00 | Excavation and pouring foundation and pouring walls for main electrical manholes | Approved | 12115 | 4.2 | 100% | 50883
16.2.5 | Complete Branch Electrical Manhole with pipes | 2026-04-30 | HFR1-05-003-SAK-TS9-1FIR-STU-0184-00 | EXCAVATION AND POURING FOUNDATION AND POURING WALLS FOR BRANCH ELECTRICAL MANHOLES | Approved | 3617 | 26 | 60% | 56425.2
16.2.10 | Complete road crossing duct bank for site electrical cables including pipes | 2026-05-09 | FIR -HFR1-05-003-SAK-TS9-1FIR-ST-00198-00 | Pouring Concrete of Duct bank for electrical cable including pipes as per attached highlighted drawing. | Approved | 907 | 163.62 | 100% | 148403.34
16.2.11 | Complete road crossing duct bank for site telecom cables including pipes | 2026-05-07 | FIR -HFR1-05-003-SAK-TS9-1FIR-ST-00205-00 | Pouring Concrete of Duct bank for site telecom cables including pipes as per attached highlighted drawing. | Approved | 294 | 636.62 | 100% | 187166.28
4.1.1 | at internal walls (100mm thick) | 2026-05-12 | FIR -HFR1-05-003-SAK-TS9-1-FIR-ARC-00001-00 | Supply and install CMU Block for internal walls (100mm thick) for Bathroom & Entrance Area Grid#(A-N\1-3) as per attached highlighted drawing. | Approved | 70 | 22.32 | 90% | 1406.16
4.1.2 | at internal walls (200mm thick) | 2026-05-12 | FIR -HFR1-05-003-SAK-TS9-1FIR-ARC-00002-00 | Supply and install CMU Block for internal walls (200mm thick) for Bathroom & Entrance Area Grid#(A-N\1-3) as per attached highlighted drawing. | Approved | 84 | 169.86 | 90% | 12841.416
4.1.3 | at external walls (200mm thick insulated) | 2026-05-12 | FIR -HFR1-05-003-SAK-TS9-1FIR-ARC-00003-00 | Supply and install CMU Block for internal walls (200mm thick) for Bathroom & Entrance Area Grid#(A-N\1-3) as per attached highlighted drawing. | Approved | 106 | 103.84 | 90% | 9906.336
4.1.4 | at electrical room (200mm thick, 2 hr fire rated) | 2026-05-12 | FIR -HFR1-05-003-SAK-TS9-1-FIR-ARC-00008-00 | Supply and install CMU Block forat electrical room (200mm thick, 2 hr fire rated)) for Bathroom & Entrance Area Grid#(A-N\1-3) as per attached highlighted drawing.Block1 | Approved | 91 | 68.28 | 90% | 5592.132
4.1.1 | at internal walls (100mm thick) | 2026-05-12 | FIR -HFR1-05-003-SAK-TS9-1FIR-ARC-00004-00 | Supply and install CMU Block for internal walls (100mm thick) for Bathroom & Entrance Area Block-2 Grid#(A-N\1-3) as per attached highlighted drawing. | Approved | 70 | 22.32 | 10% | 156.24
4.1.2 | at internal walls (200mm thick) | 2026-05-12 | FIR -HFR1-05-003-SAK-TS9-1FIR-ARC-00005-00 | Supply and install CMU Block for internal walls (200mm thick) for Bathroom & Entrance Area Block-2-Grid#(A-N\1-3) as per attached highlighted drawing. | Approved | 84 | 169.86 | 10% | 1426.824
4.1.3 | at external walls (200mm thick insulated) | 2026-05-12 | FIR -HFR1-05-003-SAK-TS9-1FIR-ARC-00006-00 | Supply and install CMU Block for internal walls (200mm thick) for Bathroom & Entrance Area Block-2, Grid#(A-N\1-3) as per attached highlighted drawing. | Approved | 106 | 103.84 | 10% | 1100.704
4.1.4 | at electrical room (200mm thick, 2 hr fire rated) | 2026-05-12 | FIR -HFR1-05-003-SAK-TS9-1-FIR-ARC-00009-00 | Supply and install CMU Block forat electrical room (200mm thick, 2 hr fire rated)) for Bathroom & Entrance Area Grid#(A-N\1-3) as per attached highlighted drawing.Block2 | Approved | 91 | 68.28 | 10% | 621.348
11.1.2 | Intumescent paint to steel works to ensure the fire rating required for 2 hours | 2026-05-12 | FIR -HFR1-05-003-SAK-TS9-1-FIR-ARC-00007-00 | Spraying and applying 2 hours fire rated intumescent paint for Steel Structure as per attached Highlighted drawing. | Approved | 411856 | 1 | 30% | 123556.8
15.2.1.2 | Supply and installation of HDPE PE 100 PN16 pipes, for cold water supply piping system (underground) as specified on drawings and documents, 90 mm Ø | 2026-05-11 | FIR -HFR1-05-003-SAK-TS9-1-FIR-Mech-0010-00 | Installation of HDPE PE 100 PN16 Pipes 90mm AS SHOWN ATTACHED DRAWING. | Approved | 143 | 471.5 | 22% | 14833.39
11.1.2 | Intumescent paint to steel works to ensure the fire rating required for 2 hours | 2026-05-31 | FIR - HFR1-05-003-SAK-TS9-1FIR-ARC-00007-01 | Spraying and applying 2 hours fire rated intumescent paint for Steel Structure as per attached Highlighted drawing. For Block 1 | Approved | 411856 | 1 | 30% | 123556.8
3.2.6 | Roof Slab | 2026-05-25 | FIR - HFR1-05-003-SAK-TS9-1FIR-ST-0263-00 | Pouring concrete for Roof Slab at Bathroom and Masjid Area Axis (A-N/1x3) as per attached highlighted drawing For Block 2 | Approved | 1098 | 15.42 | 100% | 16931.16
11.1.1 | Supply and install the PEB for one block with an area 1990 square meter. The PEB Steel structure shall include epoxy painted 150 micron, and shall fully comply with drawings and specifications; | 2026-05-31 | FIR - HFR1-05-003-SAK-TS9-1FIR-ARC-00012-00 | Supply and install sandwich panel (100 mm) for external walls and roof and rock wool for internal wall at Block 1&2 as per attached highlighted drawing. For Block 1 & 2 | Approved | 950000 | 1 | 50% | 475000
16.8.2 | PP-AC: Air Conditioning Power Panel | 2026-06-11 | FIR-HFR1-05-003-SAK-TS9-1FIR-ELE-0008-00 | Supply, install, of PP-AC Panel boards | Approved | 10307 | 27 | 70% | 194802.3
16.2.7 | pipes for all telecom network at site | 2026-05-08 | FIR-HFR1-05-003-SAK-TS9-1FIR-ELE-004-00 | Installation PIPES FOR TELECOMMUNICATION NETWORK HDPE 32MM | Approved | 103 | 1877.88 | 100% | 193421.64
16.2.8 | pipes for all electrical network at site | 2026-05-24 | FIR-HFR1-05-003-SAK-TS9-1FIR-ELE-0006-00 | Installation PIPES FOR ELECTRICAL SITE | Approved | 103 | 826.26 | 100% | 85104.78
15.1.2.1 | Supply and install HDPE PE100 PN16 Pipes as specified on drawings and documents, 200 mm Ø | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0011-00 | Install & test of HDPE PE100 PN16 Pipes as specified on drawings and documents, ,200 mm Ø. | Approved | 253 | 18.48 | 100% | 4675.44
15.1.2.2 | Supply and install HDPE PE100 PN16 Pipes as specified on drawings and documents, 150 mm Ø | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0011-00 | Install & test of HDPE PE100 PN16 Pipes as specified on drawings and documents, 150 mm Ø | Approved | 209 | 125.94 | 100% | 26321.46
15.1.3.1 | 200 mm Ø | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0012-00 | Install & test Directly Buried Gate valve complete as specified on drawings and documents and as per authorities requirements and Engineer on site , 150 mm Ø , 200 mm Ø | Approved | 5500 | 1 | 100% | 5500
15.1.3.2 | 150 mm Ø | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0012-00 | Install & test Directly Buried Gate valve complete as specified on drawings and documents and as per authorities requirements and Engineer on site , 150 mm Ø , 200 mm Ø | Approved | 3300 | 2 | 100% | 6600
15.2.1.1 | 100 mm Ø | 2026-06-15 | FIR -HFR1-05-003-SAK-TS9-1-FIR-MECH-0013-00 | Installation & test of HDPE PE 100 PN16 pipes, for cold water supply piping system (underground) as specified on drawings and documents, 100 mm | Approved | 165 | 15.98 | 80% | 2109.36
15.2.1.2 | 90 mm Ø | 2026-06-15 | FIR -HFR1-05-003-SAK-TS9-1-FIR-MECH-0013-00 | Installation & test of HDPE PE 100 PN16 pipes, for cold water supply piping system (underground) as specified on drawings and documents, 90 mm Ø | Approved | 143 | 471.5 | 36% | 24272.82
15.2.1.3 | 63 mm Ø | 2026-06-15 | FIR -HFR1-05-003-SAK-TS9-1-FIR-MECH-0013-00 | Installation & test of HDPE PE 100 PN16 pipes, for cold water supply piping system (underground) as specified on drawings and documents, 63 mm Ø | Approved | 121 | 21.94 | 100% | 2654.74
15.2.1.4 | 50 mm Ø | 2026-06-15 | FIR -HFR1-05-003-SAK-TS9-1-FIR-MECH-0013-00 | Installation & test of HDPE PE 100 PN16 pipes, for cold water supply piping system (underground) as specified on drawings and documents, 50 mm Ø | Approved | 99 | 123.12 | 64% | 7800.8832
15.2.2.1 | 100 mm Ø | 2026-06-15 | FIR -HFR1-05-003-SAK-TS9-1-FIR-MECH-0014-00 | Install & test of Directly Buried Gate valve complete as specified on drawings and documents and as per authorities requirements and Engineer on site , 100 mm Ø | Approved | 2750 | 1 | 100% | 2750
15.2.2.2 | 90 mm Ø | 2026-06-15 | FIR -HFR1-05-003-SAK-TS9-1-FIR-MECH-0014-00 | Install & test of Directly Buried Gate valve complete as specified on drawings and documents and as per authorities requirements and Engineer on site ,90 mm Ø | Approved | 1650 | 8 | 100% | 13200
15.2.2.3 | 63 mm Ø | 2026-06-15 | FIR -HFR1-05-003-SAK-TS9-1-FIR-MECH-0014-00 | Install & test of Directly Buried Gate valve complete as specified on drawings and documents and as per authorities requirements and Engineer on site , 63 mm Ø | Approved | 1100 | 4 | 100% | 4400
15.2.3.1 | 63 mm Ø | 2026-06-15 | FIR -HFR1-05-003-SAK-TS9-1-FIR-MECH-0015-00 | Install & test of Service connection -HDPE -complete as specified and shown on Drawings and documents, 63 mm Ø | Approved | 1650 | 4 | 100% | 6600
15.2.5.1 | For 100 mm Ø pipe | 2026-06-15 | FIR -HFR1-05-003-SAK-TS9-1-FIR-MECH-0016-00 | Install Road Crossing sleeve for under ground water supply Pipes, including excavation, backfilling, disposal of surplus materials, concrete works as specified on drawings and documents, For 100 mm Ø pipe | Approved | 330 | 13.75 | 100% | 4537.5
15.2.6.2 | Washout Valve | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0017-00 | Install following valves including chamber complete as specified on drawings and documents and as per authorities requirements and Engineer on site, Washout Valve | Approved | 1100 | 1 | 100% | 1100
15.2.8.1 | Hot Press GRP Sectional Panel Water Tanks (10x8x4m) | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0019-00 | Install, connection of Facility water storage tanks Including overflow, vent, float valves, altitude valves, drain valves, access opeining, access ladder, emergency tanker fill and all necessary accessories, connections and fittings as per drawings and specifications, Hot Press GRP Sectional Panel Water Tanks (10x8x4m) | Approved | 275000 | 1 | 20% | 55000
15.3.2.1 | 160 mm Pipe in trench not exceeding 2.00 m depth to invert | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0020-00 | Install & test of 160 mm Pipe in trench not exceeding 2.00 m depth to invert | Approved | 440 | 348.06 | 35% | 53601.24
15..3.4 | Supply and install 100mm GRP pipe service connections between building sewage inspection chamber and main wastewater line as specified on drawings and documents and as per Engineer on site | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0022-00 | Install 100mm GRP pipe service connections between building sewage inspection chamber and main wastewater line as specified on drawings and documents and as per Engineer on site | Approved | 1650 | 4 | 100% | 6600
15.5.2.1 | 63 mm Ø (2 1/2" Ø )Cold water | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0023-00 | Install, test of PPR SDR 7.4 PN 16, DIN 8077/78 pipes, for cold and hot water supply piping system (Aboveground), complete with fittings, valves and accessories including AAVs, WHA, fiberglass thermal insulation for hot pipes, flushing and all other accessories as per drawings and specifications,63 mm Ø (2 1/2" Ø ), 50 mm Ø (2" Ø ), 40 mm Ø ( 1 1/2" Ø), 25 mm Ø ( 1" Ø), 20 mm Ø ( 3/4" Ø)Cold water, 20 mm Ø ( 3/4" Ø) Hot water | Approved | 110 | 21.12 | 80% | 1858.56
15.5.2.2 | 50 mm Ø (2" Ø )Cold water | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0023-00 | Install, test of PPR SDR 7.4 PN 16, DIN 8077/78 pipes, for cold and hot water supply piping system (Aboveground), complete with fittings, valves and accessories including AAVs, WHA, fiberglass thermal insulation for hot pipes, flushing and all other accessories as per drawings and specifications,63 mm Ø (2 1/2" Ø ), 50 mm Ø (2" Ø ), 40 mm Ø ( 1 1/2" Ø), 25 mm Ø ( 1" Ø), 20 mm Ø ( 3/4" Ø)Cold water, 20 mm Ø ( 3/4" Ø) Hot water | Approved | 99 | 22.8 | 80% | 1805.76
15.5.2.3 | 40 mm Ø ( 1 1/2" Ø) Cold water | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0023-00 | Install, test of PPR SDR 7.4 PN 16, DIN 8077/78 pipes, for cold and hot water supply piping system (Aboveground), complete with fittings, valves and accessories including AAVs, WHA, fiberglass thermal insulation for hot pipes, flushing and all other accessories as per drawings and specifications,63 mm Ø (2 1/2" Ø ), 50 mm Ø (2" Ø ), 40 mm Ø ( 1 1/2" Ø), 25 mm Ø ( 1" Ø), 20 mm Ø ( 3/4" Ø)Cold water, 20 mm Ø ( 3/4" Ø) Hot water | Approved | 83 | 40.14 | 80% | 2665.296
15.5.2.4 | 25 mm Ø ( 1" Ø) Cold water | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0023-00 | Install, test of PPR SDR 7.4 PN 16, DIN 8077/78 pipes, for cold and hot water supply piping system (Aboveground), complete with fittings, valves and accessories including AAVs, WHA, fiberglass thermal insulation for hot pipes, flushing and all other accessories as per drawings and specifications,63 mm Ø (2 1/2" Ø ), 50 mm Ø (2" Ø ), 40 mm Ø ( 1 1/2" Ø), 25 mm Ø ( 1" Ø), 20 mm Ø ( 3/4" Ø)Cold water, 20 mm Ø ( 3/4" Ø) Hot water | Approved | 55 | 26.76 | 80% | 1177.44
15.5.2.5 | 20 mm Ø ( 3/4" Ø) Cold water | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0023-00 | Install, test of PPR SDR 7.4 PN 16, DIN 8077/78 pipes, for cold and hot water supply piping system (Aboveground), complete with fittings, valves and accessories including AAVs, WHA, fiberglass thermal insulation for hot pipes, flushing and all other accessories as per drawings and specifications,63 mm Ø (2 1/2" Ø ), 50 mm Ø (2" Ø ), 40 mm Ø ( 1 1/2" Ø), 25 mm Ø ( 1" Ø), 20 mm Ø ( 3/4" Ø)Cold water, 20 mm Ø ( 3/4" Ø) Hot water | Approved | 44 | 124.88 | 80% | 4395.776
15.5.2.6 | 20 mm Ø ( 3/4" Ø) Hot water | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0023-00 | Install, test of PPR SDR 7.4 PN 16, DIN 8077/78 pipes, for cold and hot water supply piping system (Aboveground), complete with fittings, valves and accessories including AAVs, WHA, fiberglass thermal insulation for hot pipes, flushing and all other accessories as per drawings and specifications,63 mm Ø (2 1/2" Ø ), 50 mm Ø (2" Ø ), 40 mm Ø ( 1 1/2" Ø), 25 mm Ø ( 1" Ø), 20 mm Ø ( 3/4" Ø)Cold water, 20 mm Ø ( 3/4" Ø) Hot water | Approved | 55 | 96.58 | 80% | 4249.52
15.5.3.1 | 63 mm Ø | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0024-00 | Install of Ball Valve, 63 mm Ø | Approved | 715 | 4 | 80% | 2288
15.5.3.2 | 50 mm Ø | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0024-00 | Install of Ball Valve, 50 mm Ø | Approved | 550 | 4 | 80% | 1760
15.5.3.3 | 40 mm Ø | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0024-00 | Install of Ball Valve,, 40 mm Ø | Approved | 440 | 4 | 80% | 1408
15.5.4.1 | 50 mm Ø | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0025-00 | Install of Capped connection (For tenant use), 50 mm Ø | Approved | 660 | 24 | 80% | 12672
15.5.5.1 | 63 mm Ø | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0026-00 | Install of valve box 80*80 cm with gate valve including all the required works (keep a suffiecient distance to install meter), complete with accessories and as per drawings and specifications, 63 mm Ø, 50 mm Ø | Approved | 1320 | 4 | 80% | 4224
15.5.5.2 | 50 mm Ø | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0026-00 | Install of valve box 80*80 cm with gate valve including all the required works (keep a suffiecient distance to install meter), complete with accessories and as per drawings and specifications, 63 mm Ø, 50 mm Ø | Approved | 1100 | 24 | 80% | 21120
15.6.1.2 | Supply, install, test and commission uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification, Ø 3" | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0027-00 | Install & test of uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification , Ø 3" | Approved | 77 | 69.08 | 20% | 1063.832
15.6.1.3 | Supply, install, test and commission uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification, Ø 2" | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0027-00 | Install & test of uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification , Ø 2" | Approved | 61 | 116 | 80% | 5660.8
15.7.7 | Supply, installation , testing & commissioning of condensate drain piping, complete as per drawings, specifications and method of measurement. | 2026-06-15 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0028-00 | Installation & test of condensate drain piping, complete as per drawings, specifications and method of measurement. | Approved | 165 | 78 | 80% | 10296
16.3.2 | Complete street lighting poles with LED lighting fixtures | 2026-05-11 | FIR-HFR1-05-003-SAK-TS9-1FIR-ELE-0005-00 | Supply Street Lighting Poles With LED Lighting Fixtures and Concrete Foundations For Street Lighting Poles | Approved | 4015 | 27 | 100% | 108405
2.1.3 | Backfilling with selected fill material free of debris and boulders, in layers. Price also includes testing each layer by a specialized laboratory. The works shall satisfy the project specification and soil report requirements and shall be accepted and approved by the Engineer. | 2026-06-22 | HFR1-05-003-SAK-TS9-1FIR-SUR-0116-00 | Supply and Install Backfilling Material for Road-2, Zone1&2, works from Station 0+000 to 0+94.152 as per attached highlighted drawing. | Approved | 39 | 1698.03 | 100% | 66223.17
2.1.3 | Backfilling with selected fill material free of debris and boulders, in layers. Price also includes testing each layer by a specialized laboratory. The works shall satisfy the project specification and soil report requirements and shall be accepted and approved by the Engineer. | 2026-06-22 | HFR1-05-003-SAK-TS9-1FIR-SUR-0117-00 | Supply and Install Backfilling Material for Road-2, Zone1&2, works from Station 0+000 to 0+94.152 as per attached highlighted drawing. | Approved | 39 | 6149.24 | 100% | 239820.36
11.1.2 | Intumescent paint to steel works to ensure the fire rating required for 2 hours | 2026-06-07 | FIR-HFR1-05-003-SAK-TS9-1FIR-ARC-0015-00 | Spraying and applying 2 hours fire rated intumescent paint for Steel Structure as per attached Highlighted drawing. | Approved | 411856 | 1 | 70% | 288299.2
11.1.2 | Intumescent paint to steel works to ensure the fire rating required for 2 hours | 2026-05-31 | FIR - HFR1-05-003-SAK-TS9-1FIR-ARC-00007-01 | Spraying and applying 2 hours fire rated intumescent paint for Steel Structure as per attached Highlighted drawing. For Block 1 | Approved | 411856 | 1 | 70% | 288299.2
11.1.1 | Supply and install the PEB for one block with an area 1990 square meter. The PEB Steel structure shall include epoxy painted 150 micron, and shall fully comply with drawings and specifications; | 2026-05-31 | FIR - HFR1-05-003-SAK-TS9-1FIR-ARC-0023-00 | Supply and install sandwich panel (100 mm) for external walls and roof and rock wool for internal wall at Block 1&2 as per attached highlighted drawing. For Block 2 | Approved | 950000 | 1 | 40% | 380000
11.1.1 | Supply and install the PEB for one block with an area 1990 square meter. The PEB Steel structure shall include epoxy painted 150 micron, and shall fully comply with drawings and specifications; | 2026-05-31 | FIR - HFR1-05-003-SAK-TS9-1FIR-ARC-00012-01 | Supply and install sandwich panel (100 mm) for external walls and roof and rock wool for internal wall at Block 1&2 as per attached highlighted drawing. For Block 1 | Approved | 950000 | 1 | 40% | 380000
8.1.1 | Supply and install (D6) 3000*3500mm galvanized steel heavy duty industrial isolated type roll up shutter door finished with polyurethane coating, with automatic and manual control system, as per manufacturer specification and approved by the Client, complete with all accessories and fittings, and as per door schedule and specifications | 2026-06-25 | FIR - HFR1-05-003-SAK-TS9-1-FIRARC-0028-00 | Supply and install (D6) 3000*3500mm galvanized steel heavy duty industrial isolated type roll up shutter door finished with polyurethane coating, with automatic and manual control system, as per manufacturer specification and approved as per attached highlighted drawing. | Approved | 15510 | 24 | 15% | 55836
8.1.2 | Supply and install fire rated 45 min. (D5) 1000*2200mm single leaf steel door with door construction type C with hardware set type HW2 paint finish as per manufacturer detail and approved by the Client with complete accessories as per door schedule, drawings and specification | 2026-06-27 | FIR - HFR1-05-003-SAK-TS9-1-FIRARC-0029-00 | Supply and install fire rated 45 min. (D5) 1000*2200mm single leaf steel door with door construction type C with hardware set type HW2 paint finishas per attached highlighted drawing. | Approved | 2750 | 24 | 10% | 6600
16.1 | Supply, install, and construct at site concrete foundation for Electrical Substation, useable for all type, with security fence as per SEC latest specifications and standards | 2026-06-23 | FIR - HFR1-03-005-SAK-TS9-1-FIR-STU-0311-00 | Supply, install, and construct at site concrete foundation for Electrical Substation, useable for all type, with security fence as per attached highlighted drawing. | Approved | 27500 | 2 | 100% | 55000
16.2.1 | Complete Branch Telecom Manhole (MH1) with pipes | 2026-06-25 | FIR - HFR1-03-005-SAK-TS9-1-FIR-STU-0325-00 | Excavation,Bedding and Pouring Concretefor Foundation &wallBranch Telecom Manhole (MH1) with pipes 60%, as per the attached highlighted drawing. | Approved | 5515 | 18 | 60% | 59562
16.2.2 | Complete Main Telecom Manhole (MH2) with pipes | 2026-06-25 | FIR - HFR1-03-005-SAK-TS9-1-FIR-STU-0320-00 | Excavation,Bedding and Pouring Concretefor Foundation &wallMain Telecom Manhole (MH2) with pipes60%as per attached highlighted drawing | Approved | 5240 | 8 | 60% | 25152
16.2.3 | Complete Telecom Handhole (HH) with pipes | 2026-05-03 | FIR - HFR1-03-005-SAK-TS9-1-FIR-STU-0207-00 | Excavation and pouring reinforcement for foundation | Approved | 2002 | 8 | 60% | 9609.6
16.6.1 | 4C x 185 mm2 +1C x 95mm2 | 2026-06-19 | FIR- HFR1-05-003-SAK-TS9-1-FIR-ELE-0018-00 | install, of low voltage Copper Cables 4C x 185 mm2 +1C x 95mm2 | Approved | 514 | 1938 | 12.5% | 124516.5
16.8.1 | LP: Lighting Power Panel | 2026-06-27 | FIR - HFR1-05-003-SAK-TS9-1-FIR-ELE-0012-00 | INSTALLATION OF LP: Lighting Power Panel | Approved | 4323 | 27 | 70% | 81704.7
16.8.3 | MDB: Main Distribution Board | 2026-06-27 | FIR - HFR1-05-003-SAK-TS9-1-FIR-ELE-0013-00 | INSTALLATION FOR MDB: Main Distribution Board BLOCK B1 | Approved | 13200 | 13 | 70% | 120120
16.8.3 | MDB: Main Distribution Board | 2026-06-27 | FIR - HFR1-05-003-SAK-TS9-1-FIR-ELE-0014-00 | INSTALLATION FOR MDB: Main Distribution Board BLOCK B2 | Approved | 13200 | 13 | 70% | 120120
16.10.1 | Suspended High-Bay LED lighting | 2026-06-16 | FIR - HFR1-05-003-SAK-TS9-1-FIR-ELE-0011-01 | Installation of Suspended High-Bay LED lighting | Approved | 953 | 192 | 10% | 18297.6
16.11.1 | Telecom Cabinet ( Rack ) Complete | 2026-06-19 | FIR - HFR1-05-003-SAK-TS9-1-FIR-ELE-0017-00 | Installation of telecom cabinet with all inside components and accessories | Approved | 2530 | 25 | 70% | 44275
16.11.2 | Telecom Junction Box | 2026-06-19 | FIR - HFR1-05-003-SAK-TS9-1-FIR-ELE-0017-00 | Installation of telecom cabinet with all inside components and accessories | Approved | 1045 | 25 | 70% | 18287.5
16.11.4 | Complete Telephone Patch Panel | 2026-06-19 | FIR - HFR1-05-003-SAK-TS9-1-FIR-ELE-0017-00 | Installation of telecom cabinet with all inside components and accessories | Approved | 1320 | 25 | 70% | 23100
16.11.5 | Complete Data Patch Panel | 2026-06-19 | FIR - HFR1-05-003-SAK-TS9-1-FIR-ELE-0017-00 | Installation of telecom cabinet with all inside components and accessories | Approved | 1540 | 25 | 70% | 26950
16.16.1 | Solar Power Plant | 2026-06-15 | FIR - HFR1-05-003-SAK-TS9-1-FIR-ELE-0009-00 | Installation of solar power plant | Approved | 53900 | 12 | 10% | 64680
16.16.1 | Solar Power Plant | 2026-06-15 | FIR - HFR1-05-003-SAK-TS9-1-FIR-ELE-0010-00 | Installation of solar power plant | Approved | 53900 | 12 | 10% | 64680
3.1.1 | Lean concrete under foundations and grade beams. | 2026-03-17 | FIR - HFR1-05-003-SAK-TS9-1-FIR-STU-0122-00 | Pouring Plain concrete under Pump shed Grade beams | Approved | 42 | 15.6 | 100% | 655.2
3.2.1 | Cast in place reinforced concrete (Isolated Footing) | 2026-05-16 | FIR - HFR1-05-003-SAK-TS9-1FIR-ST-0236-00 | Pouring concrete for Electrical Room-1 as per attached highlighted drawing. | Approved | 862 | 1.728 | 100% | 1489.536
3.2.1 | Cast in place reinforced concrete (Isolated Footing) | 2026-05-11 | FIR - HFR1-05-003-SAK-TS9-1FIR-ST-0224-00 | Pouring concrete for Strip Footing no.2 at Electrical Room-2 as per attached highlighted drawing. | Approved | 862 | 1.44 | 100% | 1241.28
3.2.2 | Cast in place reinforced concrete (grade beams) | 2026-03-15 | FIR - HFR1-05-003-SAK-TS9-1FIR-STU-0121-00 | Supply & Install 250 micron polyethylene sheet under Pump Shed Grade beams as shown attached drawing. | Approved | 988 | 2.5 | 100% | 2470
3.2.2 | Cast in place reinforced concrete (grade beams) | 2026-05-23 | FIR - HFR1-05-003-SAK-TS9-1-FIR-STU-0257-00 | Pouring concrete for Grade Beam at Electrical Room-1 as per attached highlighted drawing. | Approved | 988 | 0.416 | 100% | 411.008
3.2.2 | Cast in place reinforced concrete (grade beams) | 2026-05-23 | FIR - HFR1-05-003-SAK-TS9-1-FIR-STU-0258-00 | Pouring concrete for Grade Beam at Electrical Room-2 as per attached highlighted drawing. | Approved | 988 | 0.32 | 100% | 316.16
3.2.4 | Cast in place reinforced concrete (Pedstel) | 2026-06-04 | FIR - HFR1-05-003-SAK-TS9-1FIR-ST-0275-00 | Pouring concrete for Column at Electrical Room-1 as per attached highlighted drawing. | Approved | 1218 | 0.32 | 100% | 389.76
3.2.4 | Cast in place reinforced concrete (Pedstel) | 2026-06-03 | FIR - HFR1-05-003-SAK-TS9-1FIR-ST-0276-00 | Pouring concrete for Column at Electrical Room-2 as per attached highlighted drawing. | Approved | 1218 | 0.32 | 100% | 389.76
3.2.6 | Roof Slab | 2026-05-23 | FIR - HFR1-05-003-SAK-TS9-1FIR-ST-0252-00 | Pouring concrete for Roof Slab at Bathroom and Masjid Area Axis (A-N/1x3) as per attached highlighted drawing For Block 1 | Approved | 1098 | 15.42 | 100% | 16931.16
3.2.7 | Roof Beams | 2026-06-09 | FIR - HFR1-05-003-SAK-TS9-1FIR-ST-0304-00 | Pouring Concrete for Inverted Beams at Building-2 as per attached highlighted drawing | Approved | 1098 | 11.04 | 100% | 12121.92
3.2.7 | Roof Beams | 2026-06-09 | FIR - HFR1-05-003-SAK-TS9-1FIR-ST-0315-00 | Pouring Concrete for Inverted Beams at Building-1 as per attached highlighted drawing | Approved | 1098 | 3.924 | 100% | 4308.552
3.2.7 | Roof Beams | 2026-06-09 | FIR - HFR1-05-003-SAK-TS9-1FIR-ST-0317-00 | Pouring Concrete for Parapet Beam at Building-2 as per attached highlighted drawing | Approved | 1098 | 3.924 | 100% | 4308.552
15.1.1 | Supply, install, test and commission Fire Pump system, Local code & UL/FM approved, meeting all NFPA requirements, complete with all pipework within pump shade and upto field network, valves, flow sensors/switch, alarm valves, Control panel with starters, ATS, all controls and relays, factory cabling & wiring from Control panel to motors & controls, complete set mounted on structural steel frame with necessary vibration isolators, connections to field pipework. System complete with controls, fittings, motors, specialties, connections, cabling/wiring, alarm panels, couplings, base, controllers, flow-measuring systems, flue gas piping with insulation, muffler, Diesel tank and all other accessories as per drawings and specifications. Set comprising of 1 Electric Drive centrifugal Fire Pump (FPE-GF-01) (1 operating) + 1 Diesel Engine Drive Centrifugal Fire Pump (FPD-GF-01) (1 Standby) + 1 pressure maintenance Pump (JP-GF-01). Electric Fire Pump & Diesel Fire Pump: 47 L/S @ 70m Pressure Maintenance Pump: 1 L/S @ 77m | 2026-06-23 | FIR - HFR1-05-003-SAK-TS9-1-FIR-MECH-0029-00 | install, test and commission Fire Pump System, Local code & UL/FM approved, meeting all NFPA requirements, complete with all pipework within pump shade and upto field network, ver drawings and specifications. | Approved | 330000 | 1 | 40% | 132000
2.1.3 | Backfilling with selected fill material free of debris and boulders, in layers. Price also includes testing each layer by a specialized laboratory. The works shall satisfy the project specification and soil report requirements and shall be accepted and approved by the Engineer. | 2026-03-15 | FIR - HFR1-05-003-SAK-TS9-1-FIR-SUR-0052-00 | Back fill material under slab Grid#(A-N\1-16) as per attached drawing. | Approved | 39 | 6977.5 | 100% | 272122.5
2.1.1 | Excavation in any type of soil from existing level to bottom of excavation depth including compaction and remove surplus excavated material and all necessary works complete in accordance with specifications, soil report, and drawings | 2026-06-04 | FIR - HFR1-05-003-SAK-TS9-1-FIR-SUR-0003-00 | Excavation from natural ground level to formation level, including disposal of excavated material and compaction in accordance with specifications, soil report, and drawings For Block 1 and 2 | Approved | 28 | 629.24 | 100% | 17618.72
15.1.1 | Supply, install, test and commission Fire Pump system, Local code & UL/FM approved, meeting all NFPA requirements, complete with all pipework within pump shade and upto field network, valves, flow sensors/switch, alarm valves, Control panel with starters, ATS, all controls and relays, factory cabling & wiring from Control panel to motors & controls, complete set mounted on structural steel frame with necessary vibration isolators, connections to field pipework. System complete with controls, fittings, motors, specialties, connections, cabling/wiring, alarm panels, couplings, base, controllers, flow-measuring systems, flue gas piping with insulation, muffler, Diesel tank and all other accessories as per drawings and specifications. Set comprising of 1 Electric Drive centrifugal Fire Pump (FPE-GF-01) (1 operating) + 1 Diesel Engine Drive Centrifugal Fire Pump (FPD-GF-01) (1 Standby) + 1 pressure maintenance Pump (JP-GF-01). Electric Fire Pump & Diesel Fire Pump: 47 L/S @ 70m Pressure Maintenance Pump: 1 L/S @ 77m | 2026-07-23 | FIR - HFR1-05-003-SAK-TS9-1-FIR-MECH-0030-00 | pipes connection between fire pumps & GRP tank & network 5% | Approved | 330000 | 1 | 25% | 82500
15.4.5.1 | Supply, install, test and commission OS&Y Gate valve , 6" Ø | 2026-07-23 | FIR - HFR1-05-003-SAK-TS9-1-FIR-MECH-0031-00 | INSTALL OS&Y. 6"Ø | Approved | 3300 | 6 | 100% | 19800
15.4.5.2 | Supply, install, test and commission OS&Y Gate valve , 4" Ø | 2026-07-23 | FIR - HFR1-05-003-SAK-TS9-1-FIR-MECH-0031-00 | INSTALL OS&Y. 4"Ø | Approved | 2200 | 4 | 100% | 8800
15.4.5.3 | Supply, install, test and commission OS&Y Gate valve , 2 1/2" Ø | 2026-07-23 | FIR - HFR1-05-003-SAK-TS9-1-FIR-MECH-0031-00 | INSTALL OS&Y. 2 ½"Ø | Approved | 880 | 24 | 100% | 21120
15.7.1.1 | Exhaust fan 425 CFM ex. Static 100 Pascal for toilets | 2026-07-23 | FIR - HFR1-05-003-SAK-TS9-1-FIR-MECH-0032-00 | INSTALL inline exhaust fans/make-up air fans AMCA, UL Listed, direct drive complete with supports, controls, accessories and as per drawings and specifications. | Approved | 1100 | 4 | 100% | 4400
15.7.1.2 | Make-up fan 360 CFM ex. Static 32 Pascal for toilets | 2026-07-23 | FIR - HFR1-05-003-SAK-TS9-1-FIR-MECH-0032-00 | INSTALL inline exhaust fans/make-up air fans AMCA, UL Listed, direct drive complete with supports, controls, accessories and as per drawings and specifications. | Approved | 1320 | 4 | 100% | 5280
15.7.2.1 | Exhaust fan 2351 CFM ex. Static 32 Pa for Factory area | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0033-00 | Install, side wall propeller type exhaust fans/make-up air fans with back draft damper, aluminum blades, AMCA certified, UL Listed, direct drive complete with mounting plate, supports, controls, accessories and as per drawings and specifications. | Approved | 2200 | 24 | 100% | 52800
15.7.2.2 | Make-up fan 1998 CFM ex. Static 32 Pa for Factory area | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0033-00 | Install, side wall propeller type exhaust fans/make-up air fans with back draft damper, aluminum blades, AMCA certified, UL Listed, direct drive complete with mounting plate, supports, controls, accessories and as per drawings and specifications. | Approved | 2420 | 24 | 100% | 58080
15.7.3 | Supply, install, test and commission indoor ductwork as per SMACNA Standards, complete, VD, duct tape, adhesive, duct sealant, hangers, supports and all other accessories, (Flanged TDC Type) and as per drawings and specification. | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0034-00 | Install, indoor ductwork as per SMACNA Standards, complete VD, duct tape, adhesive, duct sealant, hangers, supports and all other accessories. | Approved | 33 | 184.7424 | 100% | 6096.4992
15.7.7 | Supply, installation , testing & commissioning of condensate drain piping, complete as per drawings, specifications and method of measurement. | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0047-00 | Installation of foundation, walls, roof, insulation & backfilling Gully trap chamber & inspection chamber. | Approved | 165 | 78 | 100% | 12870
15.2.6.1 | Air Valve | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0037-00 | Installation of foundation, walls, roof, insulation & backfilling of air valve chamber. | Approved | 715 | 1 | 100% | 715
15.3.2.1 | 160 mm Pipe in trench not exceeding 2.00 m depth to invert | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-MECH-0038-00 | Installation, test & backfilling of 160 mm GRP Pipes in trench not exceeding 2.00 m depth to invert. | Approved | 440 | 348.06 | 20% | 30629.28
15.4.2.1 | 150mm Ø | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0035-00 | Install, test and commission black steel pipes and mechanical fittings for aboveground installation, sch. 40 ASTM A 53 complete with hangers & supports, AAVs, two coats of primer and final finish red color painting, accessories and insulation as per drawings and specification. | Approved | 330 | 53.7 | 100% | 17721
15.4.2.2 | 100mm Ø | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0035-00 | Install, test and commission black steel pipes and mechanical fittings for aboveground installation, sch. 40 ASTM A 53 complete with hangers & supports, AAVs, two coats of primer and final finish red color painting, accessories and insulation as per drawings and specification. | Approved | 220 | 219.16 | 100% | 48215.2
15.4.2.3 | 90mm Ø | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0035-00 | Install, test and commission black steel pipes and mechanical fittings for aboveground installation, sch. 40 ASTM A 53 complete with hangers & supports, AAVs, two coats of primer and final finish red color painting, accessories and insulation as per drawings and specification. | Approved | 154 | 41.76 | 100% | 6431.04
15.4.2.4 | 80mm Ø | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0035-00 | Install, test and commission black steel pipes and mechanical fittings for aboveground installation, sch. 40 ASTM A 53 complete with hangers & supports, AAVs, two coats of primer and final finish red color painting, accessories and insulation as per drawings and specification. | Approved | 138 | 43.2 | 100% | 5961.6
15.4.2.5 | 65mm Ø | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0035-00 | Install, test and commission black steel pipes and mechanical fittings for aboveground installation, sch. 40 ASTM A 53 complete with hangers & supports, AAVs, two coats of primer and final finish red color painting, accessories and insulation as per drawings and specification. | Approved | 121 | 353.38 | 100% | 42758.98
15.4.2.6 | 50mm Ø | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0035-00 | Install, test and commission black steel pipes and mechanical fittings for aboveground installation, sch. 40 ASTM A 53 complete with hangers & supports, AAVs, two coats of primer and final finish red color painting, accessories and insulation as per drawings and specification. | Approved | 99 | 129.34 | 100% | 12804.66
15.4.2.7 | 40mm Ø | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0035-00 | Install, test and commission black steel pipes and mechanical fittings for aboveground installation, sch. 40 ASTM A 53 complete with hangers & supports, AAVs, two coats of primer and final finish red color painting, accessories and insulation as per drawings and specification. | Approved | 88 | 158.78 | 100% | 13972.64
15.4.2.9 | 25mm Ø | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0035-00 | Install, test and commission black steel pipes and mechanical fittings for aboveground installation, sch. 40 ASTM A 53 complete with hangers & supports, AAVs, two coats of primer and final finish red color painting, accessories and insulation as per drawings and specification. | Approved | 61 | 1154.6 | 100% | 70430.6
15.4.4 | Supply, install, test and commission fire hose cabinet (FHC-2), complete with 30m long hose, nozzle, shut-off valve,6 kg ABC type dry chemical fire extingusher and fixing accessories.(valve and nozzel UL listed) as per drawings and specification | 2026-07-23 | HFR1-05-003-SAK-TS9-1-FIR-MECH-0040-00 | Install of fire hose cabinet (FHC-2), complete with 30 m long hose, nozzle, shut-off valve, 6 kg ABC type dry chemical fire extinguisher and fixing accessories. (valve and nozzle UL listed) as per drawings and specification. | Approved | 2420 | 12 | 100% | 29040
15.4.6 | Supply, install, testing and commission Fire Alarm Check Valve (ACV) assembly with OS&Y gate valve 6" Ø, complete with accessories.as per drawing and specifications | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-MECH-0041-00 | Fire Alarm Check Valve (ACV), Fire Department Connection (FDC) 6″ with double check valve, 1″ Ø Automatic air release valve. | Approved | 6600 | 2 | 100% | 13200
15.4.7 | Supply, install, test and commission Fire Department Connection (FDC) 6" with double check valve as per drawings and specification. | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-MECH-0041-00 | Fire Alarm Check Valve (ACV), Fire Department Connection (FDC) 6″ with double check valve, 1″ Ø Automatic air release valve. | Approved | 5500 | 2 | 100% | 11000
15.4.8 | Supply, install, test and commission 1" Ø Automatic air release valve | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-MECH-0041-00 | Fire Alarm Check Valve (ACV), Fire Department Connection (FDC) 6″ with double check valve, 1″ Ø Automatic air release valve. | Approved | 715 | 2 | 100% | 1430
15.5.4.1 | 50 mm Ø | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-MECH-0044-00 | Install, test and backfilling of capped connection (for tenant use), 50 mm Ø. | Approved | 660 | 24 | 20% | 3168
15.6.1.3 | Supply, install, test and commission uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification, Ø 2" | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-MECH-0046-00 | Install test & backfilling of uPVC pipes, schedule 40 for sewage, drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification Ø 4″ Ø 3″ Ø 2″ Ø 1″ | Approved | 61 | 343.64 | 20% | 4192.408
15.6.1.4 | Supply, install, test and commission uPVC pipes, schedule 40 for sewage ,drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification, Ø 1" | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-MECH-0046-00 | Install test & backfilling of uPVC pipes, schedule 40 for sewage, drainage piping system and vent piping system, complete with push fittings with rubber gasket and accessories, warning tape, excavation, backfilling, thrust blocks, FCO, CO and all other accessories as per drawings and specification Ø 4″ Ø 3″ Ø 2″ Ø 1″ | Approved | 44 | 458.88 | 20% | 4038.144
15.6.4 | Supply, install, test and commission Gully Traps with heavy duty cover and all other accessories as per drawings and specification. | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-MECH-0047-00 | Installation of foundation, walls, roof, insulation & backfilling Gully trap chamber & inspection chamber. | Approved | 605 | 16 | 100% | 9680
15.6.5 | Supply, install, test and commission Inspection chamber with heavy duty cover and all other accessories as per drawings and specification. | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-MECH-0047-00 | Installation of foundation, walls, roof, insulation & backfilling Gully trap chamber & inspection chamber. | Approved | 2200 | 4 | 100% | 8800
16.10.1 | Suspended High-Bay LED lighting | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00020-00 | Installation of First & Second Fix for Fire Alarm System | Approved | 953 | 192 | 60% | 109785.6
16.10.2 | Surface mounted LED lighting | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00020-00 | Installation of First & Second Fix for Fire Alarm System | Approved | 425 | 92 | 70% | 27370
16.10.3 | Wall mounted LED Emergency lighting | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00020-00 | Installation of First & Second Fix for Fire Alarm System | Approved | 607 | 25 | 70% | 10622.5
16.10.4 | Exits LED lighting | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00020-00 | Installation of First & Second Fix for Fire Alarm System | Approved | 535 | 24 | 70% | 8988
16.10.5 | Outdoor wall mounted LED lighting | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00020-00 | Installation of First & Second Fix for Fire Alarm System | Approved | 475 | 48 | 70% | 15960
16.10.6 | Outdoor wall mounted LED Flood lighting | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00020-00 | Installation of First & Second Fix for Fire Alarm System | Approved | 733 | 48 | 70% | 24628.8
16.10.7 | Lighting Outlet | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00020-00 | Installation of First & Second Fix for Fire Alarm System | Approved | 348 | 24 | 70% | 5846.4
16.10.8 | 2 Gang switch, one way | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00020-00 | Installation of First & Second Fix for Fire Alarm System | Approved | 165 | 51 | 70% | 5890.5
16.10.9 | One Gang switch, one way | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00020-00 | Installation of First & Second Fix for Fire Alarm System | Approved | 110 | 10 | 70% | 770
16.11.3 | Telecom Pulling Box | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-0021-00 | Installation of First & Second Fix for Fire Alarm System | Approved | 550 | 25 | 70% | 9625
16.11.6 | Wall mounted Telephone Outlet | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-0021-00 | Installation of First & Second Fix for Fire Alarm System | Approved | 369 | 150 | 70% | 38745
16.11.7 | Wall mounted Data Outlet | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-0021-00 | Installation of First & Second Fix for Fire Alarm System | Approved | 405 | 150 | 70% | 42525
16.14.1 | Wall mounted Addressable Fire Alarm Control Panel Complete | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00019-00 | Installation of First & Second Fix for Fire Alarm system | Approved | 54780 | 2 | 70% | 76692
16.14.2 | Inoisation, photoelectric, intellegent multi-sensor detectors complete with base | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00019-00 | Installation of First & Second Fix for Fire Alarm system | Approved | 435 | 166 | 70% | 50547
16.14.3 | Wall mounted Manual Pull Station | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00019-00 | Installation of First & Second Fix for Fire Alarm system | Approved | 501 | 25 | 70% | 8767.5
16.14.4 | Wall mounted Fire Alarm Sounder Bell | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00019-00 | Installation of First & Second Fix for Fire Alarm system | Approved | 611 | 25 | 70% | 10692.5
16.14.5 | Wall mounted Firewarning Flash Light with Sounder | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00019-00 | Installation of First & Second Fix for Fire Alarm system | Approved | 715 | 25 | 70% | 12512.5
16.14.6 | Wall mounted Firewarning Flash Light with Sounder, Weather-Proof | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00019-00 | Installation of First & Second Fix for Fire Alarm system | Approved | 902 | 25 | 70% | 15785
16.15.1 | Wall mounted Duplex Socket | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00022-00 | Installation of First & Second Fix for Fire Alarm system | Approved | 337 | 244 | 70% | 57559.6
16.15.2 | High level single electrical outlet for Emergency lights | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00022-00 | Installation of First & Second Fix for Fire Alarm system | Approved | 321 | 25 | 70% | 5617.5
16.15.3 | Electrical outlet for Package units & AC Split units | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00022-00 | Installation of First & Second Fix for Fire Alarm system | Approved | 589 | 78 | 70% | 32159.4
16.15.4 | Electrical outlet for Exhaust fans | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00022-00 | Installation of First & Second Fix for Fire Alarm system | Approved | 438 | 54 | 70% | 16556.4
16.15.8 | Electrical outlet for Water-heater | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00022-00 | Installation of First & Second Fix for Fire Alarm system | Approved | 388 | 4 | 70% | 1086.4
16.15.9 | Electrical outlet for Hand-dryer | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-00022-00 | Installation of First & Second Fix for Fire Alarm system | Approved | 388 | 4 | 70% | 1086.4
16.16.1 | Solar Power Plant |  | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-0024-00 |  | Approved | 53900 | 12 | 60% | 388080
16.16.1 | Solar Power Plant |  | FIR-HFR1-05-003-SAK-TS9-1-FIR-ELE-0026-00 |  | Approved | 53900 | 12 | 60% | 388080
3.2.8 | For Pump room SOG + external steps and ramps | 2026-07-22 | FIR-HFR1-05-003-SAK-TS9-1FIR-ST-0338-00 | Pouring Concrete for Pump room SOG + external steps and ramps at Building-1&2, as per attached highlighted drawing. | Approved | 951 | 72.707 | 100% | 69144.4042
3.4 | The autoclaved aerated panel for slabs, external and internal walls and parapet with lintels for all openings with necessary joining reinforcement between walls, straps, filler board and steel reinforcement and whatever needed to do a perfect work all as per drawings and specifications | 2026-07-13 | FIR-HFR1-05-003-SAK-TS9-1FIR-ST-0331-00 | Supply and installation of Autoclaved Aerated Concrete (AAC) panels for Prayer area as per attached highlighted drawing. | Approved | 330 | 126.2 | 100% | 41646
7.4.1 | Supply and install liquid applied waterproofing membrane; single-component pitch modified polyurethane based elastomeric high performance waterproofing; applied in multi-coats including sand fill materials for toilets | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ARC-0063-00 | Supply and install liquid applied waterproofing membrane at Building-2, as per highlighted drawing. | Approved | 83 | 68.04 | 100% | 5647.32
7.4.2 | Supply and install geotextile sheet | 2026-07-25 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ARC-0064-00 | Supply and install geotextile sheet at Building-2, as per highlighted drawing. | Approved | 9 | 68.04 | 100% | 612.36
7.4.3 | Supply and install polyurethane waterpoof coating to internal surfaces of concrete trench | 2026-07-26 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ARC-0065-00 | Supply and install polyurethane waterproof coating to internal surfaces of concrete trench at Building-2, as per highlighted drawing. | Approved | 66 | 19.2 | 100% | 1267.2
7.4.1 | Supply and install liquid applied waterproofing membrane; single-component pitch modified polyurethane based elastomeric high performance waterproofing; applied in multi-coats including sand fill materials for toilets | 2026-07-23 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ARC-0067-00 | Supply and install liquid applied waterproofing membrane at Building-1, as per highlighted drawing. | Approved | 83 | 68.04 | 100% | 5647.32
7.4.2 | Supply and install geotextile sheet | 2026-07-25 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ARC-0068-00 | Supply and install geotextile sheet at Building-1, as per highlighted drawing. | Approved | 9 | 68.04 | 100% | 612.36
7.4.3 | Supply and install polyurethane waterpoof coating to internal surfaces of concrete trench | 2026-07-26 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ARC-0069-00 | Supply and install polyurethane waterproof coating to internal surfaces of concrete trench at Building-1, as per highlighted drawing. | Approved | 66 | 19.2 | 100% | 1267.2
8.1.1 | Supply and install (D6) 3000*3500mm galvanized steel heavy duty industrial isolated type roll up shutter door finished with polyurethane coating, with automatic and manual control system, as per manufacturer specification and approved by the Client, complete with all accessories and fittings, and as per door schedule and specifications | 2026-07-21 | HFR1-05-003-SAK-TS9-1-FIR-ARC-0058-00 | Supply and install (D6) 3000*3500mm galvanized steel heavy duty industrial isolated type roll up shutter door Building-1, as per highlighted drawing. | Approved | 15510 | 12 | 35% | 65142
8.1.2 | Supply and install fire rated 45 min. (D5) 1000*2200mm single leaf steel door with door construction type C with hardware set type HW2 paint finish as per manufacturer detail and approved by the Client with complete accessories as per door schedule, drawings and specification | 2026-07-21 | HFR1-05-003-SAK-TS9-1-FIR-ARC-0060-00 | Supply and install fire rated 45 min. (D5) 1000*2200mm single leaf steel door Building-1, as per highlighted drawing. | Approved | 2750 | 12 | 40% | 13200
8.1.1 | Supply and install (D6) 3000*3500mm galvanized steel heavy duty industrial isolated type roll up shutter door finished with polyurethane coating, with automatic and manual control system, as per manufacturer specification and approved by the Client, complete with all accessories and fittings, and as per door schedule and specifications | 2026-07-21 | HFR1-05-003-SAK-TS9-1-FIR-ARC-0059-00 | Supply and install (D6) 3000*3500mm galvanized steel heavy duty industrial isolated type roll up shutter door Building-2, as per highlighted drawing. | Approved | 15510 | 12 | 35% | 65142
8.1.2 | Supply and install fire rated 45 min. (D5) 1000*2200mm single leaf steel door with door construction type C with hardware set type HW2 paint finish as per manufacturer detail and approved by the Client with complete accessories as per door schedule, drawings and specification | 2026-07-21 | HFR1-05-003-SAK-TS9-1-FIR-ARC-0061-00 | Supply and install fire rated 45 min. (D5) 1000*2200mm single leaf steel door Building-2, as per highlighted drawing. | Approved | 2750 | 12 | 40% | 13200
9.2.1 | Supply and install internal plastering to walls and columns min. 15mm thick with cement mortar of specified grade including galvanized mesh, corner beads, angle beads, CE bonds to rough and smooth plaster complete the work as per drawing & specification. | 2026-07-04 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ARC-0036-00 | Supply and install internal plastering to walls and columns min. 15mm thick with cement mortar of specified grade at Block-2, (Axis-A-N-1/3) as per attached highlighted drawing. | Approved | 31 | 162.08 | 100% | 5024.48
9.2.1 | Supply and install internal plastering to walls and columns min. 15mm thick with cement mortar of specified grade including galvanized mesh, corner beads, angle beads, CE bonds to rough and smooth plaster complete the work as per drawing & specification. | 2026-07-04 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ARC-0037-00 | Supply and install internal plastering to walls and columns min. 15mm thick with cement mortar of specified grade at Block-1, (Axis-A-N-1/3) as per attached highlighted drawing. | Approved | 31 | 162.08 | 100% | 5024.48
9.2.1 | Supply and install internal plastering to walls and columns min. 15mm thick with cement mortar of specified grade including galvanized mesh, corner beads, angle beads, CE bonds to rough and smooth plaster complete the work as per drawing & specification. | 2026-07-16 | FIR-HFR1-05-003-SAK-TS9-1FIR-ARC-0072-00 | Supply and install internal plastering to walls and columns min. 15mm thick with cement mortar of specified grade at Electrical Room 1&2 as per attached highlighted drawing. | Approved | 31 | 24.02 | 100% | 744.62
9.2.2 | Supply and install external plastering to external walls min. 15mm thick with cement mortar of specified grade including galvanized mesh, corner beads, angle beads, CE bonds to rough and smooth plaster complete the work as per drawing & specification. | 2026-07-04 | FIR-HFR1-05-003-SAK-TS9-1FIR-ARC-0071-00 | Supply and install External plastering to walls and columns min. 15mm thick with cement mortar of specified grade at Building-1, (Axis-A-N-1/3) as per attached highlighted drawing. | Approved | 33 | 343.057 | 100% | 11320.881
9.2.2 | Supply and install external plastering to external walls min. 15mm thick with cement mortar of specified grade including galvanized mesh, corner beads, angle beads, CE bonds to rough and smooth plaster complete the work as per drawing & specification. | 2026-07-16 | FIR-HFR1-05-003-SAK-TS9-1FIR-ARC-0072-00 | Supply and install internal plastering to walls and columns min.15mm thick with cement mortar of specified grade at Electrical Room 1&2 as per attached highlighted drawing. | Approved | 33 | 343.057 | 100% | 11320.881
9.2.7 | Supply and install 300*300mm glazed ceramic wall tiles on cement mortar and including rough and smooth plaster, galvanized mesh, corner beads, angle beads, CE bonds (For Toilets) | 2026-07-20 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ARC-0056-00 | Supply and install 300*300mm glazed ceramic wall tiles on cement mortar and including rough and smooth plaster, galvanized mesh, corner beads, angle beads, Building-1, as per highlighted drawing. | Approved | 127 | 166.4504 | 100% | 21139.2008
9.2.7 | Supply and install 300*300mm glazed ceramic wall tiles on cement mortar and including rough and smooth plaster, galvanized mesh, corner beads, angle beads, CE bonds (For Toilets) | 2026-07-21 | FIR-HFR1-05-003-SAK-TS9-1-FIR-ARC-0057-00 | Supply and install 300*300mm glazed ceramic wall tiles on cement mortar and including rough and smooth plaster, galvanized mesh, corner beads, angle beads, Building-2, as per highlighted drawing. | Approved | 127 | 166.4504 | 100% | 21139.2008
2.2.4 | Supply and execute subgrade material up to the full width of the road as per specifications and drawings | 2026-08-08 | HFR1-05-003-SAK-TS9-1FIR-SUV-0143-00 | Supply and execute subgrade material Layer-1 (15cm Sub Base), as per highlighted drawing. | Approved | 66 | 1047.6555 | 100% | 69145.263
2.2.4 | Supply and execute subgrade material up to the full width of the road as per specifications and drawings | 2026-08-19 | HFR1-05-003-SAK-TS9-1FIR-SUV-0144-00 | Supply and execute subgrade material Layer-2 (15cm Sub Base), as per highlighted drawing. | Approved | 66 | 1047.6555 | 100% | 69145.263
2.3.8.1 | Kerb type K1A | 2026-08-02 | HFR1-05-003-SAK-TS9-1-FIR-ARC-0073-00 | Supply and install Kerb type K1A as per attached highlighted drawing. | Approved | 55 | 973.32 | 100% | 53532.6
5.1 | Supply and install steel ladder with safety cage including all necessary fixings, fixtures, painting all as per drawings and specifications. (Height = 5.5m) |  | HFR1-05-003-SAK-TS9-1-FIR- ARC-0074-00 | Supply and install steel ladder with safety cage including all necessary fixings, fixtures. | Approved | 5940 | 2 | 100% | 11880
7.4.4 | Supply and install 4mm thick APP modified bituminous membrane - single layer | 2026-08-08 | FIR-HFR1-05-003-SAK-TS9-1-FIR- ARC-0078-00 | Supply and install 4mm thick APP modified bituminous membrane - single layer, Building-1 roof area, as per highlighted drawing. | Approved | 44 | 100.0937 | 100% | 4404.1228
7.4.4 | Supply and install 4mm thick APP modified bituminous membrane - single layer | 2026-08-08 | FIR-HFR1-05-003-SAK-TS9-1-FIR- ARC-0080-00 | Supply and install 4mm thick APP modified bituminous membrane - single layer, Building-2 roof area, as per highlighted drawing. | Approved | 44 | 100.0937 | 100% | 4404.1228
7.4.4 | Supply and install 4mm thick APP modified bituminous membrane - single layer | 2026-08-16 | FIR-HFR1-05-003-SAK-TS9-1-FIR- ARC-0111-00 | Supply and installing of 4mm thick APP modified bituminous membrane - single layer, Masjid roof area, as per highlighted drawing. | Approved | 44 | 39.3304 | 100% | 1730.5376
7.4.5 | Supply and install 50mm thk rigid insulation (extruded polystyrene) | 2026-08-12 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0083-00 | Supply and install 50mm thk rigid insulation (extruded polystyrene) at Building-1, as per highlighted drawing. | Approved | 61 | 91.08 | 100% | 5555.88
7.4.5 | Supply and install 50mm thk rigid insulation (extruded polystyrene) | 2026-08-12 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0082-00 | Supply and install 50mm thk rigid insulation (extruded polystyrene) at Building-2 roof area, as per highlighted drawing. | Approved | 61 | 91.08 | 100% | 5555.88
7.4.5 | Supply and install 50mm thk rigid insulation (extruded polystyrene) | 2026-08-12 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0096-00 | Supply and install 50mm thk rigid insulation (extruded polystyrene) at Masjid roof area, as per highlighted drawing. | Approved | 61 | 33.6 | 100% | 2049.6
7.4.6 | Supply and cast in place foam concrete screed 50mm thk minimum laid to fall and cross fall | 2026-08-13 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0085-00 | Supply and cast in place foam concrete screed 50mm thk minimum laid to fall and cross fall at Building-2 roof area, as perhighlighted drawing. | Approved | 33 | 91.08 | 100% | 3005.64
7.4.6 | Supply and cast in place foam concrete screed 50mm thk minimum laid to fall and cross fall | 2026-08-13 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0104-00 | Supply and cast in place foam concrete screed 50mm thk minimum laid to fall and cross fall at Masjid (Prayer room), as per highlighted drawing. | Approved | 33 | 91.08 | 100% | 3005.64
7.4.6 | Supply and cast in place foam concrete screed 50mm thk minimum laid to fall and cross fall | 2026-08-13 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0105-00 | Supply and cast in place foam concrete screed 50mm thk minimum laid to fall and cross fall at Masjid (Prayer room), as per highlighted drawing. roof area as per highlighted drawing. | Approved | 33 | 33.6 | 100% | 1108.8
7.4.7 | Supply and install 300 micron polyethylene sheet | 2026-08-10 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0086-00 | Supply and install 300 micron polyethylene sheet at Building-1, roof area as per highlighted drawing. | Approved | 5 | 91.08 | 100% | 455.4
7.4.7 | Supply and install 300 micron polyethylene sheet | 2026-08-10 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0087-00 | Supply and install 300 micron polyethylene sheet at Building-2, roof area as per highlighted drawing. | Approved | 5 | 91.08 | 100% | 455.4
7.4.8 | Supply and install 50mm thk loose gravel toppings | 2026-08-12 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0094-00 | Supply and install Supply and install 50mm thk loose gravel toppings at Roof Area Building-1, as per highlighted drawing. | Approved | 17 | 91.08 | 100% | 1548.36
7.4.8 | Supply and install 50mm thk loose gravel toppings | 2026-08-08 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0093-00 | Supply and install Supply and install 50mm thk loose gravel toppings at Roof Area Building-2, as per highlighted drawing. | Approved | 17 | 91.08 | 100% | 1548.36
7.4.8 | Supply and install 50mm thk loose gravel toppings | 2026-08-12 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0095-00 | Supply and install Supply and install 50mm thk loose gravel toppings at Roof Area Masjid (Prayer room), as per highlighted drawing | Approved | 17 | 33.6 | 100% | 571.2
7.4.9 | Supply and install high density polyisocynurate cover board (12.7mm) | 2026-08-15 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0081-00 | Supply and install high density polyisocynurate cover board (12.7mm) at Roof Area Building-1, as per highlighted drawing. | Approved | 66 | 91.08 | 100% | 6011.28
7.4.9 | Supply and install high density polyisocynurate cover board (12.7mm) | 2026-08-15 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0097-00 | Supply and install high density polyisocynurate cover board (12.7mm) at Roof Area Building-2, as per highlighted drawing | Approved | 66 | 91.08 | 100% | 6011.28
8.1.1 | Supply and install (D6) 3000*3500mm galvanized steel heavy duty industrial isolated type roll up shutter door finished with polyurethane coating, with automatic and manual control system, as per manufacturer specification and approved by the Client, complete with all accessories and fittings, and as per door schedule and specifications |  | HFR1-05-003-SAK-TS9-1-FIR-ARC-0122-00 |  | Approved | 15510 | 24 | 35% | 130284
8.1.2 | Supply and install fire rated 45 min. (D5) 1000*2200mm single leaf steel door with door construction type C with hardware set type HW2 paint finish as per manufacturer detail and approved by the Client with complete accessories as per door schedule, drawings and specification |  | HFR1-05-003-SAK-TS9-1-FIR-ARC-0123-00 |  | Approved | 2750 | 24 | 35% | 23100
8.1.3 | Supply and install (D2) 1000*2200 mm single leaf galvanized steel door with door construction type B with hardware set type HW1 paint finish as per manufacturer detail and approved by the Client with complete accessories as per door/window schedule and as per drawings and specification. | 2026-08-20 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0120-00 | Supply and install (D2) 1000*2200 mm single leaf galvanized steel door with door construction type B with hardware set type HW1 paint finish at Building-1 (axis A-N/1x3), as per highlighted drawing. | Approved | 3355 | 2 | 100% | 6710
8.1.4 | Supply and install (D3) 800*2200 mm single leaf semi solid wood door with door construction type B with hardware set type HW1 paint finish as per manufacturer detail and approved by the Client with complete accessories as per door/window schedule and as per drawings and specification. | 2026-08-20 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0121-00 | Supply and install (D3) 800*2200 mm single leaf semi solid wood door with door construction type B with hardware set type HW1 paint finish at Building-1 (axis A-N/1x3), as per highlighted drawing. | Approved | 2896 | 2 | 100% | 5792
8.1.4 | Supply and install (D3) 800*2200 mm single leaf semi solid wood door with door construction type B with hardware set type HW1 paint finish as per manufacturer detail and approved by the Client with complete accessories as per door/window schedule and as per drawings and specification. | 2026-08-20 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0119-00 | Supply and install (D3) 800*2200 mm single leaf semi solid wood door with door construction type B with hardware set type HW1 paint finish at Building-2 (axis A-N/1x3), as per highlighted drawing. | Approved | 2896 | 2 | 100% | 5792
8.2.1.1 | Window W1 (size 1000*1300) | 2026-08-10 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0090-00 | Window W1 (size 1000*1300) at Building-1, as per highlighted drawing. | Approved | 1111 | 12 | 100% | 13332
8.2.1.1 | Window W1 (size 1000*1300) | 2026-08-10 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0091-00 | Window W1 (size 1000*1300) at Building-2, as per highlighted drawing. | Approved | 1111 | 12 | 100% | 13332
8.2.1.2 | Window W2 (size 1600*1200) | 2026-08-12 | HFR1-05-003-SAK-TS9-1-FIR-ARC-0106-00 | Window W2 (size 1600*1200) Building-1, as per highlighted drawing. | Approved | 1589 | 1 | 100% | 1589
8.2.1.2 | Window W2 (size 1600*1200) | 2026-08-12 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0092-00 | Window W2 (size 1600*1200) Building-2, as per highlighteddra wing. | Approved | 1589 | 1 | 100% | 1589
8.3.1 | Supply and install (D1) 1890*2800mm double leaf glass and aluminum door with CNC decorative stainless steel shapes for mosque including hardware installed on concrete frame with a clear width 2000mm as per manufacturer detail and approved by the Client with complete accessories as per door schedule, drawings and specification | 2026-08-13 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0103-00 | Supply and install (D1) 1890*2800mm double leaf glass and aluminium door with CNC decorative stainless-steel shapes for mosque including hardware installed on concrete frame at Masjid (Prayer room), as per highlighted drawing. | Approved | 6182 | 1 | 100% | 6182
8.4.1.1 | Window W1 (size 1800*2800) | 2026-08-15 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0109-00 | Window W1 (size 1800*2800) at Masjid (Prayer room), as per highlighted drawing. | Approved | 3991 | 2 | 100% | 7982
9.1.1 | Supply and install 300*300mm ceramic tiles with approved quality on 30 mm mortar including sand fill material as approved by the Client for toilets | 2026-08-15 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0107-00 | Supply and install 300*300mm ceramic tiles with approved quality on 30 mm mortar including sand fill, Building-1 (Zone 1 to 4), as per highlighted drawing. | Approved | 110 | 68.04 | 100% | 7484.4
9.1.1 | Supply and install 300*300mm ceramic tiles with approved quality on 30 mm mortar including sand fill material as approved by the Client for toilets | 2026-08-15 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0108-00 | Supply and install 300*300mm ceramic tiles with approved quality on 30 mm mortar including sand fill, Building-2 (Zone 1 to 4), as per highlighted drawing. | Approved | 110 | 68.04 | 100% | 7484.4
9.2.3 | Supply and install 2 coats of acrylic paint at internal walls and roof including one coat of primer and two coats of putty to give smooth Surface as a base for paint including fiberglass tape to joints and all other accessories as per Modon specification and drawings | 2026-07-19 | FIR-HFR1-05-003-SAK-TS9-1FIR-ARC-0052-00 | Supply and install 2 coats of acrylic paint at internal walls and parapet for Building-1 (Axis A-N/ 1-3), as per the attached highlighted drawing | Approved | 28 | 145.28 | 30% | 1220.352
9.2.3 | Supply and install 2 coats of acrylic paint at internal walls and roof including one coat of primer and two coats of putty to give smooth Surface as a base for paint including fiberglass tape to joints and all other accessories as per Modon specification and drawings | 2026-07-19 | FIR-HFR1-05-003-SAK-TS9-1FIR-ARC-0053-00 | Supply and install 2 coats of acrylic paint at internal walls and parapet for Building-2 (Axis A-N/ 1-3), as per the attached highlighted drawing | Approved | 28 | 145.28 | 30% | 1220.352
9.2.4 | Supply and install 2 coats of acrylic paint at external walls and parapet including one coat of primer and two coats of putty to give smooth Surface as a base for paint including fiberglass tape to joints and all other accessories as per Modon specification and drawings | 2026-07-16 | FIR-HFR1-05-003-SAK-TS9-1- FIR-ARC-0049-00 | Inspection Request for External two coats of putty to give smooth Surface as a base for paint at Building-1 (Axis A–N / 1–3), as per the attached highlighted drawing. | Approved | 33 | 343.057 | 30% | 3396.2643
9.2.4 | Supply and install 2 coats of acrylic paint at external walls and parapet including one coat of primer and two coats of putty to give smooth Surface as a base for paint including fiberglass tape to joints and all other accessories as per Modon specification and drawings | 2026-07-16 | FIR-HFR1-05-003-SAK-TS9-1- FIR-ARC-0048-00 | Inspection Request for External two coats of putty to give smooth Surface as a base for paint at Building-2 (Axis A–N / 1–3), as per the attached highlighted drawing. | Approved | 33 | 343.057 | 30% | 3396.2643
9.2.5 | Supply and install layer of marble chips on external walls and grooves to conform with specification requirements to complete the works as per drawing. Color and material is subject for Client approval. | 2026-08-16 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0112-00 | Supply and install layer of marble chips on external walls and grooves at Masjid (Prayer room), as per highlighted drawing. | Approved | 50 | 129.726 | 100% | 6486.3
9.2.8 | Supply and install phenolic partitions with doors for toilets including accessories, fixations, fittings, and all the required works as shown in the drawings and specification with approved quality by the Client |  | HFR1-05-003-SAK-TS9-1-FIR- ARC-0116-00 |  | Approved | 660 | 65 | 100% | 42900
9.2.8 | Supply and install phenolic partitions with doors for toilets including accessories, fixations, fittings, and all the required works as shown in the drawings and specification with approved quality by the Client |  | HFR1-05-003-SAK-TS9-1-FIR- ARC-0117-00 |  | Approved | 660 | 65 | 100% | 42900
9.3.1 | Supply and install 12.5mm thk, moisture resistant gypsum board suspended ceiling including suspension system, paints as required specification and material as approved by the Client including frames supports, access openings and all other accessories to complete as shown in the drawings and specification. (For toilets) | 2026-08-12 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0099-00 | Supply and install 12.5mm thk, moisture resistant gypsum board suspended ceiling including suspension system, paints as required at Building-1, as per highlighted drawing. | Approved | 105 | 68.04 | 100% | 7144.2
9.3.1 | Supply and install 12.5mm thk, moisture resistant gypsum board suspended ceiling including suspension system, paints as required specification and material as approved by the Client including frames supports, access openings and all other accessories to complete as shown in the drawings and specification. (For toilets) | 2026-08-12 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0100-00 | Supply and install 12.5mm thk, moisture resistant gypsum board suspended ceiling including suspension system, paints as required at Building-2, as per highlighted drawing. | Approved | 105 | 68.04 | 100% | 7144.2
9.3.2 | Supply and install 12.5mm thk, gypsum board suspended ceiling including suspension system, paints as required specification and material as approved by the Client including frames supports, access openings and all other accessories to complete as shown in the drawings and specification..(For prayer room) | 2026-08-13 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0102-00 | Supply and install 12.5mm thk, gypsum board suspended ceiling including suspension system at Prayer Room Building-1, as per highlighted drawing. | Approved | 99 | 18 | 100% | 1782
9.3.2 | Supply and install 12.5mm thk, gypsum board suspended ceiling including suspension system, paints as required specification and material as approved by the Client including frames supports, access openings and all other accessories to complete as shown in the drawings and specification..(For prayer room) | 2026-08-13 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0101-00 | Supply and install 12.5mm thk, gypsum board suspended ceiling including suspension system at Prayer Room Building-2, as per hig hli ghted drawing. | Approved | 99 | 18 | 100% | 1782
15.2.7.1 | Supply, install, test and commission Factory-assembled and -tested, vertical packaged booster pump unit, with motor, constant speed drive, all pipework within pump shade and upto field network complete with supports, warning tape, excavation and backfilling, thrust blocks , valves, strainers, sensors, control panel, controls, adjustable-speed-drive units, hydropneumatic tank and all other necessary accessories, connections to tanks and feild network and fittings, cabling & wiring from Control panel to motors & controls as per drawings and specifications. (1W+1S Pumps) - Total flow 5 L/S @ 30 Meters |  | HFR1-05-003-SAK-TS9-1-FIR-MECH-0018-00 |  | Approved | 30800 | 1 | 45% | 13860
15.2.7.1 | Supply, install, test and commission Factory-assembled and -tested, vertical packaged booster pump unit, with motor, constant speed drive, all pipework within pump shade and upto field network complete with supports, warning tape, excavation and backfilling, thrust blocks , valves, strainers, sensors, control panel, controls, adjustable-speed-drive units, hydropneumatic tank and all other necessary accessories, connections to tanks and feild network and fittings, cabling & wiring from Control panel to motors & controls as per drawings and specifications. (1W+1S Pumps) - Total flow 5 L/S @ 30 Meters | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0050-00 | Install of Factory-assembled and -tested, vertical packaged booster pump unit, with motor, constant speed drive, all pipework within pump shade and up to field network complete with supports, warning tape, excavation and backfilling, thrust blocks , valves, strainers, sensors, control panel, controls, adjustable-speed-drive units, hydropneumatic tank and all other necessary accessories, connections to tanks and feild network and fittings, cabling & wiring from Control panel to motors & controls as per drawings and specifications. (1W+1S Pumps) - Total flow 5 L/S @ 30 Meters | Approved | 30800 | 1 | 20% | 6160
15.2.8.1 | Hot Press GRP Sectional Panel Water Tanks (10x8x4m) | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0051-00 | install, test and commission Facility water storage tanks Including overflow, vent, float valves, altitude valves, drain valves, access opening, access ladder, emergency tanker fill and all necessary accessories, connections and fittings as per drawings and specifications, Hot Press GRP Sectional Panel Water Tanks (10x8x4m) | Approved | 275000 | 1 | 30% | 82500
15.5.2.1 | 63 mm Ø (2 1/2" Ø )Cold water | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0052-00 | install and test of PPR SDR 7.4 PN 16, DIN 8077/78 pipes, for cold and hot water supply piping system (Aboveground), complete with fittings, valves and accessories including AAVs, WHA, fiberglass thermal insulation for hot pipes, flushing and all other accessories as per drawings and specifications. 63 mm Ø (2 1/2" Ø )Cold water 50 mm Ø (2" Ø )Cold water 40 mm Ø ( 1 1/2" Ø) Cold water 25 mm Ø ( 1" Ø) Cold water 20 mm Ø ( 3/4" Ø) Cold water 20 mm Ø ( 3/4" Ø) Hot water | Approved | 110 | 21.12 | 20% | 464.64
15.5.2.2 | 50 mm Ø (2" Ø )Cold water | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0052-00 | install and test of PPR SDR 7.4 PN 16, DIN 8077/78 pipes, for cold and hot water supply piping system (Aboveground), complete with fittings, valves and accessories including AAVs, WHA, fiberglass thermal insulation for hot pipes, flushing and all other accessories as per drawings and specifications. 63 mm Ø (2 1/2" Ø )Cold water 50 mm Ø (2" Ø )Cold water 40 mm Ø ( 1 1/2" Ø) Cold water 25 mm Ø ( 1" Ø) Cold water 20 mm Ø ( 3/4" Ø) Cold water 20 mm Ø ( 3/4" Ø) Hot water | Approved | 99 | 22.8 | 20% | 451.44
15.5.2.3 | 40 mm Ø ( 1 1/2" Ø) Cold water | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0052-00 | install and test of PPR SDR 7.4 PN 16, DIN 8077/78 pipes, for cold and hot water supply piping system (Aboveground), complete with fittings, valves and accessories including AAVs, WHA, fiberglass thermal insulation for hot pipes, flushing and all other accessories as per drawings and specifications. 63 mm Ø (2 1/2" Ø )Cold water 50 mm Ø (2" Ø )Cold water 40 mm Ø ( 1 1/2" Ø) Cold water 25 mm Ø ( 1" Ø) Cold water 20 mm Ø ( 3/4" Ø) Cold water 20 mm Ø ( 3/4" Ø) Hot water | Approved | 83 | 40.14 | 20% | 666.324
15.5.2.4 | 25 mm Ø ( 1" Ø) Cold water | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0052-00 | install and test of PPR SDR 7.4 PN 16, DIN 8077/78 pipes, for cold and hot water supply piping system (Aboveground), complete with fittings, valves and accessories including AAVs, WHA, fiberglass thermal insulation for hot pipes, flushing and all other accessories as per drawings and specifications. 63 mm Ø (2 1/2" Ø )Cold water 50 mm Ø (2" Ø )Cold water 40 mm Ø ( 1 1/2" Ø) Cold water 25 mm Ø ( 1" Ø) Cold water 20 mm Ø ( 3/4" Ø) Cold water 20 mm Ø ( 3/4" Ø) Hot water | Approved | 55 | 26.76 | 20% | 294.36
15.5.2.5 | 20 mm Ø ( 3/4" Ø) Cold water | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0052-00 | install and test of PPR SDR 7.4 PN 16, DIN 8077/78 pipes, for cold and hot water supply piping system (Aboveground), complete with fittings, valves and accessories including AAVs, WHA, fiberglass thermal insulation for hot pipes, flushing and all other accessories as per drawings and specifications. 63 mm Ø (2 1/2" Ø )Cold water 50 mm Ø (2" Ø )Cold water 40 mm Ø ( 1 1/2" Ø) Cold water 25 mm Ø ( 1" Ø) Cold water 20 mm Ø ( 3/4" Ø) Cold water 20 mm Ø ( 3/4" Ø) Hot water | Approved | 44 | 124.88 | 20% | 1098.944
15.5.2.6 | 20 mm Ø ( 3/4" Ø) Hot water | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0052-00 | install and test of PPR SDR 7.4 PN 16, DIN 8077/78 pipes, for cold and hot water supply piping system (Aboveground), complete with fittings, valves and accessories including AAVs, WHA, fiberglass thermal insulation for hot pipes, flushing and all other accessories as per drawings and specifications. 63 mm Ø (2 1/2" Ø )Cold water 50 mm Ø (2" Ø )Cold water 40 mm Ø ( 1 1/2" Ø) Cold water 25 mm Ø ( 1" Ø) Cold water 20 mm Ø ( 3/4" Ø) Cold water 20 mm Ø ( 3/4" Ø) Hot water | Approved | 55 | 96.58 | 20% | 1062.38
15.5.3.1 | 63 mm Ø | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0053-00 | Install & test of Ball Valve, 63 mm Ø, 50 mm Ø, 40 mm Ø | Approved | 715 | 4 | 20% | 572
15.5.3.2 | 50 mm Ø | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0053-00 | Install & test of Ball Valve, 63 mm Ø, 50 mm Ø, 40 mm Ø | Approved | 550 | 4 | 20% | 440
15.5.3.3 | 40 mm Ø | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0053-00 | Install & test of Ball Valve, 63 mm Ø, 50 mm Ø, 40 mm Ø | Approved | 440 | 4 | 20% | 352
15.5.5.1 | 63 mm Ø | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0054-00 | Installation of foundation,walls,roof ,insulation & backfilling valve box 80*80 cm 63 mm Ø 50 mm Ø | Approved | 1320 | 4 | 20% | 1056
15.5.5.2 | 50 mm Ø | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0054-00 | Installation of foundation,walls,roof ,insulation & backfilling valve box 80*80 cm 63 mm Ø 50 mm Ø | Approved | 1100 | 24 | 20% | 5280
15.6.6.1 | Supply, install, test and commission electric water heater (EWH-1) horizontal type, 50 Liters SASO certified, complete with mounting bracet, angle valves and all other accessories as per drawings and specification. | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-MECH-0055-00 | install, test and commission electric water heater (EWH-1) horizontal type, 50 Liters SASO certified, complete with mounting bracet, angle valves and all other accessories as per drawings and specification. | Approved | 605 | 4 | 100% | 2420
16.3.5 | 4C x 16mm2 +1C x 10mm2 | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-ELE-0027-00 | Installation of 4C x 16mm2 +1C x 10mm2 cable | Approved | 66 | 578.48 | 100% | 38179.68
16.6.1 | 4C x 185 mm2 +1C x 95mm2 | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-ELE-0018-00 | install, of low voltage Copper Cables 4C x 185 mm2 +1C x 95mm2 | Approved | 514 | 1938 | 65% | 647485.8
16.7.2 | Covered Cable Tray |  | HFR1-05-003-SAK-TS9-1- FIR-ELE-0030-00 |  | Approved | 275 | 252.5 | 70% | 48606.25
16.13.1 | Lightning Protection System for each block | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-ELE-0029-00 | INSTALLATION OF LIGHTNING SYSTEM | Approved | 40728 | 3 | 100% | 122184
16.17.1 | Skylight fixtures | 2026-08-13 | HFR1-05-003-SAK-TS9-1- FIR-ELE-0028-00 | INSTALLATION OF skylight fixtures including all accessories | Approved | 3300 | 48 | 100% | 158400
7.4.9 | Supply and install high density polyisocynurate cover board (12.7mm) | 2026-08-15 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0098-00 | Supply and install high density polyisocynurate cover board (12.7mm) at Roof Area Masjid (Prayer Room), as per highlighted drawing. | Approved | 66 | 33.6 | 100% | 2217.6
7.4.10 | Supply and install geotextile sheets (200 g/m2) | 2026-08-16 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0113-00 | Supply and install geotextile sheets (200 g/m2) at Building-1, as per highlighted drawing. | Approved | 17 | 91.08 | 100% | 1548.36
7.4.10 | Supply and install geotextile sheets (200 g/m2) | 2026-08-16 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0114-00 | Supply and install geotextile sheets (200 g/m2) at Building-2, as per highlighted drawing | Approved | 17 | 91.08 | 100% | 1548.36
7.4.10 | Supply and install geotextile sheets (200 g/m2) | 2026-08-16 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0115-00 | Supply and install geotextile sheets (200 g/m2) at Masjid roof area, as per highlighted drawing. | Approved | 17 | 33.6 | 100% | 571.2
7.5 | Supply and install aluminium cladding where material is approved by the Client, including sub-frames, all accessories and fittings, and whatever needed to do perfect work all as per drawing and specification. | 2026-08-12 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0089-00 | Supply and install aluminium cladding where material is approved by the Client, including sub-frames, all accessories and fittings at Building-1, as per highlighted drawing. | Approved | 352 | 360.11 | 100% | 126758.72
7.5 | Supply and install aluminium cladding where material is approved by the Client, including sub-frames, all accessories and fittings, and whatever needed to do perfect work all as per drawing and specification. | 2026-08-12 | HFR1-05-003-SAK-TS9-1-FIR- ARC-0088-00 | Supply and install aluminium cladding where material is approved by the Client, including sub-frames, all accessories and fittings at Building-2, as per highlighted drawing. | Approved | 352 | 360.11 | 100% | 126758.72
0
Total Amount for the Period | [8 empty] | 11743680.0968 | 71.19%

## Conclusion
مشروع إنشاء وحدات الحرفيين الصناعية بحفر الباطن
معلومات المشروع |  |  |  |  | نطاق المشروع | [5 empty] | موقع المشروع
المقاول | شركة صروح الخير للمقاولات العامة | الاستشاري | شركة ايجيس السعودية للاستشارات |  | البند | وحدة القياس | الكمية الكلية | الكمية المنفذة | الكمية المتبقية | نسبة المنفذ
تاريخ استلام الموقع | 2025-11-27 | مدة التنفيذ | 10 شهرًا ميلاديًا |  | Backfilling | م3 | 20258.76 | 14724.77 | 5533.99 | 72.68%
بداية العقد | من تاريخ استلام الموقع | قيمة العقد | #REF! | #REF! | Footing | م3 | 232.38 | 232.38 | 0 | 100%
نسبة الإنجاز المخطط له | 99.55% | نسبة الإنجاز الفعلي | 98.15% |  | Pedestal | م3 | 96.06 | 96.06 | 0 | 100%
|  | 16496856 |  |  | Grade Beam | م3 | 107.98 | 107.98 | 0 | 100%
ملخص جدول الكميات |  |  |  |  | Slab on Grade | م3 | 559.36 | 559.36 | 0 | 100%
مكونات المشروع |  | التكلفة (غير شامل ضريبة القيمة المضافة) | النسبة الاجمالية |  | Steel Structures | عدد | 2 | 2 | 0 | 100% |  | 20865877 | 20423520.4076
أعمال الموقع |  | 1700281 | 10.31% |  | AAC Panels | م2 | 126.2 | 126.2 | 0 | 100% |  | 10508920 | 10286130.896
أعمال الخرسانة والمباني |  | 1487094 | 9.014% |  | Sandwich Panels | عدد | 2 | 2 | 0 | 100% |  | 23728460 | 23225416.648
الأعمال المعدنية |  | 103488 | 0.6273% |  | CMU Blocks | م2 | 783.36 | 783.36 | 0 | 100%
أعمال العزل الحراري والمائي |  | 379274 | 2.299% |  | Shutter door | عدد | 24 | 24 | 0 | 100%
أعمال الأبواب والشبابيك |  | 517138 | 3.135% |  | Steel door | عدد | 24 | 24 | 0 | 100%
أعمال التشطيبات |  | 502112 | 3.044% |  | Pump Shed | عدد | 1 | 1 | 0 | 100%
الأعمال الخاصة |  | 157080 | 0.9522% |  | Pumps | عدد | 2 | 0.95 | 1.05 | 47.5% | تقدم أعمال layout | 7970089 | 7801123.1132
أعمال منشأت سابقة الهندسة |  | 2851126 | 17.28% |  | ملخص التوريدات | [6 empty] | 8842925 | 8655454.99
الأعمال الميكانيكية |  | 2114939 | 12.82% |  | البند | الكمية الكلية | الكمية المورده | الكمية المتبقية |  | نسبة التوريد
الأعمال الكهربائية |  | 6684324 | 40.52% |  | Road | 460 | 0 | 0 |  | 0%
[5 empty] | GRP Pipe | 344 | 344 | 0 |  | 100%
[5 empty] | Portable Water Supply | 612 | 612 | 112 |  | 100%
[5 empty] | Fire Fighting | 138 | 138 | 60 |  | 100%
[5 empty] | LV Power cable | 1500 | 1200 | 300 |  | 100%
[5 empty] | Low Current Cable | 750 | 750 | 400 |  | 100%
معالم البرنامج الزمني
البند |  | التاريخ حسب الجدول الزمني | ملاحظة
نهاية الشروع |  | 2026-09-26
بداية المشروع |  | 2025-11-27
Site General Works |  | 2026-03-22 | Complete |  |  |  | 0 | 0
Hunger 1 |  | 2026-09-26 | Progress |  |  |  |  | 0
Hunger 2 |  | 2026-09-26 | Progress |  | التحديات والعوائق
Septic Tank |  | 2026-06-28 | Complete |  |  |  | الإجراء التصحيحي | التحديات والعقبات
Mosque- Elec and Toilet |  | 2026-07-27 | Progress |  |  |  | سوف يتم زيادة العمالة خلال الفترة القادمة | الحاجة إلى زيادة القوى العاملة
GRP Tank |  | 2026-08-12 | Complete
Pump Room |  | 2026-07-20 | Progress
External MEP Work |  | 2026-06-02 | Progress
Testing and Commission |  | 2026-09-26 | Progress
موقع المشروع
موقع المشروع
تم الانتهاء من اعمال الحفر و لاساسات
مرحلة التركيبات المعدنية

## Codes (hidden)
Status List
| Approved |  | Y
| Pending |  | N | [5 empty] | (Manhours)
| Potential | [7 empty] | (Mandays)
| Phase | Stage |  | Stage |  | Status |  | Score
[8 empty] | Low | Contractor | Active
| Launch | LOA |  | LOA |  | Active |  | Medium | CM | Expired
| Launch | Kick-off Meeting |  | Kick-off Meeting |  | On Hold |  | High | PgM | Occurred
| Launch | Site Handover |  |  |  | Terminated |  |  | Modon | Pending
| Launch | Mobilization |  | Mobilization | Initial staff and equipment in place, ready to start production | Terminated, Closed |  |  | Other
| Execution | Construction |  | Execution | Tender Documents Issued | Substantial Complete | Initial Handover done at site
| Execution | T&C |  |  | Responses to the OCS completed | Complete | Initial Handover Signed
| Execution | Initial Handover |  | Closeout | Design close-out process complete | Closed | Final Handover done at Site
Warranty Period
Final Handover
Project Status Score
Elements |  |  | Max | Score | Planned | Actual | Remarks
SPI (Physical Effort) |  |  | 100% | 98.29% | No Entry Required
SPI (Cost) |  |  | 100% | 98.62% | No Entry Required
On Schedule -Active |  |  | 100% | 107.5% | No Entry Required |  |  |  | 0.6
Manpower Availability |  |  | 100% | 170.6% | No Entry Required
Major Equipment Availability |  |  | 100% | 100% | No Entry Required
Billing % Compared to Planned |  |  | 100% | 2.634% | No Entry Required
Safety Score |  |  | 100% | 75.5% | No Entry Required
Quality Score |  |  | 100% | #REF! | No Entry Required