## Slide 1: Weekly Progress Report – Construction Projects
Projects Department

## Slide 2: Disclaimer
This report is not all inclusive, nor it is intended to address the entirety of construction progress. It is concerned primarily with construction progress and is intended to provide near term management information. The report itself serves as the Agenda for the weekly/Biweekly/Monthly or as required progress meetings.

## Slide 3: Introduction

## Slide 4: Introduction
Purpose
This report is to be prepared by the construction contractor and submitted to the Construction Consultant and MODON Project Manager before 12:00 PM on every Wednesdays with Progress data cut off date is Tuesday. The premise behind this report and the key to successfully managing projects is to update schedules weekly.
Calendar
The complete report will serve as the agenda for the weekly site meetings. The Construction Manger will chair the meeting. Attendance shall be limited to essential personnel only. Construction Contractor, appropriate Contractor staff, Construction Manager, Program Manager, and MODON Project Manager shall be in attendance.
Minutes of Meeting will be taken by the Construction Manager and submitted to the Program Manager (If Applicable) within 48 hours. Minutes shall describe attendance, the conduct of the meeting, discussion items, and problem resolutions, and shall provide action items with responsible parties and due dates.
Construction Manager shall maintain the Action Items Register. At subsequent meetings, open action items shall be discussed first.

## Slide 5: Weekly Progress Report Dashboard
Summary Dashboard
Weekly Progress Report Dashboard is an outcome for completing all the sheets within the weekly progress report file.
No manual input is needed for the summary sheet.
It is important that sheets should not be deleted or replaced. All input should be entered manually as a part of weekly update.

## Slide 6: Weekly Progress Report Attachment
Weekly Progress Report Attachement
Contractor/Consultant should ensure that the weekly progress report are supported with required attachment.
Those attachment should include the following as a minimum requirement:
Approved Primavera P6 Schedule in xer format.
3-5 latest progress photographs in JPG format
Updated Primavera P6 schedule in .xer format & PDF Format Three weeks look ahead in PDF format. (as per plf link)
Remaining Works in PDF format.
Any other supporting document required per the development of the project.

## Slide 7: Weekly Report Areas / Sections

## Slide 8: Weekly Report Areas / Sections
Contract General Information
Key Dates
Progress Overview
Construction Milestones
Submittals Status
Material Approval Status
HSE
Invoices
Shop Drawing Status
Resources at Site
Primavera P6 Schedule Status
Contract Change Order Log
Major Quantity Trackers
Testing And Commissioning
Top Issues
Quality

## Slide 9: Weekly Report Areas / General Information
Contract General Information
Project Name: Factories Low- Process Unit (HAFR Al BATIN)
Project ID: HFR1-05-003
Contractor: SOROH AL KHAIR CONTRACTING CO.
Consultant: EGIS
Stage: Construction
Status: Active.
MODON PM: Eng. Mohammad Al Essa

## Slide 10: Weekly Report Areas / Dates
Key Dates
Contract Award Date: 15 Oct 2025
Contract Sign Date: 16 Nov 2025
Site Handover Date: 27 Nov 2025
Original Completion: 26 Sep 2026
Revised Completion Date: 26 Sep 2026
Committed Completion Date: 29 Oct 2026
Forecast Completion: 07 Nov 2026
Variance: 42

## Slide 11: Weekly Report Areas / Dates
Key Dates
Quality Plan submission: 10 Jan 2026
Quality Plan approval: 25 Mar 2026
Quality Plan Last Update: 25 Mar 2026
Safety Plan submission: 30 Dec 2025
Safety Plan approval: 22 Sep 2026
Safety Plan Last Update: --
Risk Management Plan submission: 30 Dec 2025
Risk Management Plan approval: 22 Sep 2026
Risk Management Plan Last Update: --
Baseline Schedule submission: 29 Dec 2025
Baseline Schedule approval: 7 Mar 2026
No of Schedule Versions: 2
Last Schedule Approval Date: --
BOQ submission: 01 Jan 2026
BOQ approval: 16-May-2026
No of Approved Version of BOQ: --
Construction Plan submission : 22 Sep 2026
Construction Plan Approval : --

## Slide 12: Weekly Report Areas / Progress
Progress Overview
WBS: Deliverables as per Modon Work Breakdown Structure (WBS) and WBS dictionary (Same in P6)
BoQ Value (SAR) Value of every WBS element so that total value is equal to the current approved value of the current.
%Wt.: No Entry required – Percentage of each WBS item based on total contract value.
Weekly Planned: Weekly Planned Value of the element derived from scheduling software
Weekly Earned: Weekly Value of the deliverables accomplished, derived from scheduling software
ToDate Planned: ToDate Planned Value of the element derived from scheduling software
ToDate Earned: ToDate Value of the deliverables accomplished, derived from scheduling software
Provide the project scope statement and WBS deliverable information. Note that you WBS details can be broken to the convenient level as required and agreed with Modon PM. A precaution is required as this is linked to summary dashboard. Avoid deleting WBS-Level 1 rows any number of rows can be added in WBS Level-2 sections. Check with Modon Project controls if further clarity is required.

## Slide 13: Weekly Report Areas / Progress
Progress Overview
Budgeted Effort (Manhours): Total Manhours/Mandays planned per WBS and loaded in P6. Select from Manhours/Mandays drop down list as applicable.
%Wt.: No Entry required – Percentage of each WBS item based on total manhours/mandays.
Weekly Planned: Weekly Planned effort of the element derived from scheduling software
Weekly Earned: Weekly effort of the deliverables accomplished, derived from scheduling software
ToDate Planned: ToDate Planned effort of the element derived from scheduling software
ToDate Earned: ToDate effort of the deliverables accomplished, derived from scheduling software

## Slide 14: Weekly Report Areas / Progress
Progress Overview
Following Cumulative Curves should be plotted; Value (SAR) in %age against Time for:
Base line or Original Plan
Revised Plan (Only if EOT/CO is approved by MODON through change management)
Earn Value for the work accomplished
Forecast Curve
Gross Paid Value (Invoices)
Note that the data entry for the curves is in sheet named “EV-Chart Data”. All the four curves should have data from P6 except for the invoices those should be entered manually every month.
Chart: Earned Value - Cost
| 45991 | 46022 | 46053 | 46081 | 46112 | 46142 | 46173 | 46203 | 46234 | 46265 | 46295 | 46326 | 46356 | 46387 | 46418 | 46446 | 46477 | 46507 | 46538 | 46568 | 46599 | 46630
Baseline Plan | 0 | 0.00010475 | 0.053937 | 0.083638 | 0.25131 | 0.54084 | 0.6821 | 0.81392 | 0.89485 | 0.93657 | 1
Revised / Recovery Plan
Earned Value | 7.856e-05 | 0.062143 | 0.12072 | 0.24032 | 0.51983 | 0.64583 | 0.74617 | 0.83901 | 0.92083 | 0.98173
Forecast | 0.71917 | 0.76551 | 0.8406 | 0.87101 | 0.91521 | 0.94798 | 0.99781 | 1
Gross Paid Value | 0.1 | 0.1 | 0.1 | 0.11707 | 0.11707 | 0.11707 | 0.30258 | 0.30258 | 0.62994 | 0.74787

## Slide 15: Weekly Report Areas / Progress
Progress Overview
Following Cumulative Curves should be plotted; Labor units in %age against Time for:
Base line or Original Plan Effort (Manhours/Mandays whatever is applicable)
Revised Plan (Only if EOT/CO is approved by MODON (Manhours/Mandays whatever is applicable)
Earned manhour or mandays for the work accomplished. (Not the Actual manhours or mandays spent on site)
Forecast Curve for the remaining period of time
Note that the data entry for the curves is in sheet named “Physical-Chart Data”. All the four curves should have data from P6.
Chart: Physical Progress - Effort
| 45991 | 46022 | 46053 | 46081 | 46112 | 46142 | 46173 | 46203 | 46234 | 46265 | 46295 | 46326 | 46356 | 46387 | 46418 | 46446 | 46477 | 46507 | 46538
Baseline Plan | 0.0037454 | 0.051112 | 0.10422 | 0.15384 | 0.29526 | 0.48538 | 0.61895 | 0.7453 | 0.89656 | 0.9396 | 0.99999
Revised / Recovery Plan
Earned Effort % | 0.0042229 | 0.042086 | 0.10192 | 0.17313 | 0.33446 | 0.48611 | 0.57382 | 0.65952 | 0.78395 | 0.90239 | 0.98015
Forecast | 0.64063 | 0.7428 | 0.82619 | 0.86989 | 0.91191 | 0.95243 | 0.9916 | 0.99999

## Slide 16: Weekly Report Areas / Milestones
Construction Milestones
Contractor to list all important milestones upon agreement with consultant and MODON to track the status of such milestones. The construction milestones should be included into P6 data and information should extracted weekly.
Status should be update manually for Actuals as “A” and forecast as “F”

## Slide 17: Weekly Report Areas / Submittals
Submittals Status
Contractor should be able to determine all the shop drawing needed for the project and categorize it into disciplines or per approved WBS.
Total : 266
Total Processed Drawings Codes (A,B,C,D) : 266
Remaining Drawings: 0
Pending Submittal with Consultant: 0
Total Submittals:266

## Slide 18: Weekly Report Areas / Shop Drawings
Shop Drawings
Contractor should be able to determine all the shop drawing needed for the project and categorize it into disciplines or per approved WBS.
Total : 266
Total Processed Drawings Codes (A,B,C,D) : 266
Remaining Drawings: 0
Pending Submittal with Consultant: 0
Total Submittals: 266

## Slide 19: Weekly Report Areas / Materials
Material Approval
Contractor should be able to determine all the material that will require prior approval for the project and categorize it into disciplines or per approved WBS.
Total : 86
Total Processed Material Codes (A,B,C,D) : 84
Remaining to Approve: 0
Pending Submittal with Consultant: 2
Total Submittals: 86

## Slide 20: Weekly Report Areas / Quality
Quality Reports
This section is designed to track the number and status of Non Conformance Report (NRC), Site Instructions (SI), Material Inspection Reports (MIR) and Field Inspection Reports (FIR).
Issued : Total items issued by contractor/consultant.
Closed : Total items that has been addressed properly and closed by consultant.
Pending: Total items that are pending action with contractor/consultant that require further action to be properly closed.
Average Closing in Days: This should calculate the actual average duration to close the items in the closed category .
Pending (Duration): This should calculate the pending items status in terms of duration elapsed within contractor/consultant.

## Slide 21: Weekly Report Areas / Quality
Quality Audit
QC Observation checklist is an audit that PMC consultant will conduct and issue on a weekly basis.
Contractor is required to take the quality control observation checklist and reflect it into the weekly report on weekly basis.
Also, contractor should maintain a log for all weekly audits score and duration required to close all comments.
Note that the Quality checklist may get updated from Modon Quality department from time to time. Site planner to confirm with Modon Project Controls if he has the latest checklist

## Slide 22: Weekly Report Areas / HSE
Health, Safety & Environmental (HSE)
Total Hours Worked: Total Man-hours worked.
Safe Hours Worked: Total Safe Man-hours worked Reported Incidents
Total Manpower: The average number of available manpower on site.
Near Misses: The number of near misses occurred at the project.
Lost Working Days: The number of Lost Working Days occurred at the project.
Fatalities: Fatalities occurred in the project.
Environmental Incident: The number of Lost Working Days occurred at the project.
Medical Treatment: The number of Medical treatment occurred at the project.
Fire Incident Cases: The number of Fire Incident Cases occurred at the project.
Property Damage Cases: The number of Property Damage Cases occurred at the project.
Safety Trainings: The number of Safety Trainings Conducted at the project.
Induction Training: The number of Induction training at the project.
Toolbox Talks: The number of Toolbox talks occurred at the project.
Award Recognition: The number of Award recognition at the project.
Inspection Conducted by Consultant: The number of inspection conducted by PMC consultant at the project.
Inspection Conducted by Client: The number of inspection conducted by client or client representative at the project.

## Slide 23: Weekly Report Areas / HSE
Health, Safety & Environmental (HSE) Audits
HSE Site Inspection Report is an audit that PMC consultant will conduct and issue on a weekly basis.
Contractor is required to take the HSE Inspection Report Summary sheet and reflect it into the weekly report on weekly basis.
Also, contractor should maintain a log for all weekly audits score and duration required to close all comments.
Note that the HSE checklist may get updated from Modon Safety department from time to time. Site planner to confirm with Modon Project Controls if he has the latest checklist

## Slide 24: Weekly Report Areas / Invoices
Invoice Log
Invoice Log will contain the details of each invoice submitted to MODON
Gross Value : Gross Value of the invoice
AP Recovery: Advance Payment recovery deducted from the invoice.
Retention: Retention recovered from the invoice.
Deduction/Penalties: amount of deduction or penalties have been applied to the invoice.
Amount (Net): Calculated automatically based on gross value and all deductions.
Start/End Date: Period of the invoice
Date to CM: Date the contractor sent the invoice to consultant for approval.
CM Approval: Dropdown list (Y/N). If consultant approved the invoice should show “Y”. Otherwise, “N”.
CM Reply Date: Consultant approval date.
Date to PM: Date the consultant sent the invoice to MODON for approval.
PM Approval: Dropdown list (Y/N). If MODON PM approved the invoice should show “Y”. Otherwise, “N”.
PM Reply Date: MODON PM approval date.
Date to Accounts: Date sent the invoice to accounts for processing.
Account Approval: Dropdown list (Y/N). If MODON accounts approved the invoice should show “Y”. Otherwise, “N”.
Account Reply Date: MODON Account approval Date.
Amount Paid: Amount paid to the contractor.
Remarks: Any remarks related to the invoice.

## Slide 25: Weekly Report Areas / Invoices
Invoice Summary
Invoice Summary will contain the details of each invoice submitted to MODON.
Original Contract Value: The original contract value for construction works (Not including O&M).
Revised Contract Value : The revised contract value for construction works if there are any change in the contract value.
Estimated Completion Value: The forecast completion value.
O&M Value: Value of Operation and Maintenance if any.
Revised O&M Value: The revised Operation and Maintenance value if there are any change in the contract value.
Advance Payments: Total percentage of the advance payment relative to the contract value.
Retention: Total percentage of the retention value relative to the contract value.
Remaining cells will be automatically calculated based on the information provided in the detail invoice log.

## Slide 26: Weekly Report Areas / CCOs
Contract Change Orders (CCOs)
This will enable the contractor to maintain high-level log of the contract changes to the contract.
Date Added.: Date submitted to MODON.
Description of Change: Should include a brief description of the changes and the reason for the change.
Status: Status of the CCO, dropdown list “Approved, Pending and Potential”.
SR: Cost of change order.
Schedule Impact: Duration of the change order in Months.
Date Approved: Date of CCO approval from MODON officially.
Duration: Calculated cell with no input required.

## Slide 27: Weekly Report Areas / Quantities
Major Quantity Trackers
Identify major quantities to be tracked for the successful completion of project. This list can be agreed with MODON PM / CM at site. Provide the total quantity of the item, the plan to date and actual to date and remaining of the item at site along with the unit of measurement (UOM)

## Slide 28: Weekly Report Areas / Resources
Resources
Manpower will be tracked per the approved plan to include manual and non-manual and will also monitor the actual average manpower with a forecast till the completion of the project. It will also include the manpower by craft or category (man-hours, man-days, crews, etc.) from approved primavera schedule.
Note that the actual data are not man days, it will be average per month.
Equipment will be similar to the manpower. However, it will include in the table how many equipment at site are idle.
Chart: MANUAL MANPOWER HISTOGRAM
| 45664 | 45716 | 45747 | 45777 | 45808 | 45838 | 45869 | 45900 | 45930 | 45961 | 45991 | 46022 | 46053 | 46081 | 46112 | 46142 | 46173 | 46203 | 46234 | 46265 | 46295
Plan - Monthly | 0 | 3 | 32 | 49 | 61 | 89 | 92 | 81 | 76 | 57 | 34
Actual - Monthly | 15 | 21 | 22 | 30 | 35 | 51 | 54 | 67 | 57 | 63 | 58
Forecast - Monthly | 0 | 18 | 17 | 40 | 53 | 75 | 82 | 85 | 81 | 75 | 72
Chart: EQUIPMENT HISTOGRAM
| Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26
Plan - Monthly | 0 | 11 | 18 | 18 | 23 | 24 | 26 | 22 | 17 | 16
Actual - Monthly | 0 | 5 | 8 | 14 | 8 | 13 | 16 | 15 | 12 | 11 | 13
Forecast - Monthly | 10 | 16 | 18 | 24 | 20 | 21

## Slide 29: Weekly Report Areas / Schedule Status
Primavera P6 Schedule Status
Schedule Statistics
Total Act: The number activities in the schedule
Not Started The number of activities not started yet (from P6 schedule run report)
In Progress: The number activities in the schedule that have been started, but not completed. (from P6 schedule run report)
Completed: Then number of activities completed so far. (from P6 schedule run report)
Active Schedule Activities
Active: The number of activities in progress (same as above; no entry required)
Ahead: Total number of activities ahead of schedule
On/Behind: Number of activities on schedule / Behind schedule
Critical Path Activities
Last Week: The number of activities on the critical path up to the last week (Cumulative)
This Week: The number of activities on the critical path up to this week. (Cumulative)
Free Float Management
Greater than 14 days: The number of activities with free float greater than 14 days for last week and this week.
Less than 14 days: The number of activities with free float less than 14 days for last week and this week.
Failed Starts
Last Week: Total activities failed to start as planned until last week.
This Week: Total activities failed to start as planned until this week.
Min.Float: Minimum Float value of any of the activity in the schedule i.e (Maximum negative float of any activity)

## Slide 30: Weekly Report Areas / Testing and Commissioning
Testing And Commissioning
Testing and Commissioning items should be agreed upon at the start of the project between the contractor/consultant and MODON.
It should include the planned start and finish dates originally from approved baseline schedule. Contractor will be updating the forecast/actual start and finish dates per the development of the project.
Also, when the system testing has started, it is important to maintain the progress completion percentage of the whole system and the punch list status.

## Slide 31: Weekly Report Areas / Issues
Active Issues
Issue Log will contain the top five active issues that are critical to the project and it should be extracted on weekly basis from the risk registrar.
Date Identified: Date of which the issue has been identified.
Issue description: a brief description of the issue and should identify the cause of the issue.
Responsibility: Dropdown list for responsible party.
Action Taken: The action that contract/consultant/MODON has taken to resolve the issue.
Mitigation: The recommended course of action to mitigate the current issue.
Current Status: Dropdown list for current status.
Expected/Actual Closure: Forecast/Actual date of issue closure.
Duration Elapsed: Automatically calculated cell based date identified and actual closure date.
.

## Slide 32: شكراً