## Sheet1
Failed Start List
Project: Factories Low-process Unit (HAFR Al Batin)
2026-09-14
# | P6 Activity ID | P6 Activity Description | Planned Start | Forecast Start | Variance | Remarks
1 | HFR1-05-4380 | Procurement Complete |  |  | 0 | Not required
2 | HFR1-05-2990 | Completion of Engneering and Material |  |  | -73 | Not required
3 | HFR1-05-4590 | Site Works & External Networks Completed |  |  | -73 | Not required
4 | HFR1-05-4620 | Main Buildings Architectural Completed |  |  | -73 | Not required
5 | HFR1-05-3390 | Main Buildings Structure Completed |  |  | -73 | Not required
6 | HFR1-05-4400 | Mosque Works Completed |  |  | -71 | Not required
7 | HFR1-05-5570 | Material Delivery for Aggregate Base Course | 2026-01-29 | 07-Sep-26 A | -71 | Not required
8 | HFR1-05-9130 | Material Delivery for Pavement Markings | 2026-05-24 | 01-Sep-26 A | -71 | Not required
9 | HFR1-05-9390 | Material Delivery for Logo | 2026-04-22 | 10-Aug-26 A | -71 | Not required
10 | HFR1-05-2730 | External Paint Touch-up & Inspection | 2026-05-30 | 06-Aug-26 A | -25 | Not required
11 | HFR1-05-2630 | External Paint Primer + Final Coat | 2026-05-03 | 06-Aug-26 A | -72 | Not required
12 | HFR1-05-2640 | Epoxy Paint | 2026-05-03 | 15-Aug-26 A | -72 | Not required
13 | HFR1-05-2690 | Cladding | 2026-05-19 | 10-Aug-26 A | -72 | Not required
14 | HFR1-05-2600 | Paint Primer + Putty + Final Coat INSIDE | 2026-04-25 | 24-Aug-26 A | -69 | Not required
15 | HFR1-05-2820 | Specialites Fittings | 2026-07-13 | 01-Sep-26 A | -69 | Not required
16 | HFR1-05-2790 | Signage Layout & Marking Locations | 2026-07-07 | 03-Sep-26 A | -69 | Not required
17 | HFR1-05-2770 | Metal works | 2026-07-01 | 06-Jul-26 A | -69 | Not required
18 | HFR1-05-2720 | Finishes floor Installation | 2026-05-20 | 09-Jul-26 A | -69 | Not required
19 | HFR1-05-2900 | Testing plumping system & Final Inspection | 2026-09-06 | 04-May-26 A | -162 | Not required
20 | HFR1-05-2700 | Water sprinkles | 2026-07-06 | 05-Jul-26 A | -162 | Not required
21 | HFR1-05-2040 | Fire Alarm system Testing works | 2026-07-22 | 08-Apr-26 A | -162 | Not required
22 | HFR1-05-1990 | Light current devices installations & Final Inspection | 2026-04-01 | 18-Apr-26 A | -175 | Not required
23 | HFR1-05-2070 | Power System and lighting and lightcurrent Testing (Continuity + Insulation) & Final Inspection | 2026-08-12 | 01-Apr-26 A | -86 | Not required
24 | HFR1-05-2080 | Comission of Panel boards ( cables and testing) | 2026-08-19 | 14-Jun-26 A | -90 | Not required
25 | HFR1-05-2100 | Comission of Lighting Fixtures Installations /LED lighting | 2026-08-30 | 29-Jun-26 A | -100 | Not required
26 | HFR1-05-1530 | External Paint Touch-up & Inspection | 2026-06-08 | 06-Aug-26 A | -100 | Not required
27 | HFR1-05-1480 | External Paint Primer + Final Coat | 2026-05-12 | 08-Aug-26 A | -100 | Not required
28 | HFR1-05-1490 | Epoxy Paint | 2026-05-12 | 16-Aug-26 A | -125 | Not required
29 | HFR1-05-1510 | Cladding | 2026-06-01 | 09-Aug-26 A | -125 | Not required
30 | HFR1-05-1450 | Paint Primer + Putty + Final Coat INSIDE | 2026-05-04 | 23-Aug-26 A | -56 | Not required
31 | HFR1-05-1570 | Specialites Fittings | 2026-07-06 | 01-Sep-26 A | -56 | Not required
32 | HFR1-05-1560 | Signage Layout & Marking Locations | 2026-06-30 | 03-Sep-26 A | -56 | Not required
33 | HFR1-05-1520 | Finishes floor Installation | 2026-06-02 | 09-Jul-26 A | -65 | Not required
34 | HFR1-05-1790 | Testing plumping system & Final Inspection | 2026-08-18 | 04-May-26 A | -65 | Not required
35 | HFR1-05-1650 | Water sprinkles | 2026-05-06 | 07-Jun-26 A | -65 | Not required
38 | HFR1-05-1800 | Fire Fighting Testing (Hydrostatic Test) & Final Inspection | 2026-09-06 | 04-May-26 A | -65 | Not required
39 | HFR1-05-2180 | Fire Alarm system Testing works | 2026-05-18 | 14-Apr-26 A | -65 | Not required
40 | HFR1-05-2130 | Light current devices installations & Final Inspection | 2026-04-16 | 27-Apr-26 A | -65 | Not required
43 | HFR1-05-2210 | Power System and lighting and lightcurrent Testing (Continuity + Insulation) & Final Inspection | 2026-06-11 | 07-Apr-26 A | -32 | Not required
44 | HFR1-05-2220 | Comission of Panel boards ( cables and testing) | 2026-06-18 | 14-Jun-26 A | -32 | Not required
45 | HFR1-05-2240 | Comission of Lighting Fixtures Installations /LED lighting | 2026-07-02 | 02-Jul-26 A | -25 | Not required
46 | HFR1-05-4090 | 50mm thk loose gravel toppings | 2026-07-04 | 10-Sep-26 A | -25 | Not required
47 | HFR1-05-3490 | granite Insulation (extruded polystyrene) | 2026-05-18 | 15-Aug-26 A | -25 | Not required
48 | HFR1-05-4230 | External Paint Touch-up & Inspection | 2026-07-07 | 11-Jul-26 A | -25 | Not required
49 | HFR1-05-4120 | External Paint Primer + Final Coat | 2026-07-01 | 09-Jul-26 A | -25 | Not required
50 | HFR1-05-4000 | Paint Primer + Putty + Final Coat INSIDE | 2026-06-25 | 08-Jul-26 A | -25 | Not required
51 | HFR1-05-4010 | Internal Paint Touch-up & Inspection INSIDE | 2026-06-25 | 08-Jul-26 A | -25 | Not required
52 | HFR1-05-3900 | External Paint Surface Preparation | 2026-06-20 | 09-Jul-26 A | -25 | Not required
53 | HFR1-05-3860 | external Paint Surface Preparation INSIDE | 2026-06-20 | 28-Jul-26 A | -65 | Not required
54 | HFR1-05-4020 | Supply and install carpet rolls | 2026-06-25 | 2026-09-22 | -25 | Not required
55 | HFR1-05-3970 | polyisocynurate cover board | 2026-06-29 | 25-Aug-26 A | -31 | Not required
56 | HFR1-05-4300 | Mosque Arch Carpet | 2026-07-13 | 2026-10-05 | -10 | Not required
57 | HFR1-05-4250 | signs for toilets & prayer room | 2026-07-07 | 12-Sep-26 A | -10 | Not required
58 | HFR1-05-4360 | Wood skirting works | 2026-07-19 | 20-Aug-26 A | -10 | Not required
59 | HFR1-05-3930 | Plumping fixtures | 2026-06-24 | 09-May-26 A | -10 | Not required
61 | HFR1-05-3830 | Exasut fans | 2026-06-17 | 09-May-26 A | -10 | Not required
62 | HFR1-05-3240 | steel fence gate | 2026-06-02 | 2026-09-16 | -35 | Not required
67 | HFR1-05-3270 | install galvanized steel fence | 2026-06-13 | 14-Apr-26 A | -35 | Not required
68 | HFR1-05-3780 | Testing firefighting | 2026-06-02 | 18-May-26 A | -35 | Not required
69 | HFR1-05-4150 | Street Lighting Testing (Megger + Lighting Test) & Final Inspection | 2026-05-19 | 27-Apr-26 A | -35 | Not required
71 | HFR1-05-4320 | ROAD Laying bituminous second asphalt base layer | 2026-08-19 | 10-Sep-26 A | -35 | Not required
73 | HFR1-05-4560 | Concrete Works external steps | 2026-09-05 | 21-Jul-26 A | -35 | Not required
74 | HFR1-05-4550 | ROAD subgrade laye Interlocking Paving Blocks | 2026-09-06 | 06-Aug-26 A | -35 | Not required
75 | HFR1-05-4390 | ROADTack Coat (RC2) | 2026-08-25 | 2026-12-03 | -35 | Not required
76 | HFR1-05-4480 | ROAD interlocking block pavers | 2026-09-02 | 25-Aug-26 A | -35 | Not required
77 | HFR1-05-3610 | ROAD execute subgrade layer including Watering and compaction | 2026-07-23 | 13-Jun-26 A | -35 | Not required
78 | HFR1-05-4510 | ROAD Interlock install concrete parking bumpers | 2026-09-06 | 25-Aug-26 A | -35 | Not required
79 | HFR1-05-4540 | ROAD Road Marking thermoplastic traffic lines | 2026-09-05 | 2026-12-08 | -35 | Not required
80 | HFR1-05-4530 | ROAD single I.P.E. post Road signs-Asphalt install traffic signs | 2026-09-05 | 10-Sep-26 A | -35 | Not required
81 | HFR1-05-4570 | Outdoor Granite works | 2026-09-05 | 01-Sep-26 A | -35 | Not required
82 | HFR1-05-4520 | ROAD Asphalt Reflective Road Markings | 2026-09-06 | 2026-12-09 | -35 | Not required
83 | HFR1-05-3990 | ROAD Application of prime coat | 2026-08-06 | 06-Sep-26 A | -35 | Not required
84 | HFR1-05-4500 | ROAD InterlockWalkway -pedestrian interlocking block pavers | 2026-08-31 | 12-Aug-26 A | -35 | Not required
85 | HFR1-05-4140 | ROAD execute bituminous base course asphalt layer | 2026-08-13 | 07-Sep-26 A | -35 | Not required
88 | HFR1-05-4440 | ROAD Bituminous Wearing Course Asphalt | 2026-08-31 | 07-Sep-26 A | -35 | Not required
89 | HFR1-05-4420 | Test For Roads | 2026-09-13 | 23-Jun-26 A | -35 | Not required
90 | HFR1-05-4630 | Test For Electrical Works | 2026-09-03 | 22-Jun-26 A | -35 | Not required
91 | HFR1-05-4600 | Test For Water Utilities | 2026-04-01 | 26-Apr-26 A | -35 | Not required
92 | HFR1-05-4430 | Test For Pump Room | 2026-07-21 | 14-Jun-26 A | -35 | Not required

## Sheet2
Activity ID | Activity Name | BL Project Start | Start | Schedule % Complete | Performance % Complete
HFR1-05-4380 | Procurement Complete |  |  | 100% | 0%
HFR1-05-2990 | Completion of Engneering and Material |  |  | 100% | 0%
HFR1-05-4590 | Site Works & External Networks Completed |  |  | 100% | 0%
HFR1-05-4620 | Main Buildings Architectural Completed |  |  | 100% | 0%
HFR1-05-3390 | Main Buildings Structure Completed |  |  | 100% | 0%
HFR1-05-4400 | Mosque Works Completed |  |  | 100% | 0%
HFR1-05-5570 | Material Delivery for Aggregate Base Course | 2026-01-29 | 07-Sep-26 A | 100% | 90%
HFR1-05-9130 | Material Delivery for Pavement Markings | 2026-05-24 | 01-Sep-26 A | 100% | 80%
HFR1-05-9390 | Material Delivery for Logo | 2026-04-22 | 10-Aug-26 A | 100% | 80%
HFR1-05-2730 | External Paint Touch-up & Inspection | 2026-05-30 | 06-Aug-26 A | 100% | 85%
HFR1-05-2630 | External Paint Primer + Final Coat | 2026-05-03 | 06-Aug-26 A | 100% | 85%
HFR1-05-2640 | Epoxy Paint | 2026-05-03 | 15-Aug-26 A | 100% | 85%
HFR1-05-2690 | Cladding | 2026-05-19 | 10-Aug-26 A | 100% | 95%
HFR1-05-2600 | Paint Primer + Putty + Final Coat INSIDE | 2026-04-25 | 24-Aug-26 A | 100% | 80%
HFR1-05-2820 | Specialites Fittings | 2026-07-13 | 01-Sep-26 A | 100% | 95%
HFR1-05-2790 | Signage Layout & Marking Locations | 2026-07-07 | 03-Sep-26 A | 100% | 45%
HFR1-05-2770 | Metal works | 2026-07-01 | 06-Jul-26 A | 100% | 100%
HFR1-05-2720 | Finishes floor Installation | 2026-05-20 | 09-Jul-26 A | 100% | 95%
HFR1-05-2900 | Testing plumping system & Final Inspection | 2026-09-06 | 04-May-26 A | 100% | 95%
HFR1-05-2700 | Water sprinkles | 2026-07-06 | 05-Jul-26 A | 100% | 95%
HFR1-05-2040 | Fire Alarm system Testing works | 2026-07-22 | 08-Apr-26 A | 100% | 85%
HFR1-05-1990 | Light current devices installations & Final Inspection | 2026-04-01 | 18-Apr-26 A | 100% | 95%
HFR1-05-2070 | Power System and lighting and lightcurrent Testing (Continuity + Insulation) & Final Inspection | 2026-08-12 | 01-Apr-26 A | 100% | 95%
HFR1-05-2080 | Comission of Panel boards ( cables and testing) | 2026-08-19 | 14-Jun-26 A | 100% | 95%
HFR1-05-2100 | Comission of Lighting Fixtures Installations /LED lighting | 2026-08-30 | 29-Jun-26 A | 100% | 95%
HFR1-05-1530 | External Paint Touch-up & Inspection | 2026-06-08 | 06-Aug-26 A | 100% | 85%
HFR1-05-1480 | External Paint Primer + Final Coat | 2026-05-12 | 08-Aug-26 A | 100% | 85%
HFR1-05-1490 | Epoxy Paint | 2026-05-12 | 16-Aug-26 A | 100% | 85%
HFR1-05-1510 | Cladding | 2026-06-01 | 09-Aug-26 A | 100% | 95%
HFR1-05-1450 | Paint Primer + Putty + Final Coat INSIDE | 2026-05-04 | 23-Aug-26 A | 100% | 70%
HFR1-05-1570 | Specialites Fittings | 2026-07-06 | 01-Sep-26 A | 100% | 95%
HFR1-05-1560 | Signage Layout & Marking Locations | 2026-06-30 | 03-Sep-26 A | 100% | 45%
HFR1-05-1520 | Finishes floor Installation | 2026-06-02 | 09-Jul-26 A | 100% | 95%
HFR1-05-1790 | Testing plumping system & Final Inspection | 2026-08-18 | 04-May-26 A | 100% | 95%
HFR1-05-1650 | Water sprinkles | 2026-05-06 | 07-Jun-26 A | 100% | 90%
HFR1-05-1800 | Fire Fighting Testing (Hydrostatic Test) & Final Inspection | 2026-09-06 | 04-May-26 A | 52.94% | 90%
HFR1-05-2180 | Fire Alarm system Testing works | 2026-05-18 | 14-Apr-26 A | 100% | 90%
HFR1-05-2130 | Light current devices installations & Final Inspection | 2026-04-16 | 27-Apr-26 A | 100% | 95%
HFR1-05-2210 | Power System and lighting and lightcurrent Testing (Continuity + Insulation) & Final Inspection | 2026-06-11 | 07-Apr-26 A | 100% | 95%
HFR1-05-2220 | Comission of Panel boards ( cables and testing) | 2026-06-18 | 14-Jun-26 A | 100% | 95%
HFR1-05-2240 | Comission of Lighting Fixtures Installations /LED lighting | 2026-07-02 | 02-Jul-26 A | 100% | 95%
HFR1-05-4090 | 50mm thk loose gravel toppings | 2026-07-04 | 10-Sep-26 A | 100% | 40%
HFR1-05-3490 | granite Insulation (extruded polystyrene) | 2026-05-18 | 15-Aug-26 A | 100% | 90%
HFR1-05-4230 | External Paint Touch-up & Inspection | 2026-07-07 | 11-Jul-26 A | 100% | 90%
HFR1-05-4120 | External Paint Primer + Final Coat | 2026-07-01 | 09-Jul-26 A | 100% | 90%
HFR1-05-4000 | Paint Primer + Putty + Final Coat INSIDE | 2026-06-25 | 08-Jul-26 A | 100% | 95%
HFR1-05-4010 | Internal Paint Touch-up & Inspection INSIDE | 2026-06-25 | 08-Jul-26 A | 100% | 95%
HFR1-05-3900 | External Paint Surface Preparation | 2026-06-20 | 09-Jul-26 A | 100% | 95%
HFR1-05-3860 | external Paint Surface Preparation INSIDE | 2026-06-20 | 28-Jul-26 A | 100% | 95%
HFR1-05-4020 | Supply and install carpet rolls | 2026-06-25 | 2026-09-22 | 100% | 0%
HFR1-05-3970 | polyisocynurate cover board | 2026-06-29 | 25-Aug-26 A | 100% | 90%
HFR1-05-4300 | Mosque Arch Carpet | 2026-07-13 | 2026-10-05 | 100% | 0%
HFR1-05-4250 | signs for toilets & prayer room | 2026-07-07 | 12-Sep-26 A | 100% | 50%
HFR1-05-4360 | Wood skirting works | 2026-07-19 | 20-Aug-26 A | 100% | 95%
HFR1-05-3930 | Plumping fixtures | 2026-06-24 | 09-May-26 A | 100% | 80%
HFR1-05-3830 | Exasut fans | 2026-06-17 | 09-May-26 A | 100% | 80%
HFR1-05-3240 | steel fence gate | 2026-06-02 | 2026-09-16 | 100% | 0%
HFR1-05-3270 | install galvanized steel fence | 2026-06-13 | 14-Apr-26 A | 100% | 40%
HFR1-05-3780 | Testing firefighting | 2026-06-02 | 18-May-26 A | 100% | 90%
HFR1-05-4150 | Street Lighting Testing (Megger + Lighting Test) & Final Inspection | 2026-05-19 | 27-Apr-26 A | 100% | 90%
HFR1-05-4320 | ROAD Laying bituminous second asphalt base layer | 2026-08-19 | 10-Sep-26 A | 100% | 40%
HFR1-05-4560 | Concrete Works external steps | 2026-09-05 | 21-Jul-26 A | 100% | 90%
HFR1-05-4550 | ROAD subgrade laye Interlocking Paving Blocks | 2026-09-06 | 06-Aug-26 A | 100% | 90%
HFR1-05-4390 | ROADTack Coat (RC2) | 2026-08-25 | 2026-12-03 | 100% | 0%
HFR1-05-4480 | ROAD interlocking block pavers | 2026-09-02 | 25-Aug-26 A | 100% | 95%
HFR1-05-3610 | ROAD execute subgrade layer including Watering and compaction | 2026-07-23 | 13-Jun-26 A | 100% | 95%
HFR1-05-4510 | ROAD Interlock install concrete parking bumpers | 2026-09-06 | 25-Aug-26 A | 100% | 90%
HFR1-05-4540 | ROAD Road Marking thermoplastic traffic lines | 2026-09-05 | 2026-12-08 | 100% | 0%
HFR1-05-4530 | ROAD single I.P.E. post Road signs-Asphalt install traffic signs | 2026-09-05 | 10-Sep-26 A | 100% | 50%
HFR1-05-4570 | Outdoor Granite works | 2026-09-05 | 01-Sep-26 A | 100% | 70%
HFR1-05-4520 | ROAD Asphalt Reflective Road Markings | 2026-09-06 | 2026-12-09 | 100% | 0%
HFR1-05-3990 | ROAD Application of prime coat | 2026-08-06 | 06-Sep-26 A | 100% | 60%
HFR1-05-4500 | ROAD InterlockWalkway -pedestrian interlocking block pavers | 2026-08-31 | 12-Aug-26 A | 100% | 90%
HFR1-05-4140 | ROAD execute bituminous base course asphalt layer | 2026-08-13 | 07-Sep-26 A | 100% | 80%
HFR1-05-4440 | ROAD Bituminous Wearing Course Asphalt | 2026-08-31 | 07-Sep-26 A | 100% | 80%
HFR1-05-4420 | Test For Roads | 2026-09-13 | 23-Jun-26 A | 27.27% | 80%
HFR1-05-4630 | Test For Electrical Works | 2026-09-03 | 22-Jun-26 A | 91.67% | 75%
HFR1-05-4600 | Test For Water Utilities | 2026-04-01 | 26-Apr-26 A | 100% | 95%
HFR1-05-4430 | Test For Pump Room | 2026-07-21 | 14-Jun-26 A | 100% | 85%